## Title Page
Request for Proposals
​​RFP #C043776
Converged Eligibility and Enrollment (E&E) System and Appeals Management System (AMS)
Attachment E
RFP Requirements Matrix

## Instructions
Instructions
The requirements of the Converged E&E System and AMS RFP are categorized into the following tabs in this workbook:
Office of Health Insurance Programs Medicaid Enterprise System Standards
Project Management
Transition-In
Maintenance and Operations
Implementation Approach
Business Requirements for the Converged E&E System
Solution Development Life Cycle
Data Conversion and Migration
Training
Deployment
Hypercare
System Testing
Organizational Change Management
Major System Updates, Capacity-Based Team, and Enhancements
Artificial Intelligence Usage
Centers for Medicare & Medicaid Services Certification and Compliance
Transition-Out
Staffing
Office Facility
Reporting
Information Technology
Security and Privacy
Deliverables
Service Level Agreements
The Bidder must review each requirement and must indicate whether the Bidder complies with the requirement (Yes or No) in column C (or column D for Business Requirements). If the Bidder's response to the question in column C (or column D for Business Requirements) for any requirement is "No," the Bidder must provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent in the corresponding cell in column D (or column E for Business Requirements).
For a complete list and further details of deliverables, see Section 5.8 - Deliverables in the RFP.
Where applicable, reference to the relevant Service Level Agreements (SLA) is indicated. For further details on SLAs, see Attachment F - Service Level Agreements (SLAs).
Where applicable, hyperlinks are provided in footnotes at the bottom of each tab.
Yes
No

## OHIP MES Standards
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
GS-01 | The Contractor must adhere to the Office of Health Insurance Programs (OHIP) Medicaid Enterprise System (MES) Standards throughout the Contract term. This includes compliance with the most current version of the OHIP MES Standards and with any additional OHIP MES Standards developed by the Department during the Contract term.
GS-02 | The Contractor must comply with each OHIP MES Standard requirement in accordance with its assigned compliance tier, as specified in Appendix B of the applicable Domain Document.
GS-03 | The Contractor must adhere to the OHIP Standard Deviation Process (SDP) for any mandatory (“must”) compliance requirement from which the Contractor seeks to deviate during the Contract term and prior to implementing a noncompliant approach.
GS-04 | The Contractor must provide written justification to the Department for any request to deviate from a strong recommendation (“should”) requirement during the Contract term and prior to implementing a noncompliant approach.
GS-05 | The Contractor must provide the Department with access to systems, records, personnel, and any other necessary resources during a Standards audit.
GS-06 | The Contractor must develop, maintain, and update all applicable deliverables, artifacts, and project documentation in accordance with the OHIP MES Standards throughout the Contract term.
GS-07 | The Contractor must comply with the tools specified in the OHIP Infrastructure and Operations Domain Document, Preferred Operational Tools Standard. If the Contractor seeks to deviate from the Preferred Operational Tools List to support a business function, the Contractor may request a change, including a written justification, detailed cost information, and documentation demonstrating the ability to meet the Department's requirements at a minimum.

## Project Management
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
PM-1 | The Contractor must manage the project using a methodology aligned with the most recent edition of the Project Management Institute (PMI) Project Management Book of Knowledge (PMBOK®).
PM-2 | The Contractor must establish and maintain compatibility with the Department’s standard suite of desktop tools for all project plans and documentation, as identified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard.
PM-3 | The Department will provide the Contractor with the existing Medicaid Eligibility and Client Management (MECM) System and Appeals Management System (AMS) Project Management Plan (PMP). The most recent PMP is provided in Exhibit G.17 – MECM System and AMS Project Management Plan. The Department may provide an updated version of the MECM System and AMS PMP following Contractor onboarding and the Engagement Kick-Off meeting and presentation, as necessary. The Contractor must update the provided PMP and associated sub-management plans to align with the requirements of this Request for Proposals (RFP) and with changes that occur during the Contract term to create the Converged Eligibility and Enrollment (E&E) System and AMS PMP. The Contractor must submit this PMP to the Department for review and approval.
PM-4 | Using the MECM System and AMS PMP provided by the Department, the Contractor must update, develop, deliver, maintain, and execute the Converged E&E System and AMS PMP to manage the project from project initiation through the end of the Contract term. Updates to the PMP must comply with the requirements of this RFP. The PMP must include, at a minimum, the following sub-management plans: • Governance Management Plan • Stakeholder Management Plan • Communication Management Plan • Budget Management Plan • Quality Management Plan • Staff and Resource Management Plan • Risk and Issue Management Plan • Scope Management Plan • Procurement and Licensing Management Plan • Project Change Control Plan (PCCP) • Schedule Management Plan • Document Management Plan
PM-5 | The Contractor must maintain and update the PMP and its sub-management plans as the project evolves, reflecting process improvements, lessons learned, and the Department’s feedback and inputs, as requested. The Contractor must submit an updated PMP to the Department for review and approval on a quarterly basis, or as directed by the Department.
PM-6 | The Contractor must execute and oversee all activities defined in the Department-approved PMP and associated sub-management plans throughout the Contract term.
PM-7 | The Contractor must collaborate with key Department stakeholders to prepare for the Engagement Kick-Off meeting and presentation. The purpose of the Engagement Kick-Off meeting and presentation is to establish a shared understanding of project objectives, schedule, roles and responsibilities, and required deliverables.
PM-8 | The Contractor must schedule and facilitate an Engagement Kick-Off meeting and presentation with the Department and all appropriate stakeholders within four (4) weeks of the Contract start date. The Contractor must involve all key stakeholders, including the Incumbent Contractor. Additional participants must be determined in collaboration with the Department.
PM-9 | The Contractor must develop an Engagement Kick-Off presentation in Microsoft PowerPoint and other relevant materials that address, at a minimum, the following: • Project goals and objectives • Scope of work • Schedule and milestones, including the Transition-In period • Roles and responsibilities • Communication approach • Risk strategies • Next steps
PM-10 | The Contractor must schedule the Engagement Kick-Off meeting and presentation within two (2) weeks of Department onboarding of Key and Support Staff deemed necessary for the Engagement Kick-Off. The Department will be the final authority to determine the Engagement Kick-Off meeting and presentation date.
PM-11 | The Contractor must prepare meeting agendas that clearly describe the meeting purpose to support invitee preparation and promote effective use of attendee time.
PM-12 | The Contractor must distribute meeting agendas and supporting materials at least two (2) business days prior to the meeting to allow the Department review of meeting materials in advance.
PM-13 | The Contractor must distribute meeting minutes within one (1) business day after each meeting.
PM-14 | The Contractor must conduct a weekly operational meeting with the Department to report, at a minimum, on the following: • Performance issues • Converged E&E System and AMS availability • Discontinuity of service incidents and resolutions • Maintenance plans and priorities for the Converged E&E System and the A
PM-15 | The Contractor must develop a Document Management Plan that includes, at a minimum, the following components: • How project documents will be managed throughout their life cycle, including creation, storage, version control, and disposal • Department-approved tools used to store, manage, and maintain project documents • Naming conventions, file formats, and metadata standards for organizing and categorizing project documents • Document review and approval processes, including stakeholder roles and methods for obtaining input and feedback
PM-16 | The Contractor must store and maintain all project documentation, including working and editable versions, in the Department-controlled repository designated and managed by the Department.
PM-17 | The Contractor must update key documentation, as identified by the Department, and store and archive all engagement documentation, deliverable expectation documents (DEDs), deliverables, and artifacts in a location approved by the Department and in alignment with the Document Management Plan.
PM-18 | The Contractor must facilitate a series of planning work sessions in collaboration with the Department to gather the information and input needed to create a Converged E&E System and the AMS Project Roadmap. The Project Roadmap must include, at a minimum, the following components: • Alignment with stakeholder vision and objectives • Refined or updated engagement goals and objectives • Approach for executing the contracted scope of work related to the following: • Transition-In activities, as described in Section 5.2.3 – Transition-In • Converged E&E System Implementation, as described in Section 5.2.5.1 – Implementation Approach • Major System Updates and Enhancements, as described in Section 5.2.8 – Major System Updates, Capacity-Based Team, and Enhancements • Identification of initial high-priority updates and enhancements and an implementation timeline for all known improvements
PM-19 | The Contractor must develop, deliver, maintain, and execute the Converged E&E System and AMS Project Roadmap. The Project Roadmap must describe, at a minimum, the following: • Transition-In activities, at a high level • Maintenance and Operations (M&O) transition • Converged E&E System Implementation • Improvements vision • Time frames and timelines • Dependencies • Key milestones • Preliminary Release Schedule • First Release Plan and goals
PM-20 | The Contractor must maintain and update the Converged E&E System and AMS Project Roadmap throughout the Contract term to reflect changes to scope, objectives, timelines, and Release plans related to M&O, system implementation and improvements. The Contractor must update the Project Roadmap quarterly, at a minimum.
PM-21 | The Contractor must maintain and update the Governance Structure throughout the Contract term. The Governance Structure must include, at a minimum, the following: • Roles, responsibilities, and decision-making authority of all stakeholders • Communication and reporting channels across governance levels • Frequency, format, and content of status reports and stakeholder updates • Issue escalation processes for matters that cannot be resolved at lower governance levels • Procedures for complying with applicable State and federal policies, rules, and regulations • Process for managing and updating the Governance Structure as needed
PM-22 | The Contractor must maintain and adhere to the chosen Solution Development Life Cycle (SDLC) methodology, as described in Section 5.2.5.3 – Solution Development Life Cycle. The Contractor must update or replace the SDLC described in the provided PMP to align with the requirements of the chosen SDLC methodology. The Contractor must further elaborate on SDLC details. The SDLC methodology must include, at a minimum, the following: • Methodologies, approaches, techniques, and tools used to manage and execute the SDLC phase • SDLC phases, including Design, Development, and Implementation (DDI), Hypercare, and other applicable phases • Activities conducted and deliverables developed during each SDLC phase • Activities of the Architecture Review Board (ARB), including its review of all proposed changes to confirm alignment with established architectural standards and strategic goals
PM-23 | The Contractor must maintain and update the Stakeholder Management Plan. The plan must include, at a minimum, the following: • Contractor’s approach to stakeholder identification • How the Contractor will plan, manage, and monitor stakeholder engagement, including engagement with the Department, other State agencies, and external entities, such as the Centers for Medicare & Medicaid Services (CMS) and trading partners • Activities, participation levels, and communication approaches used to promote appropriate engagement for each stakeholder group
PM-24 | The Contractor must develop a comprehensive summary that identifies all modifications made to documents provided by the Department. The summary must include source information and document versions referenced during updates. Upon request from the Department, the Contractor must conduct a walkthrough meeting of the summary to support understanding of deployed functionality and verification of changes made.
PM-25 | The Contractor must maintain and update the Communication Management Plan. The plan must include, at a minimum, the following: • Communication functions and responsibilities • Communication methods, tools, and techniques • Schedule and timeline for standard recurring communications, including meetings, documents, and media • Strategy for communicating with stakeholders regarding the project • Proposed communication timelines designed to support effective information exchange • Recommendations for communication materials • Methodologies used to produce routine and executive-level communications, as well as system and operational documentation • Objective approaches and methods for measuring the effectiveness of communications
PM-26 | The Contractor must maintain and update the Deliverable Management Plan. The plan must include, at a minimum, the following: • How deliverables will be managed throughout the Contract term, including identification, creation, coordination, review, evaluation, change management, approval, and submission processes • Schedule and criteria for submitting each deliverable in accordance with applicable acceptance criteria and timelines • Processes for reporting deliverable status to the Department and other identified stakeholders
PM-27 | The Contractor must develop and submit a DED for each deliverable for Department review and approval prior to deliverable submission, in accordance with the Integrated Master Schedule (IMS). Each DED must include, at a minimum, the following: • Table of contents • Deliverable format • Methodology for creating the deliverable • Applicable OHIP MES Standards • Deliverable requirements • Deliverable content • Deliverable acceptance criteria • Deliverable schedule with key dates • Key resources and responsibilities The Contractor must complete deliverables in accordance with Department-approved DEDs and submit deliverables to the Department for review and approval in accordance with the approved schedule.
PM-28 | All deliverables, materials, and other submissions provided by the Contractor must meet the form and content requirements specified by the Department and are subject to Department review and approval.
PM-29 | The Contractor must maintain and update all Project Management (PM) deliverables and documentation through the end of the Contract term.
PM-30 | The Contractor must provide the following PM deliverables for Department review and approval: • Engagement Kick-Off Meeting/Presentation • Converged E&E System and AMS Project Roadmap • Converged E&E System and AMS PMP • IMS • Contract Management Plan • Deliverable Management Plan • Weekly Status Reports (DDI and M&O) • Monthly Status Reports (DDI and M&O) • Contract Closeout Plan • Contract Closeout documentation
PM-31 | The Contractor must submit completed deliverables by the Department-approved dates for Department review and approval. Each deliverable must address all components required by the Contract, applicable Task Order, and any other items subsequently agreed to through meetings and planning sessions. The Department must review and approve all deliverables, including resubmitted deliverables, as applicable.
PM-32 | The Contractor must submit final copies of each deliverable to the Department in the quantity and on the dates specified in Department-approved plans.
PM-33 | The Contractor must submit an electronic copy of all deliverables unless otherwise directed by the Department. Electronic copies must be provided on media and in formats approved by the Department.
PM-34 | The Contractor must develop deliverables collaboratively with the Department. This collaborative approach must include frequent communication with appropriate Department staff and, as applicable, third-party MES solution vendor staff regarding deliverable scope, objectives, outcomes, and content. Collaboration must begin during the initial stages of deliverable development and be followed by periodic reviews of progress with the Department and other appropriate staff.
PM-35 | The Contractor must provide walkthroughs of deliverables, in their entirety, with the Department when requested or as needed, prior to formal submission.
PM-36 | The Contractor must include the Department review period for each draft deliverable included in the IMS. If requested, the Contractor must provide a walkthrough of each final deliverable with Department staff during the deliverable review period.
PM-37 | Upon submission of each deliverable, including initial and final submissions, the Contractor must certify that an internal quality review has been conducted and that the deliverable is complete and accurate.
PM-38 | The Contractor must submit all Contract correspondence, including routine correspondence and deliverables, using the Department’s standard suite of electronic desktop tools in native formats, such as Microsoft Word, Excel, and Visio. All images and embedded objects must be provided in editable formats. The Contractor must maintain consistent appearance and formatting across all Contract correspondence and deliverables. Each deliverable submission must include a transmittal document and a copy of the Department-approved DED. Deliverable transmittals must follow the Department’s transmittal process and templates, as defined in the Deliverable Management Plan.
PM-39 | For any deliverable or artifact, at the Department's request, the Contractor must produce a redacted version that redacts sensitive information in alignment with IRS Publication 1075 and NIST SP 800-53 for public release.
PM-40 | If the Department identifies deficiencies in a deliverable, the Department will notify the Contractor of the required corrections. The Contractor must address all identified deficiencies and resubmit the deliverable within five (5) business days of receipt of the Department’s notice, excluding State holidays, unless a different time frame is mutually agreed to. For each resubmission, the Contractor must clearly identify all revisions and provide responses to all Department comments.
PM-41 | The Contractor must not modify a previously accepted deliverable without prior Department approval.
PM-42 | The Contractor must maintain and update the Budget Management Plan. The plan must include, at a minimum, the following: • Procedures and responsibilities for budget management, including allocation, tracking, and control of financial resources • Cost estimation methods and tools used to determine budget requirements for each Task Order, project phase, or deliverable • Process for monitoring expenditures and maintaining alignment with approved budgets and Task Orders • Mechanisms for managing and approving budget changes, including cost overruns and scope adjustments • Reporting requirements and frequency for providing project financial updates to stakeholders • Procedures for reconciling and closing the budget at completion of the Contract term
PM-43 | The Contractor must not use a proprietary invoicing mechanism and must supply the Department with all necessary documentation to comply with audits.
PM-44 | The Contractor must update budget and cost documentation every two (2) weeks or as requested by the Department.
PM-45 | The Contractor must maintain and update the Quality Management Plan. The plan must include, at a minimum, the following: • Roles and responsibilities of the quality assurance (QA) team members • Quality management process and QA activities that will be implemented throughout the Contract term • Basis for judging product quality • Schedule for periodic QA meetings
PM-46 | The Contractor must maintain and update the Staff and Resource Management Plan. The plan must include, at a minimum, the following: • Staff member roles and responsibilities • Onboarding and offboarding processes • Timing of onboarding, offboarding, and credentialing for Key Staff positions • Processes for training, retaining, and transitioning staff • Detailed tasks and plans for all staff
PM-47 | The Contractor must submit the initial formal deliverable Staff and Resource Management Plan within ten (10) business days of Contract award and update the plan as required throughout the Contract term. The plan must detail onboarding and offboarding processes, timelines for replacement staff, escalation procedures for staffing issues, and collaboration protocols with Department teams.
PM-48 | The Contractor must maintain and update the Risk and Issue Management Plan. The plan must include, at a minimum, the following: • Process for identifying the existence of risks and issues • Process for reporting and documenting risks and issues, including collaboration with the Department • Process for assessing risks and determining risk tolerance strategies, including accept, avoid, transfer, and mitigate • Framework for assessing and managing security risks associated with third-party vendors, subcontractors, or software providers, including security due diligence, ongoing monitoring, and compliance validation • Tracking processes for issue assessment, categorization, prioritization, mitigation strategies, status, actions, and resolution • Methods for monitoring and controlling risks and issues • Risk and issue management escalation strategy that defines escalation criteria and identifies individuals responsible for addressing risks and issues • Process for updating and notifying the Department of changes to these procedures
PM-49 | As a component of the Risk and Issue Management Plan, the Contractor must provide a Risk and Issue Log using in the Department’s preferred requirements management tool as defined in the OHIP Infrastructure and Operations Domain Document, Preferred Operational Tools Standard). The Risk and Issue Log must include, at a minimum, the following: • Risk or issue name • Description of the risk or issue • Impact of the risk or issue on the project • Categorization and prioritization of the risk or issue • Resource responsible for monitoring the risk or resolving the issue • Action plans and mitigation strategies • Planned resolution date
PM-50 | The Contractor must prepare formal risk and issue assessments at the start of each project phase and at intervals determined by the Department. The Department will review and approve the risk and issue assessments and associated mitigation strategies.
PM-51 | The Department and the Contractor must jointly identify and classify risks and issues to be added to the Risk and Issue Log, develop mitigation strategies, and update risk and issue status, as necessary.
PM-52 | The Contractor must report to the Department any risk or issue not yet included in the Risk and Issue Log as soon as the risk or issue is identified.
PM-53 | The Contractor must develop a Procurement and License Management Plan. The plan must include, at a minimum, the following: • Procedures for purchasing or acquiring products or services from third-party vendors by the Contractor to maintain or support the Converged E&E System and the AMS, or on behalf of the Department • Process for identifying and presenting potential procurements to the Department, including the selection and cost details, and obtaining the Department’s consent • Process for communicating, tracking, and maintaining procurement terms and conditions
PM-54 | The Contractor is responsible for establishing and securing license agreements that comply with operational requirements, safeguard the Department’s ownership rights, preserve New York State (NYS) Medicaid, CHPlus, BHP, and QHP program continuity, and support CMS and Department compliance requirements.
PM-55 | The Contractor must maintain and update the PCCP. The plan must include, at a minimum, processes for the following: • Project Change Request (PCR) submission, including requests for customizations, configurations, additions, or deletions to the Converged E&E System and the AMS, and required submission information • Assessment of requested changes and impacts on the overall system • Cost and schedule changes • Proposed solutions • Department review and approval The plan must also include, at a minimum, the following: • Use and maintenance of the Department’s preferred Information Technology (IT) Service Management (ITSM) tool (refer to the OHIP Infrastructure and Operations Domain Document, Preferred Operational Tools Standard for additional details) to document PCRs, capture associated data, and track the status of submitted requests • Project Change Control (PCC) roles and responsibilities • Schedule for PCC activities, including submissions, meetings, reviews, and related documentation
PM-56 | The Contractor must maintain and update the Schedule Management Plan. The plan must include, at a minimum, the following: • Process for creating and maintaining the IMS • Approach for planning, scheduling, and documenting project work, including identification and sequencing of activities, estimation of effort and duration, and establishment of dependencies • Roles and responsibilities of team members involved in schedule management and development • Methods and tools used to create, update, maintain, and communicate the IMS, including standard schedule structures and data elements • Establishment of a baseline schedule against which actual progress will be measured and tracked • Process for identifying and addressing schedule deviations or delays • Procedures for monitoring and reporting schedule performance to stakeholders
PM-57 | The Contractor must take a proactive approach tor scope management and submit a Scope Management Plan that describes the approach, policies, and procedures used to manage project scope.
PM-58 | The Contractor must create and maintain all Business Architecture documentation in accordance with the OHIP Solution Delivery Domain Document, Business and Technical Architecture Standard, such as functional process flows, using the Department’s preferred Enterprise Architecture tool, as identified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard. Any updates to the business architecture must be reviewed and approved by the ARB.
PM-59 | The Contractor must comply with Department-established architecture standards for all Business Architecture documentation. This includes requirements such as hyperlinking process flow functionality to current-state functional requirements and functional design specifications and aligning documentation with standards such as the Medicaid Information Technology Architecture (MITA) standards.
PM-60 | The Contractor must develop a Contract Management Plan that describes the approach for managing the Contract efficiently and effectively and includes, at a minimum, the following: • Contract scope • Roles and responsibilities • Contract performance monitoring process • Contract issue and dispute resolution • Contract changes process • Risk management • Reporting requirements, including Service Level Agreements (SLAs) defined in this RFP and other applicable RFP requirements • Contract closeout procedures • Assumptions, Constraints, Dependencies
PM-61 | The Contractor must develop, maintain, and execute an IMS that includes, at a minimum, the following: • Activities, tasks, and subtasks with clear and meaningful names and descriptions • Tasks or subtasks for the following: o Contractor development of each deliverable o Department review of each deliverable o Contractor revision of each deliverable after Department review o Department re-review of each deliverable following Contractor revision o Additional rounds of Department review and Contractor revision, as needed o Department approval of each deliverable • Project milestones for PM, M&O, DDI, and system improvements • Start and end dates for tasks • Estimated task duration • Task dependencies • Critical path • Custom task and resource fields, as requested by the Department • Named resources • Appropriate Contractor, Department, and trading partner resource assignments, including estimated hours Near-term tasks (defined as tasks initiating within one hundred and twenty [120] days) must have actual resource names assigned. Tasks that are not near-term may have generic resource titles or teams assigned.
PM-62 | The IMS must include input from Department resources, identify all activities and tasks required for each deliverable milestone, and be organized by project phase.
PM-63 | The Contractor must incorporate any agreed-upon changes into the IMS, as approved by the Department. The IMS must identify dependencies and expectations for the Department, the Contractor, and other stakeholder staff.
PM-64 | The Contractor must maintain, modify, and re-estimate milestones, activities, tasks, and subtasks, including associated resources, hours, and durations, throughout the Contract term.
PM-65 | The Contractor must provide the IMS in the native format of the Department’s preferred PM tool, as specified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard, and in Microsoft Excel or Portable Document Format (PDF) for monthly updates.
PM-66 | The Contractor must work collaboratively with the Department and other stakeholders to determine IMS details, including tasks, durations, dependencies, resources, and level of effort.
PM-67 | The Contractor must update and maintain the IMS at least weekly to align with Weekly Status Reports and reflect progress, status, percent-complete updates, resource allocation changes, and revisions to start and end dates. IMS data must not be more than one week old at any time.
PM-68 | The Contractor must review the IMS weekly with the Department to discuss status updates and proposed changes.
PM-69 | The Contractor must submit proposed changes to the approved IMS to the Department for review and approval in accordance with the PCC process.
PM-70 | The Contractor must update the IMS within one (1) week following Department approval of changes.
PM-71 | The Contractor must develop, demonstrate to the Department, and maintain the project critical path as part of the IMS.
PM-72 | The Contractor must re-baseline the IMS at the Department’s discretion, in accordance with the PCCP.
PM-73 | The Contractor must create and maintain a high-level timeline illustration derived from the IMS that includes key project phases and milestones.
PM-74 | The Contractor must produce various views of the IMS based on the stakeholder groups using or consuming the schedule. Additionally, the IMS must include filters to identify tasks for trading partners and business stakeholders.
PM-75 | The Contractor must prepare and review all status reports with the Department, including the following: • M&O Status Report (daily; weekly; monthly) • Operations Report (daily; weekly) • DDI Status Report (weekly; monthly) For additional details regarding these reports, refer to Section 5.8 – Deliverables and Attachment F – SLAs.
PM-76 | The Contractor must produce a DDI Weekly Status Report that includes, at a minimum, the following: • Reporting period date range (start and end dates) • Status of the overall IMS, phases, milestones, and workstreams • Status of deliverables and SLAs, including completion dates • Schedule slippage, variances, and recommendations for resolution • Tasks and activities missed or behind schedule • Key accomplishments during the reporting period • Information for each pending Release, including the following: o Key performance indicators (KPIs) o Appropriate metrics o Performance management information, including changes to improve data quality and usefulness • Risks and issues with corresponding mitigation plans, including reporting any issue with immediate or detrimental impact to the Converged E&E System or the AMS to Department leadership within one (1) business day • Staffing updates, including the following: o Current staff list, status, and location o Percentage of time allocated to the project for Support Staff o Status of recruitment for Key and Support Staff positions, if vacant • When applicable, a summary of the following: o All defects, issues, and incidents o Open defects, issues, and incidents, including due dates and next steps o Defects, issues, and incidents closed during the reporting period o Summary of open PCRs • Goals and upcoming activities for the next reporting period
PM-77 | The Contractor must develop a DDI Monthly Status Report that includes, at a minimum, the following: • Overall status of the DDI period and milestones • Achievements during the reporting period • Schedule updates • Key risk and issues • Action items • Key decisions
PM-78 | As determined necessary by the Department, the Contractor must conduct knowledge transfer sessions with the Department related to engagement management processes and documentation.
PM-79 | The Contractor must review and incorporate the Department’s Contract closeout processes when developing the Contract Closeout Plan.
PM-80 | The Contractor must develop, deliver, and implement a Contract Closeout Plan that includes, at a minimum, the following: • Contractor approach for closing out the Contract • Deficiency items logged by the Contractor and the Department • Outstanding action items or tasks • Other items deemed relevant to the Closeout phase The Contractor must deliver the Contract Closeout Plan no later than twelve (12) months before the end date of the Contract or upon request of the Department, whichever is earlier.
PM-81 | The Contractor must resolve all Contract closeout expectations that include, at a minimum, the following: • Resolution of documented deficiencies attributed to the Contractor and relevant to current or prior deliverables and artifacts • Completion of Transition-Out activities as described in Section 5.2.11 – Transition-Out • Successful completion of all tasks and deliverables • Fulfillment of all remaining contractual duties as outlined in the Department-approved Contract Closeout Plan
PM-82 | In the twelve (12) months prior to the Contract end date, the Contractor must incorporate details of closeout activities, requirements status, and a summary of fulfillment of services, deliverables, and artifacts into the required reporting described in Section 5.2.11 – Transition-Out, such as Weekly Status Reports.
PM-83 | The Contractor must prepare the Contract Closeout Documentation, which includes, at a minimum, the following: • Summary of the work conducted • Verification that final payments are completed • Acknowledgement that no further legal obligations remain The Contractor must transmit the Contract Closeout Documentation to the Department for signature, electronically or as otherwise agreed upon, by the appropriate parties to officially mark the end of the Contract.
PM-84 | The Contractor must fully collaborate with and support the Department’s designated QA vendor throughout the project life cycle. If an independent verification and validation (IV&V) vendor is onboarded, the Contractor must also support the Department’s IV&V vendor throughout the project life cycle. This collaboration includes, at a minimum, the following: • Timely access to project artifacts and documentation related to planning, design, development, and implementation activities; DEDs; deliverables; test results; and personnel • Participation in interviews, assessments, and meetings • Responses to information requests and findings within five (5) business days, unless otherwise specified in this requirement, in Attachment F –SLAs, or, if an IV&V vendor is onboarded, if CMS requests an accelerated timeline
PM-85 | The Contractor must address all QA vendor recommendations deemed necessary by the Department and incorporate approved corrective actions into the IMS. If an IV&V vendor is onboarded, the Contractor must also address all IV&V vendor recommendations deemed necessary by the Department and incorporate approved corrective actions into the IMS.
PM-86 | The Contractor must not proceed to subsequent implementation phases without Department approval of QA vendor findings and completion of required remediation activities. If an IV&V vendor is onboarded, the Contractor must also not proceed to subsequent implementation phases without Department approval of IV&V vendor findings and completion of required remediation activities.

## Transition-In
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
TI-01 | The Contractor must develop, deliver, maintain, and execute a Transition-In period and documentation that identifies and implements, at a minimum, all activities, tasks, requirements, and deliverables needed for the Contractor to perform Transition-In and assume responsibility for the MECM System and the AMS. This includes managing and delivering all services, functions, and responsibilities for enhancing, operating, and maintaining the MECM System and the AMS and their related subsystems and databases.
TI-02 | The Contractor must develop, deliver, maintain, and execute, the following Transition-In deliverables: • Transition-In Knowledge Transfer Plan • Transition-In Management Plan (TIMP) • System Architecture (SA) Assessment Report • SA Evolution Roadmap • Transition-In PM Plan • Transition-In M&O Plan • Transition-In DDI Plan • Transition-In Schedule • Transition-In Weekly Meeting Agendas, Minutes, and Status Reports • Transition-In Plan Execution • Transition-In Readiness Reviews
TI-03 | The Contractor must participate in all Transition-In and, ultimately, Readiness and Transition Cutover-related activities to confirm that formal ownership of all services has occurred.
TI-04 | The Contractor must maintain sufficient staff throughout the Transition-In period to comply with all requirements identified in this RFP and the Contract.
TI-05 | The Contractor must develop, deliver, maintain, and execute a Transition-In Knowledge Transfer Plan that addresses knowledge transfer tasks, activities, and needs for the Contractor and the Department during the Transition-In period for all transition areas (SA, PM, M&O, and DDI).
TI-06 | The Contractor must execute and oversee all activities specified in the approved Transition-In Knowledge Transfer Plan throughout the Transition-In period.
TI-07 | The Contractor must manage updates to the Transition-In Knowledge Transfer Plan, as needed, throughout the Transition-In period.
TI-08 | The Contractor must provide a Transition-In Knowledge Transfer Plan that includes, at a minimum, the knowledge transfer activities needed to equip and verify that the Contractor’s staff can implement the activities, processes, and procedures required to provide MECM System and AMS assistance for all transition areas (SA, PM, M&O, and DDI).
TI-09 | The Contractor must conduct knowledge transfer activities. The Transition-In Knowledge Transfer Plan will specify the methods to be used. Examples include, at a minimum, the following: • Documentation Reviews – Review of MECM System and AMS documentation relevant to the responsibilities to be assumed by the Contractor’s staff • Question and Answer (Q&A) Sessions – Sessions in which the Contractor should ask the Incumbent Contractor clarifying questions on documentation to validate understanding of processes and procedures • Walkthroughs – Discussions or meetings between the Contractor and the Incumbent Contractor to step through operational processes and procedures, test scripts, system workflows, code development processes, and related artifacts • Training – Learning activities that prepare the Contractor’s staff to implement activities, processes, and procedures needed to support the MECM System and the AMS • Demonstration – Activities that confirm the Contractor’s staff can successfully implement activities, processes, and procedures needed to support the MECM System and the AMS
TI-10 | The Contractor must describe an M&O Knowledge Transfer approach that includes provisions for transitioning all data management functions, including, at a minimum, the following items in the Incumbent Contractor’s Turnover Plan: • Data administration • Database administration • Data encryption • Data archiving • Backup and recovery • Test data management
TI-11 | The Contractor must support the Department’s staff in becoming familiar with all Contractor’s services and any new processes and tools used by the Contractor upon transition from the Incumbent Contractor.
TI-12 | The Contractor must develop, deliver, maintain, and execute a TIMP. The TIMP will act as the Transition-In document to which all other Transition-In deliverables are traceable. The TIMP must include, at a minimum, the following: • Contractor activities to plan, execute, verify, cutover, implement initial operations, and conduct the final review, including assumptions and constraints inherent in the proposed approach and details on environment provisioning and management during the period in which both the Contractor and the Incumbent Contractor are supporting DDI simultaneously • A high-level overview of the planned start and end dates, transition key phases, and milestones that includes, at a minimum, planning, implementing, executing, tracking, and reporting for each transition area and the overall transition effort • Roles and responsibilities for implementing transition activities, including those for the Department, the Incumbent Contractor, and the Contractor, with planning requirements for the Contractor to work with designated Department staff for issue resolution and coordination of activities required to support the transition • Description of how the Contractor will collaborate with the Incumbent Contractor to plan and carry out transition activities, as well as what the Contractor requires of the Incumbent Contractor regarding knowledge transfer, data and information, and assistance for mitigating risk • Risks inherent in the overall transition (e.g., risks related to duration and transition timing, risks associated with the Incumbent Contractor approach) and the Contractor’s planned mitigation measures (e.g., Contingency Plan, Business Continuity and Disaster Recovery [BC/DR] Plan, rollback plan), designed to prevent disruption to MECM System and AMS services • Approach to transition training and knowledge transfer that includes the following: o Knowledge transfer activities the Contractor requires to obtain knowledge from the Incumbent Contractor o Training the Contractor will provide Department staff and business users on newly established transition activities and tools and any changes to how services and functionality will be delivered • Approach to conducting Transition Readiness Reviews for the four (4) transition areas to obtain Department’s approval for Transition Cutover • A section on Quality Management that will guide the Contractor, the Department, and the Incumbent Contractor in managing quality during the Transition-In period • A section on Communication Management that will guide the Contractor, the Department, and the Incumbent Contractor in managing communications during the Transition-In period • A section on Risk Management that will guide the Contractor, the Department, and the Incumbent Contractor in managing risks during the Transition-In period • A section on other transition management requirements (e.g., operations manuals) that will guide the Contractor, the Department, and the Incumbent Contractor in managing additional transition management requirements during the Transition-In period The TIMP must follow PM standards aligned with the latest version of the PMI PMBOK® Guide.
TI-13 | The Contractor must organize and facilitate a series of meetings, weekly or more frequently, with the Incumbent Contractor to ensure that the TIMP, the Incumbent Contractor’s Turnover Plan, the Transition-In Schedule, and the Incumbent Contractor’s Transition-Out Schedule are integrated and feasible for execution.
TI-14 | The Contractor must execute and oversee all activities specified in the approved TIMP throughout the Transition-In period.
TI-15 | The Contractor must review the MECM System and AMS architecture, including, at a minimum, the following: • Business Architecture • Technical Architecture and its software components • Logical Architecture • Physical Architecture • Integration Architecture • Security and Privacy Architecture The Contractor must perform an assessment of the SA against the RFP requirements and applicable SLAs to identify all areas of software and infrastructure improvement necessary to meet or exceed those requirements and SLAs and to maintain compliance throughout the Contract term. The Contractor must summarize its findings and recommendations for software and infrastructure improvements for the Department’s consideration as part of the Transition-In SA Assessment Report deliverable and submit the report to the Department in advance of the Transition-In Readiness Reviews. The Contractor must facilitate a walkthrough of their findings and recommendations with the Department, including the Enterprise Architecture team and members of the ARB, to provide justifications for the recommendations and to solicit the Department’s feedback on the feasibility of implementing the proposed changes.
TI-16 | The Contractor must develop an SA Evolution Roadmap for the Department within sixty (60) days of the Department’s indication of the software or infrastructure changes to be implemented. The SA Evolution Roadmap must include, at a minimum, the following: • Clear summary of improvements to be implemented to meet Department requests for software or infrastructure changes • High-level timeline for implementing all improvements • Approach for implementing each of the improvements • Description of roles and responsibilities of the Contractor and the Department • Cost impact to the Department for each of the improvements Depending on the number of improvement items and the scale of the implementation needed to effectuate the SA Evolution Roadmap, the Contractor must work with the Department to determine the best way to address those improvements.
TI-17 | Upon approval of the SA Evolution Roadmap, the Contractor must identify and update all relevant SA documentation, as well as all relevant M&O processes, to reflect the changes.
TI-18 | The Contractor must develop a Transition-In PMP that includes, at a minimum, the following: • Definition of how each service or function performed by the Incumbent Contractor will be transitioned and cutover to the Contractor • Identification of the activities and tasks that must be accomplished to support the transition of operational control of a service or function • Definition of the roles and responsibilities for completing transition activities and tasks • Plan for the timing, audience, and messaging for communication events • Definition of the measurements to validate or test the completion of transition of services or functions • Plan for the Transition-In Readiness Reviews in coordination with the Department and the Incumbent Contractor’s Turnover Plan • Identification of Transition Cutover activities and the target Transition Cutover date • Identification of risks and issues associated with the transition and planned mitigation measures and issue resolution approaches • Definition of contingency plans for addressing high-risk transition activities • Identification of the subject matter assistance the Contractor will require from the Incumbent Contractor (e.g., number of hours, position expertise) • Contractor’s approach to successfully assuming all PM-related responsibilities, including, at a minimum, the following: o Approach, processes, and procedures needed to cutover and assume responsibility for all services, functions, and other items identified as transition components o Description of how the Contractor will demonstrate readiness, provide evidence and confirmation that they are prepared to assume responsibility, and obtain the Department’s approval with an effective date • Identification of transition components that require validation and description of the approach and methods to be used for validation • Test and validation plan specific to each transition component (or group of components) identified for validation, along with the documentation needed to conduct validation and record results • Test and validation schedule to track, monitor, and report the progress of all test and validation activities • Description of how training and knowledge transfer activities will occur (e.g., materials, courses, Q&A session preparation, dates, times, participants) to familiarize Department staff with all the Contractor’s operations, processes, and tools
TI-19 | The Contractor must develop a Transition-In M&O Plan that includes, at a minimum, the following: • Definition of how each service or function performed by the Incumbent Contractor will be transitioned and cutover to the Contractor • Identification of the activities and tasks that must be accomplished to support the transition of operational control of a service or function • Definition of the roles and responsibilities for completing transition activities and tasks • Plan for the timing, audience, and messaging for communication events • Definition of the measurements to validate or test the completion of transition of M&O services or functions • Plan for the Transition-In Readiness Reviews in coordination with the Department and the Incumbent Contractor’s Turnover Plan • Identification of Transition Cutover activities and the target Transition Cutover date • Identification of risks and issues associated with the transition and planned mitigation measures and issue resolution approaches • Definition of contingency plans for addressing high-risk transition activities • Identification of the subject matter assistance the Contractor will require from the Incumbent Contractor (e.g., number of hours, position expertise) • Contractor’s approach to successfully assuming all M&O-related responsibilities including, at a minimum, the following: o Approach, processes, and procedures needed to cutover and assume responsibility for all services, functions, and activities identified as transition components o Description of how the Contractor will demonstrate readiness, provide evidence and confirmation that they are prepared to assume responsibility, and obtain the Department’s approval with an effective date • Identification of transition components that require validation and description of the approach and methods to be used for validation • Test and validation plan specific to each transition component (or group of components) identified for validation, along with the documentation needed to conduct validation and record results • Test and validation schedule to track, monitor, and report the progress of all test and validation activities • Description of how training and knowledge transfer activities will occur (e.g., materials, courses, Q&A session preparation, dates, times, participants) to familiarize the Department staff with all the Contractor’s operations, processes, and tools
TI-20 | The Contractor must develop a Transition-In DDI Plan that includes, at a minimum, the following: • Definition of how each DDI effort supported by the Incumbent Contractor will be transitioned and cutover to the Contractor • Identification of the activities and tasks that must be accomplished to support the transition of all MECM System and AMS DDI services or functions • Definition of the roles and responsibilities for completing DDI transition activities and tasks • Plan for the timing, audience, and messaging for communication events • Definition of the measurements to validate or test the completion of transition of DDI activities • Plan for the Transition-In Readiness Reviews in coordination with the Department and the Incumbent Contractor’s Turnover Plan • Identification of Transition Cutover activities and the target Transition Cutover date • Identification of risks and issues associated with the transition and planned mitigation measures and issue resolution approaches • Definition of contingency plans for addressing high-risk transition activities • Identification of the subject matter assistance the Contractor will require from the Incumbent Contractor (e.g., number of hours, position expertise) • Contractor’s approach to successfully assuming all DDI-related responsibilities, including, at a minimum, the following: o Approach, processes, and procedures needed to cutover and assume responsibility for all services, functions, and activities identified as transition components o Description of how the Contractor will demonstrate readiness, provide evidence and confirmation that they are prepared to assume responsibility, and obtain the Department’s approval with an effective date • Identification of transition components that require validation and description of the approach and methods to be used for validation • Test and validation plan specific to each transition component (or group of components) identified for validation, along with the documentation needed to conduct validation and record results • Test and validation schedule to track, monitor, and report the progress of all test and validation activities • Description of how training and knowledge transfer activities will occur (e.g., materials, courses, Q&A session preparation, dates, times, participants) to familiarize Department staff with all the Contractor’s operations, processes, and tools
TI-21 | The Contractor must execute and oversee all activities specified in the approved SA, PM, M&O, and DDI Transition-In Plans throughout the Transition-In period.
TI-22 | The Contractor must develop, deliver, maintain, and execute a Transition-In Schedule that identifies and manages all Transition-In activities and tasks, along with associated dates or time frames and resources required by the TIMP to support successful cutover to the Contractor. The Transition-In period will last no less than twelve (12) months, beginning on the date of the Engagement Kick-Off meeting and presentation or another date agreed upon with the Department.
TI-23 | The Transition-In Schedule must include, at a minimum, the following: • Work Breakdown Structure (WBS) • Activities, tasks, and subtasks with clear and meaningful names • Tasks for Contractor development of each Transition-In deliverable • Tasks for the Department review of each Transition-In deliverable • Tasks for Contractor revision of each Transition-In deliverable after the Department’s review • Department review of each Transition-In deliverable after Contractor revision • Additional rounds of Department review and Contractor revision, as needed • Department approval of each Transition-In deliverable • Predecessor and successor dependencies • Resource assignments • Estimated hours and durations • Custom task fields and custom resource fields as requested by the Department • Identified and tracked dependencies with work being supported by the Incumbent Contactor and the Department • Alignment with the Incumbent Contractor to define and maintain the Integrated Project Schedule for all parties • Appropriate Contractor, Department, and Incumbent Contractor resource assignments and estimated hours Near-term tasks (where near-term is defined to be within one hundred twenty [120] days in the future) must have actual resource names assigned. Tasks that are not classified as near-term may have generic resource titles (e.g., role or team identification) assigned.
TI-24 | The Contractor must maintain, modify, and re-estimate activities, tasks, subtasks, and associated hours and durations in the Transition-In Schedule through the completion of the Transition-In period.
TI-25 | The Contractor must organize and facilitate a series of meetings, as determined by the Department, to report on the progress of the Transition-In effort. Based on the information provided by the Contractor during these meetings, the Department will assess whether the Contractor is on track to complete the transition and assume control and responsibility for the MECM System and the AMS.
TI-26 | The Contractor must facilitate the weekly transition meeting to review the details of the Transition-In Schedule with Department project leads and other identified stakeholders.
TI-27 | The Contractor must facilitate a monthly transition meeting for executive-level audiences (e.g., Department Project Sponsor, Chief Information Officer [CIO], Chief Technology Officer) to review overall Transition-In progress and discuss any key risks or issues associated with the transition.
TI-28 | The Contractor must develop a weekly Transition-In Status Report that includes a summary of Transition-In activities (including knowledge transfer activities); the status of all activities; and any problems, issues, and action items, including responsible parties, due dates, and actions taken.
TI-29 | The Contractor must conduct and facilitate the final Transition-In Status Report meeting for an executive-level audience to confirm that Transition-In activities are complete and to provide information indicating that all transition components are transitioned, scheduled activities are complete, and the Contractor is responsible for all transition areas supporting the MECM System and the AMS.
TI-30 | The Contractor must provide a meeting agenda and accurate meeting minutes for all meetings, as requested by the Department.
TI-31 | The Contractor must complete the transition and assume responsibility for the SA, PM, M&O, and DDI activities, processes, procedures, and deliverables.
TI-32 | The Contractor must perform transition of all data management functions (e.g., data integration, data storage).
TI-33 | The Contractor must perform system and component subsystem testing and facilitate walkthroughs of the associated test plans and test approaches for Department staff.
TI-34 | The Contractor must, during testing, conduct weekly status meetings with Department staff, as described in requirement TI-26, to provide management-level summaries that include, at a minimum, the following: • Summary of status for test execution • Summary of areas where performance does not meet expectations relative to the baselines defined in the Transition-In PM, DDI, and M&O plans • Summary of problems and issues logged within the defect management tool (as specified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard) • Identification of where each problem occurred and an explanation of the differences between expected and actual results • Description of the differences between expected and actual results and how they will be addressed • Identification of when testing is expected to be completed
TI-35 | The Contractor must provide the Department full access to the Contractor’s Transition-In test plans and test documentation, including, at a minimum, cases, scripts, data, procedures, and results.
TI-36 | The Contractor must conduct Transition-In testing in an environment that mirrors production.
TI-37 | The Contractor must conduct Transition-In testing with Department participation for all testing identified in the Transition-In Plan. The Contractor must, in collaboration with the Department, identify the Department roles and participation required for each testing component.
TI-38 | The Contractor must participate in the transfer of data and files, including, at a minimum, the following: • E-mails • Historical transmission files • Archived database records • Documentation • Software configuration items • Test scenarios, test cases, test scripts, and test data • Any other files related to SA, PM, M&O, and DDI
TI-39 | The Contractor must develop and store all documentation related to knowledge transfer execution in a designated Department repository and make it available for Department review.
TI-40 | During the transition, the Contractor must document business process improvement opportunities for each transition area, which will be reviewed with the Department and implemented at the Department’s discretion.
TI-41 | During the transition, the Contractor must document suggested technology upgrades or improvements to MECM System and AMS components, as well as other software and infrastructure supporting the implementation of the Converged E&E System. The Contractor must review these upgrades or improvements with the Department and implement them at the Department’s discretion.
TI-42 | The Contractor must conduct a series of Transition-In Readiness Reviews with the Department for each transition area and provide evidence that the Contractor and their staff are ready to assume operational control and responsibility for the MECM System and the AMS and have coordinated Transition Cutover tasks and timing with the Incumbent Contractor. Transition-In Readiness Reviews apply to each of the transition areas (SA, PM, M&O, and DDI).
TI-43 | The Contractor must conduct Transition-In Readiness Reviews with the Department to obtain approval to assume operational control of the MECM System and the AMS. The Transition-In Readiness Reviews must include, at a minimum, review of the following: • Incumbent Contractor’s closeout checklist • Status of migration activities and tasks for each transition area • Status of knowledge transfer • Contractor’s test and validation results • Proposed Transition Cutover date (coordinated with the schedules of the Department, the Contractor, and the Incumbent Contractor) • Contractor’s confirmation of readiness • Department’s Transition Cutover Go/No-Go decision
TI-44 | The Contractor must conduct the Transition Cutover after the conclusion of the Transition-In Readiness Review sessions and after the Department has approved the Transition Cutover to initiate.
TI-45 | The Contractor must take over the MECM System and the AMS and provide a signed (electronically or as otherwise agreed upon) formal letter of acceptance stating that the Contractor accepts full responsibility to operate, maintain, and enhance the MECM System and the AMS according to the methods, processes, tools, and reviews outlined in the RFP requirements.

## M&O
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
M&O-01 | The Contractor must be responsible for maintaining and operating the Converged E&E System.
M&O-02 | The Contractor must perform responsibilities related to the following: • Maintenance • System operations • Technical support • Service ticket processing • Troubleshooting and repair • Release management and testing
M&O-03 | The Contractor must develop, deliver, maintain, and execute all M&O deliverables required by this RFP (refer to Section 5.8 – Deliverables), including the following: • Daily Production Status Report • Operations Report • M&O Manual • M&O Plan • System Enhancement and Upgrade Report • Usage and Performance Analytics Report • Open Enrollment Readiness Assessment
M&O-04 | The Contractor must maintain availability of all data required for M&O reporting deliverables, including, at a minimum, those listed in Section 5.8 – Deliverables and as directed by the Department. This must be achieved by either pulling data into reporting tools available in the Enterprise Data Warehouse (EDW) via its data lakehouse, or by generating data extracts only if EDW tools are insufficient or as explicitly directed by the Department.
M&O-05 | The Contractor must develop a monthly System Enhancement and Upgrade Report that provides a detailed assessment of areas for improvement and upgrades to improve efficiency, security, and functionality. The report must outline the technical and functional aspects of proposed upgrades, including software and infrastructure updates, integration of new technologies, system optimization techniques, and alignment with the Converged E&E System Roadmap.
M&O-06 | If the Department identifies new required M&O reports and extracts, the Contractor must, work with the Department to identify reporting data requirements, transmit the required data to the EDW for integration, update report lists to reflect the new items, and begin producing the reports in accordance with the defined reporting schedule.
M&O-07 | The Contractor must adopt, update, maintain, and provide an Operations Report that specifies scheduled system downtime and documents corrective actions taken for any unscheduled downtime. This report must include defect metrics, such as defect age and regression testing defects, and must be produced under the Operations Contract line item.
M&O-08 | The Operations Report must document accomplishments for the report period in a task-by-task format, including all tasks that are on schedule, tasks that are behind schedule, tasks planned for the next reporting period, any administrative issues encountered, and proposed resolutions for all identified problem areas. The report must align with the Converged E&E System chosen SDLC methodology processes.
M&O-09 | The Contractor must include the following metrics as part of the Operations Report: • System performance metrics • Program support metrics • Production defect metrics • Special provisions and SLA metrics • Weekly processing and transaction counts • Daily batch operations • Staffing Contact Information Report • M&O Reporting Dashboard • Programmatic data, as directed by the Department, including, at a minimum, the following: o Application processing data, including standardized denial reasons and applicant demographics by program o Disenrollment data, including standardized reasons for voluntary and involuntary disenrollment, as applicable by program, and enrollee demographics o Monthly enrollment data by member and program o Other data required to perform statistical assessments required of each program by applicable State and federal agencies Refer to the OHIP Infrastructure & Operations Domain Document, ITSM Standard for metrics reporting standards.
M&O-10 | The Contractor must work with the printing and mailing vendor to transmit files in an appropriate format for mail processing and printing services, should the Department deem this service necessary.
M&O-11 | The Contractor must provide to the Department, in conjunction with the associated invoice, a monthly report that provides an accurate accounting of all postage usage downloaded into the postage meters, as well as all consumables (e.g., paper and envelopes) associated with mailing services. The report must be in a format that allows full validation of calculations and data by a person with a business analysis skill set and must include, at a minimum, postage account balances and meter activity.
M&O-12 | The Contractor must provide environment monitoring and alerting for Amazon Web Services (AWS) and Google Cloud Platform (GCP) infrastructure resources, using AWS CloudWatch for AWS resources and Google Cloud Observability, including Cloud Monitoring and Cloud Alerting, for GCP resources. For statistics not collected by default, including memory, swap, and disk space utilization, the Contractor must deploy the applicable monitoring agent: the CloudWatch agent on AWS instances and the Google Cloud Ops Agent on Compute Engine instances. Vital statistics must include, at a minimum, the following: • System Status Check – System not reachable • Instance Status Check – Usage greater than eighty-five percent (85%) • Central Processing Unit (CPU) Utilization – Usage greater than eighty-five percent (85%) • Memory and Swap Utilization – Usage greater than eighty-five percent (85%) • Elastic Block Store and Disk Space Utilization – Usage greater than eighty-five percent (85%) • Relational Database Service (RDS) CPU Utilization – Usage greater than ninety percent (90%) Out-of-bounds statistics constitute an incident. The Contractor must include this information in the Operations Report and submit a remediation plan to address the incident in accordance with the SLAs, based on the incident’s severity level. Monitoring tools must be made available to at least three (3) additional users, as determined by the Department, and to independent parties (e.g., IV&V vendors) for analysis.
M&O-13 | The Contractor must make available to the Department all data gathered for compute utilization, network utilization, data storage usage, and all other factors and resources that impact system performance. This information must be in a format that allows for full data validation and calculations by a person with a business analysis skill set. Refer to the Data & Information Management Domain Document, Enterprise Data Governance Standard for data management compliance.
M&O-14 | The Contractor must be responsible for proactively performing a root cause analysis (RCA) and providing reports on problems, as defined in the Information Technology Infrastructure Library (ITIL), including statistics on total number of problems, outstanding problems, and resolution time. This must include continuous service improvement procedures with results measurements.
M&O-15 | The Contractor must conduct weekly incident and problem review meetings to assess status, RCA, areas of process improvement, and overall ongoing activities. This can be part of the weekly M&O Status Report meeting; however, depending on the volume of incidents and problems, the Contractor must establish a separate series of weekly meetings upon Department request.
M&O-16 | The Contractor must develop a Corrective Action Plan (CAP) after a security incident, system failure, or any event that compromises the integrity, availability, or confidentiality of the Converged E&E System and its data. The CAP must provide a comprehensive evaluation of the extent of the damage, its impact on operations and security, the steps needed for recovery, and future prevention.
M&O-17 | The Contractor must produce an M&O Monthly Status Report that provides the Department with an overview of M&O activities performed during the reporting month, including alignment with the Converged E&E System Roadmap milestones.
M&O-18 | The Contractor must produce a Usage and Performance Analytics Report that provides insights into end-user utilization of the Converged E&E System and system performance efficiency.
M&O-19 | The Contractor must produce a Daily Production Status Report that includes, at a minimum, the following: • System status overview • Maintenance activities • Incident and problem management • Recent and upcoming changes • Security updates • Compliance and audit information • Upcoming scheduled maintenance • Risks, issues, and mitigations • Action items and recommendations
M&O-20 | The Contractor must document all ongoing cloud inventory and asset management activities in the M&O Manual and associated work products.
M&O-21 | The Contractor must develop, deliver, maintain, and execute all M&O BC/DR deliverables required by this RFP (refer to Section 5.8 – Deliverables), including, at a minimum, the BC/DR Plan.
M&O-22 | The Contractor must provide and maintain a DR Plan that includes, at a minimum, the following: • Approach • Risk assessment • Business Impact Analysis (BIA) • Restoration strategies • Data backup procedures • DR team • Communication plan • Recovery plan documentation • Testing and training procedures • Maintenance schedule • After action report template
M&O-23 | The Contractor must provide secure storage and transportation of the backup media, if required.
M&O-24 | The Contractor must support the Department in validating transactions.
M&O-25 | The Contractor must support restoration of databases such that all possible transactions completed prior to data loss or service interruption of the Converged E&E System are processed automatically within the applicable Recovery Point Objective (RPO), as defined in Attachment F –SLAs.
M&O-26 | The Contractor must support backup operations that prioritize critical business functions, as identified by the Department, and allow noncritical functions to be postponed or rescheduled.
M&O-27 | The Contractor must be responsible for all system backup and restoration processes.
M&O-28 | The Contractor must perform system backups in a manner that does not negatively impact the Production Environment performance or availability.
M&O-29 | The Contractor must utilize automated backup and restoration processes that require minimal human intervention.
M&O-30 | The Contractor must deploy a secure backup and restoration solution to prevent unauthorized access to system data.
M&O-31 | The Contractor must provide and maintain a backup environment that replicates the Production Environment for DR and DR testing. The Contractor must maintain the backup environment to align with the configuration of the Production Environment and system through continuous integration/continuous delivery/deployment (CI/CD) management.
M&O-32 | The Contractor must retain and manage complete copies of AWS and GCP system software backups for the two (2) most recent major versions in the respective secured AWS Simple Storage Service (S3) and Google Cloud Storage (GCS) storage buckets.
M&O-33 | The Contractor must maintain and update current system documentation, user documentation, and all program software libraries related to BC/DR planning and execution.
M&O-34 | The Contractor must perform BC/DR Plan demonstrations at no additional cost to the Department.
M&O-35 | The Department reserves the right to waive or defer part or all the BC/DR Plan demonstrations. If the Department determines that the Contractor’s demonstration is unsuccessful, the Contractor must repeat the demonstration until it is successful, at no additional cost to the Department.
M&O-36 | The Contractor must adopt, update, deliver, maintain, and execute the BC/DR Plan. The plan must document how, upon significant loss of the enterprise environment as determined by the Department, the Contractor supports BC activities. The plan must identify impacts to business operations, establish restoration priorities for business processes, identify critical systems and processes, and document associated Recovery Time Objectives (RTOs), as defined in Attachment F –SLAs.
M&O-37 | The Contractor must successfully conduct a complete test of the BC/DR procedures at least once during each calendar year.
M&O-38 | The Contractor must administer BC/DR procedures throughout the Contract term.
M&O-39 | The Contractor must demonstrate annually to the Department or its designee (e.g., auditors) that all BC/DR components, procedures, and activities documented in the M&O Plan have been fully tested.
M&O-40 | The Contractor must develop, deliver, maintain, and execute all M&O Configuration Management deliverables required by this RFP (refer to Section 5.8 – Deliverables), including the following: • Configuration Management Plan • Content Management Plan • Web Content Management Plan • Data Management Plan (DMP) • Data Management Design Document • Logical Data Model (LDM) • Physical Data Model (PDM) • Conceptual Data Model (CDM) • Data Dictionary • Business Architecture Model(s) • Interface Control Documents (ICDs) • Interface Technical Design Document (ITDD) • Source Code
M&O-41 | The Contractor must adopt and maintain all functional and nonfunctional requirements in effect as of the Contract start date. The Contractor must change, develop, and maintain requirements in accordance with the Requirements Management Plan.
M&O-42 | The Contractor must adopt, update, maintain, and execute the Configuration Management Plan. The Contractor must follow the PMP PCC process for changes to the Configuration Management Plan.
M&O-43 | The Contractor must adopt, update, and maintain documentation in the Department-chosen electronic library or repository throughout the Contract term.
M&O-44 | The Contractor must maintain an LDM for the Converged E&E System that includes, at a minimum, the following: • Participants roles and responsibilities • Fields • Relationship views • Data flows diagrams • Data dictionary and Create, Read, Update, and Delete (CRUD) matrix
M&O-45 | The Contractor must maintain a PDM for the Converged E&E System based on the National Information Exchange Model (NIEM) and Health Level Seven (HL7)’s Fast Healthcare Interoperability Resources (FHIR) that includes, at a minimum, the following: • Representational State Transfer (REST)ful Architecture • Use of Hypertext Transfer Protocol (HTTP) methods (e.g., GET, POST, PUT, DELTE) • Persistent Data Model • Web-based format such as Extensible Markup Language (XML) or JavaScript Object Notation (JSON) • Message XML Schema Model or equivalent
M&O-46 | The Contractor must maintain the Converged E&E System CDM to include, at a minimum, the following: • High-level objects or concepts relevant to the business domain • Descriptive properties or characteristics of entities • Associations between entities that define how entities interact • Glossary of business terms and definitions to support consistent terminology and understanding across stakeholders • Illustrations or narrative descriptions of conceptual data flows between entities and systems, without inclusion of technical details • Domain-specific details or context that may affect the conceptual model and align with business needs or applicable industry standards
M&O-47 | The Contractor must deliver the LDM and PDM to the Department in the native format of the data modeling tool specified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard, as well as PDF format.
M&O-48 | The Contractor must adopt, update, including any updates required for compliance with the OHIP Data and Information Management Domain Document, Data Architecture and Naming Standard, and maintain data models and data dictionaries provided by the Department.
M&O-49 | The Contractor must support the operation and administration of environments as defined and agreed upon by the Department and the Contractor. The Contractor must also provide services to support the daily operation and administration of the system technical solution, services, applications, and supporting functionality, including, at a minimum, the following: • Databases, operating systems, middleware, and other supporting software • Daily operation and administration of Production and lower-level environments • Forms and reporting architecture, in coordination with the Department • Contractor development environments • Real-time and batch processing for internal and external interfaces • Contractor back-office support
M&O-50 | The Contractor must maintain synthetic and masked data in lower-level environments and use strict and consistent Configuration Management practices to support test data management.
M&O-51 | The Contractor must synchronize and clean out reference tables in non-Production Environments with Production reference tables, as requested by the Department or its designee.
M&O-52 | The Contractor must maintain the User Acceptance Testing (UAT) environments with, at a minimum, the Production version of system code, unless otherwise requested or approved by the Department or its designee.
M&O-53 | The Training environments must operate independently to allow maintenance activities without impacting, or being impacted by, other environments.
M&O-54 | The Contractor must maintain the Training environments with, at a minimum, the Production version of the system code or one (1) version earlier, unless otherwise requested or approved by the Department or its designee.
M&O-55 | The Contractor must update all versions of software components across system environments throughout the Contract term and must maintain versions up to N- one (1), where N represents the most current software version, unless otherwise accepted by the Department.
M&O-56 | The Contractor must provide copies of full production data, partial production data, and data sets representative of operational complexity in lower-level environments, as determined by the Department.
M&O-57 | The Contractor must be responsible for tuning and optimizing the performance of the Converged E&E System.
M&O-58 | The Contractor must be responsible for strategic and tactical planning for data circuits, access security, port management, and network device configuration to comply with performance requirements.
M&O-59 | The Contractor must adopt, update, maintain, and deliver, within the M&O Manual, an approach to change management support for Department and Contractor equipment and software upgrades, PCRs, and system Releases.
M&O-60 | The Contractor must advise the Department of the operational impacts of any software upgrade to the system or interface partners at least ninety (90) calendar days prior to implementation.
M&O-61 | The Contractor must provide services required to upgrade system software components, including, at a minimum, impact analysis, planning, testing, and implementation.
M&O-62 | The Contractor must leverage Oracle Intelligent Advisor (OIA) to maintain and operate the Business Rules Engine (BRE). This includes exposing application programming interfaces (APIs) to enable other systems to use the BRE for rule execution and performance monitoring. The Contractor must be responsible for business rules, including authoring, updating, accuracy, BRE availability, and access through APIs or interfaces.
M&O-63 | The Contractor must leverage the existing BRE catalog and use the catalog’s defined purpose, logic, and dependencies for all business rules. The Contractor must be responsible for business rules, including purpose, logic, and dependencies, and must coordinate with other vendors to provide catalog access and updates.
M&O-64 | The Contractor must leverage performance metrics and KPIs for the BRE to evaluate business rule effectiveness. The Contractor must access and report on execution times, error rates, and impact analysis, and must incorporate this information into the daily Operations Report. The Contractor must be responsible for evaluating and reporting on the effectiveness of business rules and must coordinate with other vendors to provide access to metrics.
M&O-65 | The Contractor must work with third-party vendors that leverage the BRE to create hubs to develop, test, and execute business rules, enabling the use of the BRE as an enterprise shared service (ESS).
M&O-66 | The Contractor must configure the Department’s BRE to enable applications to trigger rule evaluations in OIA based on business events and to support comprehensive logging and monitoring of all rule execution events.
M&O-67 | The Contractor must configure the Department’s BRE to integrate with OIA rule versioning and deployment capabilities so that application deployments are synchronized with the correct rule versions.
M&O-68 | The Contractor must configure the Department’s BRE to include comprehensive testing frameworks to support validation of rule behavior across scenarios for business users and technical teams.
M&O-69 | The Contractor must configure the Department’s BRE to log all calls to OIA and all returned results to support audit functions with full traceability of rule execution context and outcomes.
M&O-70 | The Contractor must configure the Department’s BRE to include monitoring and analytics for rule usage, performance, and business impact, with dashboards and reports available to all stakeholders, including third-party vendors that leverage the BRE.
M&O-71 | The Contractor must configure the Department’s BRE to integrate with the Department’s Okta Identity and Access Management (IAM) system to manage access for business users who author, test, and approve rules within OIA.
M&O-72 | The Contractor must maintain the existing ICDs for the MECM System and the AMS. The Contractor must validate that the inherited ICDs reflect all existing interfaces and must update the ICDs as necessary to maintain currency. ICDs must include, at a minimum, the following: • Description of all interfaces, including those listed in Exhibit G.25 – Converged E&E System and AMS Interfaces • Detailed interface requirements • Interface or integration approach and processing • Communication protocols with external entities • Endpoint configurations for connecting to partner systems • Orchestration details • Interface development and testing schedules • Error handling procedures • Overview of batch jobs and processes triggered by interfaces including purpose, scope, and stakeholder roles and responsibilities The Contractor must also create ICDs for any new interfaces developed during the Contract term.
M&O-73 | The Contractor must adopt and maintain the Department-provided ITDD. The ITDD must provide a comprehensive overview of the technical architecture and end-to-end (E2E) flow for all interfaces and include, at a minimum, the following: • Technical overviews of all interfaces and integration • Detailed technical flows for each interface that enables data exchange • Endpoint configurations required for system-to-partner and partner-to system connectivity with interface partners and target systems • Key technical aspects of interface design, including the following: o Real-time Simple Object Access Protocol (SOAP), Representational State Transfer (REST), and batch-based communications o Orchestration of E2E real-time or batch-based processes o Secure and reliable file transfer o Endpoint configurations required for partner system connectivity
M&O-74 | The Contractor must adopt and maintain the Department-provided ISD. The ISD must provide a comprehensive and detailed guide specifying protocols, formats, and interactions among systems, components, and software applications to support effective interoperability. The ISD serves as a blueprint for developers, engineers, and stakeholders by detailing how to design, implement, and maintain interfaces between systems.
M&O-75 | The Contractor must adopt, update, and maintain the Source Code deliverable.
M&O-76 | The Contractor must develop, deliver, maintain, and execute all M&O escalation management deliverables required by this RFP (refer to Section 5.8 – Deliverables), including the following: • Problem Management Plan • Incident Management Plan • Defect Management Plan • Patch management Plan • CAP
M&O-77 | The Contractor must provide a Problem Management Plan, aligned with the OHIP Infrastructure & Operations Domain Document, ITSM Standard, that documents processes for problem detection, logging, categorization, correlation, prioritization, investigation, diagnosis, resolution, escalation, closure, and notification to the Department. The plan must include, at a minimum, the following: • Problem management policy and procedures • Problem identification, logging, and categorization • Prioritization methods • RCA approach • Problem resolution procedures • Reporting and metrics • Communication plan • Training • ITSM process integration • Continuous Improvement • Assumptions, constraints, and dependencies
M&O-78 | The Contractor must provide an Incident Management Plan, aligned with the OHIP Infrastructure & Operations Domain Document, ITSM Standard and approved by OHIP, that documents processes for incident detection, logging, categorization, correlation, prioritization, escalation, resolution or workaround, resolution logging, closure, and communication of status updates. The plan must include, at a minimum, the following: • Incident life cycle procedures • Roles and responsibilities matrix • Incident logging and classification • Communication plan • Incident logging and classification • Incident reporting and metrics • Training and awareness • Continuous improvement • Assumptions, constraints, and dependencies
M&O-79 | The Contractor must correct all problems within the scope of Contractor requirements, deliverables, and SLA responsibilities. The Department will not consider a problem corrected until the Contractor validates that the issue has been resolved with the individual who initially reported the problem or an appropriate designee. Defects identified in Production that were billable during testing are not billable for correction.
M&O-80 | The Contractor must promptly document reported problems upon receipt and must monitor, control, communicate, and report on each problem until it is resolved or fully corrected.
M&O-81 | The Contractor must maintain communications with the Department and affected users for all problems through resolution, as designated in the communication plan.
M&O-82 | The Contractor must escalate unresolved problems in accordance with procedures established by the Department.
M&O-83 | The Contractor must develop, deliver, maintain, and execute all M&O technology operations deliverables required by this RFP (refer to Section 5.8 – Deliverables), including the following: • Procurement and Licensing Assessment Report • Technology Refresh Assessment Report
M&O-84 | The Contractor must document and provide, within the M&O Manual, processes and procedures for managing system and AWS service availability. This must include, at a minimum, the following: • Approach to monitoring, assessing, and managing system availability to comply with availability requirements • Assumptions • Description of Contractor, Department staff, and Department roles and responsibilities • Processes and procedures for the following: o Moving, adding, changing, and de-installing Contractor equipment o Installing and upgrading software components o Monitoring system availability for Contractor equipment, including identification, analysis, resolution, and reporting of issues
M&O-85 | The Contractor must be fully responsible for system availability, performance, growth, capacity, software (excluding licenses), and operational services.
M&O-86 | The Contractor must synchronize the system time across all system devices.
M&O-87 | The Contractor must continuously monitor CPU utilization, network bandwidth consumption, data storage usage, and all other factors and resources that impact system performance for all Contractor and Contractor managed equipment throughout the Contract term and must provide additional system resources as required.
M&O-88 | The Contractor must create, update, and maintain the M&O Plan.
M&O-89 | The Contractor must adopt, update, maintain, deliver, and execute operations procedures as specified in the M&O Manual and referenced in the M&O Plan.
M&O-90 | The Contractor must adopt, update, maintain, and execute operations management processes and techniques in accordance with the M&O Plan.
M&O-91 | The M&O Manual must include, at a minimum, the following: • Introduction and overview • Solution description • Operational guides and procedures • Capacity Management Plan • Availability management • Maintenance procedures • M&O Runbook • Emergency procedures and DR • Security and privacy policies and procedures • Change control procedures • Troubleshooting guide • Contact information • Glossary and abbreviations • Document control • Compliance and regulatory information • Performance reporting • SLA performance and management metrics • QA procedures • M&O staffing • Task tracking • Service interruption procedures • Testing processes • Enterprise scheduling • Interface management and monitoring • Technical database administration • Hardware and software procedures • Backup and recovery • Service and support tracking management
M&O-92 | The Contractor must develop, deliver, and maintain procedures outlined in the M&O Manual. The procedures must be stored in a version control tool and must include, at a minimum, the following: • Procedures for all tasks in the operations environment, including problem management and outage analysis • Roles and responsibilities for operations and technical support staff • Contact lists for personnel requiring notification of problems in Production and lower-level environments • Escalation procedures for all tasks in Production and lower-level environments • Procedures for scheduled maintenance of environments, (e.g., database maintenance) • Maintenance and emergency procedures for activities such as startup, shutdown, and Deployments • Schedules for operational tasks and batch processes • Procedures to coordinate with interface partners for file receipt and transfer and for monitoring interface hardware and software • Hardware and software procedures, including procurement, for tasks outside normal operations requirements • Technical support procedures for database administration, data storage, and enterprise hardware and software • Procedures for tasks associated with backup and recovery, data archiving, data distribution, and standard and exception system administration operations, including Deployments, across Production and lower-level environments • Procedures for service ticket processing, maintenance, troubleshooting and repair, Release management, and testing of Production and lower-level environments • Procedures for monitoring all interfaces and reporting successful and unsuccessful completion of transactions or data exchanges • Procedures for recovering from failed interface processing
M&O-93 | The Contractor must include all sub-plans within the M&O Manual and must update the sub-plans, as applicable, as part of ongoing M&O Manual updates.
M&O-94 | The Contractor must update the M&O Manual on an annual basis for the duration of the Contract.
M&O-95 | The Contractor must include forecasts for the next calendar year for expected needs for all AWS and GCP cloud resources, network bandwidth, and data storage capacities for all Contractor equipment as part of the annual M&O Manual update.
M&O-96 | The Contractor must document Contractor, third-party, and Department roles and responsibilities within the M&O Manual.
M&O-97 | The Contractor must, in partnership with the Department, develop, adopt, and implement the M&O Manual. At a minimum, the M&O Manual must define the tasks, roles, responsibility, and approach for supporting activities associated with maintaining the system.
M&O-98 | The Contractor must manage, facilitate, and coordinate M&O activities with Department service providers, as directed by the Department or its designee.
M&O-99 | The Contractor must provide timely justification to the Department for proposed maintenance support levels for each software component based on severity or criticality level.
M&O-100 | The Contractor must manage, facilitate, and coordinate M&O incident identification and resolution activities with Department service providers, as directed by the Department or its designee.
M&O-101 | The Contractor must notify appropriate Department staff, service desks, and all impacted vendors of any incident (e.g., limited access, outages, and security violations) in alignment with the communication and escalation procedures defined in the OHIP Infrastructure & Operations Domain Document, ITSM Standard. Notifications must include status updates as part of the incident management process.
M&O-102 | The Contractor must formally request approval for scheduled maintenance periods at least seventy-two (72) hours prior to the maintenance activity. The Contractor and the Department must mutually agree upon and approve scheduled maintenance periods.
M&O-103 | The Contractor must promptly document reported problems upon receipt and must monitor, control, communicate, and report on each problem until it is resolved or fully corrected, in alignment with the problem management activities defined in the OHIP Infrastructure & Operations Domain Document, ITSM Standard (e.g., logging, prioritization, investigation, resolution, and Department notification).
M&O-104 | The Contractor must provide and maintain all the necessary industry-standard tools and technologies to support all storage requirements including, at a minimum, the following: • File storage • Content management • Data warehouse • Business intelligence and reporting • Relational database • BRE • Identity storage • Certificate storage
M&O-105 | The Contractor must report and address all capacity issues that impact system performance requirements in alignment with the capacity management processes defined in the OHIP Infrastructure & Operations Domain Document, ITSM Standard (e.g., monitoring, forecasting, and KPI tracking).
M&O-106 | The Contractor must deploy and use browser-based performance monitoring and failure alert tools.
M&O-107 | The Contractor’s performance monitoring and failure alert tools must not adversely impact system or network performance or availability.
M&O-108 | The data layer must include industry-standard tools and technologies to support design, development, testing (e.g., functional, load, and performance testing), and runtime management and monitoring for all information systems.
M&O-109 | The Contractor must be responsible for all system monitoring functions and must adopt and follow ITIL framework best practices, as defined in the OHIP Infrastructure & Operations Domain Document, ITSM Standard. The Contractor must adopt, update, and maintain documentation for all operations procedures and services. Monitoring functions must align with the Standard’s processes including, at a minimum, the following: • Responding to alerts • Managing notifications • Coordinating with change management • Managing cloud-related issues • Maintaining documentation to reflect system changes
M&O-110 | The Contractor must provide and maintain all necessary industry-standard tools and technologies to support storage requirements, in alignment with the Department’s Code Standard guidelines for tool selection, approval, and maintenance, including, at a minimum, the following: • File storage • Content management • Data warehouse • Business intelligence and reporting • Relational database • BRE repository • Identity storage • Certificate storage
M&O-111 | The Contractor must provide and support all internal and external integration tools.
M&O-112 | The Contractor must notify the Department of available software updates and required patches and must define a timeline for implementation. The Contractor must report updates and patches in M&O status reports.
M&O-113 | The Contractor must evaluate and implement configuration updates associated with Federal Poverty Level (FPL) cost-of-living adjustments (COLAs).
M&O-114 | The Contractor must evaluate and implement changes associated with Internal Revenue Service (IRS) Form 1095 for system enrollees.
M&O-115 | The Contractor must be responsible for making application programming changes required to support upgrades to third-party software components.
M&O-116 | The Contractor must provide system capabilities to retain ten (10) years of data online and an additional ten (10) years of data in offline storage (e.g., AWS Glacier). The Contractor must also be responsible for the secure destruction of hard copy and electronic records after seven (7) years, or in accordance with applicable federal, State, and Department data retention and destruction requirements associated with the relevant data classifications. Such requirements include, at a minimum, the following: • IRS Publication 1075 – Tax Information Security Guidelines for Federal, State and Local Agencies1 (Federal Tax Information [FTI] data) • Health Insurance Portability and Accountability Act (HIPAA) record retention requirements, including 42 Code of Federal Regulations (CFR) Part 1602 and 42 CFR Part 1643 • CMS Records Schedule/Records and Information Management Policy4 • NYS State Education Department General Retention and Disposition Schedule for New York State Government Records (General Schedule)5 • Department data retention policies, such as the following: o Bureau of Emergency Medical Agencies Policy Statement No. 08-03 - Records Retention6 o The Department will provide more detailed policies once the Contractor onboards
M&O-117 | The Contractor must have the ability to copy and restore data and code for lower-level environments upon request by the Department.
M&O-118 | The Contractor must begin data restoration within twenty-four (24) hours, or sooner if requested by the Department or its designee. This requirement applies to Department-requested data restoration activities for any environment and does not apply to disaster declarations.
M&O-119 | The Contractor must notify the Department within thirty (30) business days of identifying the need for additional infrastructure, capacity, or software. If the identification occurs after a reporting deadline, the Contractor must include the details in the next Monthly Capacity Planning Report or M&O Monthly Status Report.
The Web Content Management Plan must comply with ISO/IEC/IEEE 23026:2023 – Systems and software engineering – Engineering and management of websites for systems, software, and services information and the OHIP Solution Delivery Domain Document, Usability and Accessibility Standard. At a minimum, the plan must address the following: • Effectiveness – Demonstrated by achieving a task success rate of greater than or equal to ninety-five percent (≥95%) for core workflows during usability evaluations • Efficiency – Demonstrated through defined time-on-task benchmarks, such as completing eligibility applications in less than or equal to eight (≤8) minutes • Satisfaction – Demonstrated by achieving a minimum System Usability Scale (SUS) score of ninety (90) • Learnability – Demonstrated by novice users achieving task success for routine functions in less than or equal to (≤15) minutes • Accessibility – Demonstrated by the following: o Full compliance with Web Content Accessibility Guidelines (WCAG) two point one (2.1), Level AA, with backward compatibility to WCAG two point two (2.2) for future alignment o Compliance with Section 508 and the Americans with Disabilities Act (ADA) o Validation through a Voluntary Product Accessibility Template (VPAT) o Automated and manual accessibility testing, including the use of assistive technologies (ATs) such as Job Access With Speech (JAWS) and NonVisual Digital Access (NVDA) o Evaluation across the principles of perceivability, operability, understandability, robustness, and biometric interface accessibility • User Experience (UX) – Demonstrated through documented research activities, personas, and established feedback loops • Avoidance of Harm – Demonstrated through error prevention mechanisms and fail-safe design practices • Maintainability – Demonstrated through a consistent user interface (UI) and regression testing practices The solution must comply with current and future NYS Accessibility Standards in accordance with NYS-P08-005, Accessibility of Information Communication Technology7. Effective dates include WCAG two point one (2.1) Level AA by April 24, 2026, and WCAG two point two (2.2) Level AA by January 1, 2027, for new or modified content. All evaluations must include biennial manual testing and be documented in CMS certification artifacts. Refer to the OHIP Solution Delivery Domain Document, Usability and Accessibility Standard for additional information.
M&O-121 | The Contractor must make the network management and control system, along with all resulting data and reports, accessible to the Department for review and independent analysis at all times.
M&O-122 | The Contractor must maintain the current MECM System environments described in Section 3.3.2.5 – Physical Architecture and the AMS environments described in Section 3.3.3.4 – Appeals Management System Environments.
M&O-123 | The Contractor must create and execute Deployment Requests to update the Production and UAT environments with Department-approved system code. Each Deployment Request must include the applicable system code, Deployment instructions, and all artifacts necessary to update the target environment with the specified Release. Deployment Request contents must include, at a minimum, the following: • Specific code and associated components required for the Release • Step-by-step instructions for implementing the Release, including required configuration changes and dependencies • Supporting documentation, scripts, and resources necessary for Deployment • Post-Deployment validation steps or a checklist to confirm the environment is updated and operating as intended • Deployment time frames aligned with the agreed-upon schedule The Contractor must collaborate with the Department to review and resolve issues during the Deployment Request approval process. Deployments must receive Department approval with at least forty-eight (48) hours’ notice and must include defect logs for review prior to promotion to UAT or higher environments.
M&O-124 | The Contractor must provide and maintain online Integration Testing (DEV) environments that support system testing activities, prototype development, and replication of full production system functionality.
M&O-125 | The Contractor must demonstrate that Integration Testing (DEV) environments replicate full production system functionality without impacting production data.
M&O-126 | The UAT Environment must operate independently to support maintenance or administrative activities without impacting, or being impacted by, other environments.
M&O-127 | The Contractor must make the UAT environments accessible to designated Department staff and QA users.
M&O-128 | The Contractor must provide full support for QA activities and must cooperate with QA teams and supervising agencies as directed by the Department. Support activities must include, at a minimum, the following: • Providing timely documentation, information, and system access requested by QA teams or the Department for assessment of quality standards • Supporting independent reviews of governance, PM, and deliverables • Assisting with preparation and delivery of status assessments to federal partners, with accurate and current data • Maintaining and providing comprehensive documentation, including project plans and progress reports, to support QA activities
M&O-129 | The Contractor must provide internet-based access to the UAT Environment in accordance with approved roles and responsibilities.
M&O-130 | The Contractor must manage and support batch schedules for UAT environments, which may differ from the Production Environment batch schedules. The Contractor must execute Department-requested UAT batch scheduler run cycles within two (2) hours of request by the Department or its designee.
M&O-131 | The Contractor must have the ability to copy and restore UAT data and system code upon request by the Department.
M&O-132 | The Contractor must proactively support the Department in performing UAT at no additional cost, including the following: • Preparation – Development of UAT scenarios and test scripts in collaboration with the Department, with delivery at least ten (10) business days prior to UAT start and UAT initiation contingent upon Department approval • Data Seeding – Completion of data seeding at least five (5) business days prior to UAT start, with data reflecting real-world scenarios and validated for completeness and accuracy • Scope Management – Resolution of all assigned problem tickets and completion of development prior to UAT start, with no coding changes during active UAT without Department approval The Contractor must provide weekly UAT status updates and escalate any risks to UAT readiness at least fifteen (15) business days prior to a potential risk trigger.
M&O-133 | The Contractor must provide and maintain DC environments to support DC Dry Runs, mock runs, data profiling, data cleansing, and data quality activities.
M&O-134 | The Contractor must provide and maintain DC environments to support the testing of DC and case transfer functions, including implementations related to converting and migrating NY State of Health (NYSOH) System data to the Converged E&E System.
M&O-135 | The Contractor must provide and maintain DC environments (Pre-Production/non-Production) that comply with the OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard, including the following: • Preference against the use of unmasked production data, with masked or anonymized data used where possible for development, testing, and integration • If unmasked production data is required, compelling justification, Department approval, and implementation of security controls equivalent to the Production Environment (e.g., National Institute of Standards and Technology [NIST] Special Publication [SP] 800-53 Moderate and CMS Acceptable Risk Standards [ARS] baselines) • Policies and procedures for secure data handling, including data minimization, isolation (e.g., network segmentation), continuous monitoring, access restrictions, and audit logging • Documentation in the System Security and Privacy Plan (SSPP) Workbook, with supporting artifacts for Department review
M&O-136 | The Contractor must provide internet-based access to the Training environments in accordance with approved roles and responsibilities.
M&O-137 | The Contractor must prepare the Training Environments user guide in accordance with ISO/IEC/IEEE 14764:2022 – Software engineering – Software life cycle processes – Maintenance and ISO/IEC/IEEE 15289:2019, as applicable to end-user training.
M&O-138 | The Contractor must be responsible for hosting and providing technical support for the Training environments.
M&O-139 | The Contractor must make Training environments accessible to designated Department staff.
M&O-140 | The Contractor must manage and support batch schedules for the Training environments. The Contractor must execute specific requests from the Department or its designee for the training batch scheduler run cycles within two (2) hours.
M&O-141 | The Contractor must provide and maintain Pre-Production Environments to support performance testing, production triage, problem analysis, emergency Releases, and patch testing.
M&O-142 | The Contractor must provide and maintain Pre-Production Environments configured with the current production code base to support testing of data fixes prior to Deployment.
M&O-143 | The Contractor must provide and maintain Pre-Production Environments configured and sized in accordance with Production Environments.
M&O-144 | The Contractor must provide and maintain Production Environments to support all production systems, functions, and operations.
M&O-145 | The Contractor must provide and maintain Production Environments to support all DR systems, functions, and operations in accordance with the Department’s BC/DR Plan. Refer to Section 5.2.4.4 – Business Continuity and Disaster Recovery for additional requirements.
M&O-146 | The Contractor must provide internet-based access to Production Environments in accordance with approved roles and responsibilities.
M&O-147 | The Contractor must provide concurrently available environments to authorized Department users, Contractor staff, and oversight Contractors retained by the Department.
M&O-148 | The Contractor must provide designated staff with real-time access to system jobs and maintenance schedules, submission and processing statistics, and system performance tools. The Contractor must provide the ability to backup, recover, restart, and cancel jobs.
M&O-149 | The Contractor must develop project work plans that include tasks, summary tasks, and activities reflected in project schedules and must specify task start and end dates that align with high-level milestones defined in the M&O Manual.
M&O-150 | The Contractor must prepare and provide the Department with daily and weekly Operations Reports.
M&O-151 | The Contractor must adopt, update, and maintain a Business Rules Catalog. The catalog must include the purpose, logic, and dependencies of all business rules and must enumerate attributes such as rule name, rule description, conditions, actions, priority, version, and status.
M&O-152 | The Contractor must produce and maintain documentation for each business rule within the Converged E&E System, including rule logic, decision tables, flow charts, and examples of inputs with expected outputs. The Contractor must be responsible for business rules, including rule logic, decision tables, flow charts, and input and output examples.
M&O-153 | The Contractor must develop and maintain a guide for leveraging the existing BRE, OIA, within the Converged E&E System. This guide must address system-specific pre-Deployment checks such as integration testing, Deployment steps for system changes affecting business rules, and post-Deployment validation procedures. The Contractor must be responsible for system-specific business rule activities, including pre-Deployment checks and post-Deployment validation.
M&O-154 | The Contractor must develop and maintain documentation to support compliance of business rules within the Converged E&E System with internal and external regulatory requirements. Documentation must include compliance checklists, audit logs, and governance policies and must also include coordination with other vendors to incorporate documentation for leveraged BRE rules through shared repositories or interfaces.
M&O-155 | The Contractor must provide a MITA Business Capability Matrix and a transformation roadmap for each Converged E&E System business process model describing the MITA Maturity Model. The Contractor must document the MITA Business Capability Matrix in the Department’s Enterprise Architecture tool, as specified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard.
M&O-156 | The Contractor must integrate the Enterprise Architecture tool through an API that leverages the Department’s API Manager once it becomes available.
M&O-157 | The Contractor must develop and expose web services to consumers using the following open standards: • XML • Web Services Description Language (WSDL) • REST • OpenAPI Specification (OAS) • Web Services Interoperability (WS-I) • Web Services Security (WS-Security) • SOAP • Universal Description, Discovery, and Integration (UDDI)
M&O-158 | System business processes must comply with business transaction standards mandated by the Affordable Care Act (ACA) HIPAA transaction standards, as follows: • Adoption of HIPAA transaction standards for electronic healthcare transactions • Compliance of Converged E&E System electronic E&E transactions with operating rules defined in Health Information Technology (HIT) Policy and Standards • Use of an information exchange model based on NIEM, as required by the ACA
M&O-159 | If requested by the Department, the Contractor must support the Department’s process to renew licensed products with unlimited licenses that require renewal and certification. Support may include, at a minimum, the following: • Performing license utilization assessments, including usage metrics, under- and over-utilization, recommended license types, number of users required, terms of use, and compliance • Gathering artifacts or other documentation requested by the software provider or the Department to complete license renewal activities • Supporting other license certification processes requested by the Department for products within the SA
M&O-160 | The Contractor must develop processes required to conduct inventory and asset management.
M&O-161 | The Contractor must adopt, update, and maintain required documentation and reports for software inventory management and software license compliance.
M&O-162 | The Contractor must track and document software license counts, software support end dates, software license end dates, and end-of-life dates in compliance with the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard, including through the License and Support Utilization Report and maintenance logs.
M&O-163 | The Contractor must assess potential impacts to networks and associated components resulting from modifications or upgrades to the system, third-party software, interfaces, and Department sites and networks.
M&O-164 | The Contractor must coordinate and communicate network management activities with the Department, interface partners, State sponsor agencies, and third-party vendors (e.g., telecommunications providers).
M&O-165 | The Contractor must manage and maintain interconnections and services between the Converged E&E System and interface partners. This includes joint monitoring, issue resolution, and documentation of shared responsibilities.
M&O-166 | The Contractor must provide written explanations addressing the cause, resolution, and correction time frame for all audit discrepancies.
M&O-167 | The Contractor must actively participate in, and provide assistance to, Department auditors during annual audits or audits conducted on another schedule as directed by the Department.
M&O-168 | The Contractor must work collaboratively with auditors and provide complete and accurate information and documentation.
M&O-169 | The Contractor must monitor the processing of batch files, including through automated alerts, and must review batch logs for all interfaces. These activities must be performed in accordance with the M&O Plan, the OHIP Infrastructure and Operations Domain document, Application Integration Standard, and the OHIP Infrastructure & Operations Domain Document, Log Management Standard. The Contractor must resolve defects resulting from failed batch or interface transactions in accordance with error notification SLAs and incident management processes.
M&O-170 | The Contractor must develop, deliver, maintain, and execute all M&O business support services deliverables required by this RFP, including the following: • Ongoing CMS post-certification reporting documenting continued compliance with CMS certification criteria, including the following: o Outcomes-based metrics o Evidence of system performance against certified standards o Required adjustments based on CMS guidance • Lost or stolen asset process defining procedures for lost or stolen assets Refer to Section 5.8 – Deliverables for additional requirements.
M&O-171 | When directed by the Department, the Contractor must procure and manage maintenance contracts for all software components and renew the contracts as required throughout the Contract term in compliance with the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard.
M&O-172 | The Contractor must notify the Department when no commercially available maintenance support exists for a software component.
M&O-173 | The Contractor must define equipment and software purchases and must document ongoing manufacturer maintenance and support arrangements, including software license agreements and financial information required for asset management, inventory management, and audit purposes.
M&O-174 | When directed by the Department, the Contractor must procure and manage licenses for all software components and renew them as required throughout the Contract term in compliance with the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard. The Contractor must notify the Department of the need for software procurement services one hundred and eighty (180) days in advance of any proposed software installation when software is required to support the Converged E&E System or the AMS. Software procured by the Contractor at the request of, or for, the Department must be licensed to the Department in accordance with the ownership requirements of the standard.
M&O-175 | The Contractor must prepare meeting minutes or notes, with optional recordings or transcriptions as agreed on, and for uploading the materials into Department’s document management system, as defined in the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard, unless otherwise directed by the Department. Meeting minutes must include, at a minimum, the following: • Information presented • Deliberation and courses of action considered • Decision-making summaries identifying considerations, authorizations, and responsible parties • Action items and decision items logged and included in subsequent meetings agendas
M&O-176 | The Contractor must assist the Department in evaluating the impact and cost of implementing federal or State statutory or regulatory changes, excluding routine program changes. Impact assessments must include, at a minimum, identification of impacted design components, known constraints, and use of the major system updates, the capacity-based team (CBT), or the enhancement process when a change falls outside the scope of M&O.
M&O-177 | The Contractor must support the Department in evaluating requests for audits. Evaluation criteria must include functional and data-related components including, at a minimum, the following: • Assessment of audit requests • Retrieval and analysis of requested data • Development of response recommendations for Department consideration
M&O-178 | The Contractor must not charge the Department for services rendered in connection with an audit.
M&O-179 | The Contractor must provide, upon Department request, copies of nonconfidential portions of the Contractor’s and its subcontractors’ internal audit reports that relate to the services provided under this Contract.
M&O-180 | The Contractor must follow governance processes established by the Department’s designated governance bodies, as defined in the OHIP MES Governance Framework provided during Contractor onboarding. These bodies include technical leadership and Enterprise Architecture representatives and manage technical changes in alignment with Department governance requirements. The designated governance bodies must review proposed changes to confirm alignment with the applicable OHIP MES Standards Framework, target architecture, strategic goals, and remediation of existing noncompliance, while engaging stakeholders as appropriate. The Contractor must track and log decisions issued by designated governance bodies using approved operational tools, as specified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard. Designated governance bodies must review and approve key items including, at a minimum, the following: • New IT projects or initiatives, including initial architecture designs and major subsequent architectural decisions • Significant updates or changes to existing systems that may affect the overall architecture, including major system updates, migrations, or system integrations • Introduction of new technologies, platforms, or tools • Changes impacting security architecture, including encryption methods, authentication processes, and other security controls • Changes required to comply with new regulatory or compliance mandates • High-level architecture documents outlining the overall approach and structure of a system or project prior to initiation of detailed design activities • Planned or updated technology standards, guidelines, and policies • Proof of Concepts or pilot projects with potential to scale or affect broader architectural decisions • Major infrastructure changes, including cloud migrations, hosting provider changes, or network redesigns • Changes to data models, data governance policies, and data integration approaches • Recommendations for performance improvements involving infrastructure or application design • Reviews of DR and BC architectures • Changes to software and cloud Bill of Materials (BOM)
M&O-181 | The Contractor must be responsible for confirming that all proposed additions, modifications, or improvements to software or infrastructure are reviewed by the appropriate governance bodies in alignment with OHIP MES Governance Framework and OHIP MES Standards Framework. Governance processes must include detailed analysis of proposed changes or improvements to confirm alignment with business goals and to minimize risks. Governance review objectives must include, at a minimum, the following: • Early review of architecture for improvements or new functionality to reduce cost and risk of later changes in the life cycle • Application of architecture best practices • Assessment of technology fit in alignment with enterprise goals • Adjustment of the roadmap when new ideas emerge
M&O-182 | The Contractor must actively participate in and support the following processes: • PCC • Change control meetings • Change evaluation • Risk and issue management • Service level management • Problem management • Incident management • Release and Deployment management • Deliverable review and approval • Service desk • Incident, change, and Release management • Technical change control Refer to the OHIP MES Standards Framework for additional details.
M&O-183 | The Contractor must work with the Department to prioritize and resolve CRs and service requests. A CR represents a formal request to significantly modify an existing system, process, or service and may require change control approval. A service request represents a formal request for support, assistance, or information related to an existing product or service and may include routine maintenance, troubleshooting, or simple tasks not requiring significant system changes.
M&O-184 | The Contractor must provide consultation and technical assistance on data analysis and methodology for business stakeholders (e.g., Division of Eligibility and Marketplace Integration [DEMI], Division of Operations and Systems [DOS], or other Department staff involved in eligibility, operations, or reporting). Support must include guidance on statistical methods, data visualization techniques, query optimization, trend analysis, predictive modeling, and compliance with CMS and OHIP standards, as needed to support decision-making and system improvements.
M&O-185 | The Contractor must make performance monitoring tools available to a minimum of three (3) additional users, as determined by the Department, on a floating basis and must provide unrestricted access to performance monitoring and failure alert data. Tools must support granular monitoring to assess SLA damages on an hourly basis or portion thereof.
M&O-186 | The Contractor must make performance monitoring and failure alert tools available to additional parties, such as QA vendors, for independent analysis and verification, as requested by the Department.
M&O-187 | The Contractor must conduct periodic and on-request performance testing, assess performance issues, and implement corrective actions necessary to operate the Converged E&E System at SLA-required performance levels throughout the Contract term.
M&O-188 | The Contractor must maintain all infrastructure and software for the Reporting Environment. The Reporting Environment includes any tool, service, or module that produces reports for the Contractor, the Department, or other stakeholders, as applicable. Reporting Environment infrastructure components and software include, at a minimum, the following: • Current MECM System components and tools as described in Section 3.3.2.3 – Technology Stack • Current AMS components and tools as described in Section 3.3.3.1 – Appeals Management System Technology Stack
M&O-189 | The Contractor must develop, deliver, maintain, and execute all M&O FinOps deliverables required by this RFP in compliance with the OHIP Infrastructure & Operations Domain Document, Cloud FinOps Standard, including the following: • Cloud FinOps Plan • Monthly Cloud Usage and Spend Report Refer to Section 5.8 – Deliverables for additional details.
M&O-190 | The Contractor must proactively communicate opportunities to reduce cloud usage by performing periodic spend analyses and providing recommendations for commitment opportunities to achieve improved pricing or discounts, in compliance with the OHIP Infrastructure & Operations Domain Document, Cloud FinOps Standard.
M&O-191 | The Contractor must perform weekly review of cloud usage and spend to identify variations from anticipated values and must review automated alerts on the same business day. These activities must be performed in compliance with the OHIP Infrastructure & Operations Domain Document, Cloud FinOps Standard. The Contractor must provide a Monthly Cloud Usage and Spend Report or ad hoc reports upon Department request.
M&O-192 | The Contractor must perform a monthly analysis of cloud usage and spend and track all identified optimization opportunities. When optimization activities are scheduled for implementation, the Contractor must incorporate these changes into forecasting reports and track outcomes to confirm that anticipated cost improvements are achieved.
M&O-193 | The Contractor must use native cloud cost and resource optimization tools, such as AWS Trusted Advisor and AWS Cost Optimization Hub, or Google Cloud Active Assist and the Cloud Billing FinOps Hub, or equivalent future tools to continuously monitor and identify over- and under-provisioned resources.
M&O-194 | The Contractor must maintain cloud performance requirements for compute and database services.
M&O-195 | The Contractor must conduct quarterly evaluations of cloud resources against cloud spend to identify potential optimization opportunities, in compliance with the OHIP Infrastructure & Operations Domain Document, Cloud FinOps Standard.
M&O-196 | The Contractor must conduct quarterly reviews of AWS S3 and GCS to identify optimization opportunities using AWS Storage Lens, GCS Intelligence, and manual reviews, in compliance with the OHIP Infrastructure & Operations Domain Document, Cloud FinOps Standard. Reviews must include validation of life cycle policies, including AWS S3 Lifecycle configuration and GCS Object Lifecycle Management, to confirm alignment with applicable retention requirements. The Contractor must document results in the Quarterly Spend Optimization Evaluation Summary.
M&O-197 | The Contractor must evaluate the current environment, existing cloud spend commitments, and planned workloads on a quarterly basis to develop savings plan or reserved instance recommendations for rate optimization, in compliance with the OHIP Infrastructure & Operations Domain Document, Cloud FinOps Standard.
M&O-198 | The Contractor must provide estimated pricing and a procurement schedule for the initial software BOM for third-party software under an agreed-upon timeline, in compliance with the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard. The software BOM must identify all components, libraries, dependencies, and modules that comprise a software application and must indicate the purchasing entity, either the Department or the Contractor. The software BOM must include itemized supporting details and estimated costs for planned third-party software procurement and renewal. The software BOM, and the items included within it, are subject to change based on new or revised scope or activities, with approval by an ARB established within the governance of each activity requiring software procurement services.
M&O-199 | The Contractor must continuously maintain and update the software BOM throughout the Contract term to reflect the current inventory of software products and versions, in compliance with the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard. The Contractor must annually report installed software details, including product category, product name, current version, support end dates, most recent available version, most recent supported version end dates, and product descriptions or comments. All software listed in the software BOM must be maintained at a manufacturer-supported version, defined as software version N minus one (1), unless the Department grants an exception. All changes to software and cloud BOMs must be documented through architectural reviews.
M&O-200 | If the Contractor is unable to procure third-party software on behalf of the Department due to legal, regulatory, or independence restrictions, the Contractor must perform independence checks on third-party software products upon creation of the software BOM and must promptly notify the Department of identified conflicts, in compliance with the OHIP Infrastructure & Operations Domain Document, Ongoing Licensing and Support Standard. If a conflict exists, the Contractor must support the Department in procuring the software directly while maintaining independence requirements or provide an alternative product for Department consideration. If the Department approves licensing of an alternate third-party solution, the Contractor must update the software BOM accordingly.
M&O-201 | The Contractor must establish a User Experience Monitoring and Feedback function as part of ongoing M&O to capture, analyze, and provide recommendations based on feedback from users of the Converged E&E System and the AMS. This function must integrate with service desk, incident management, and problem management practices defined in the OHIP Infrastructure & Operations Domain Document, ITSM Standard.
M&O-202 | The Contractor must convene recurring user advisory sessions to solicit user feedback and discuss potential solutions.
Footnotes:
1 | https://www.irs.gov/pub/irs-pdf/p1075.pdf
2 | https://www.ecfr.gov/current/title-45/subtitle-A/subchapter-C/part-160
3 | https://www.ecfr.gov/current/title-45/subtitle-A/subchapter-C/part-164
4 | https://www.cms.gov/medicare/regulations-guidance/guidance
5 | https://www.archives.nysed.gov/sites/archives/files/general-schedule_2016_2024rev.pdf
6 | https://www.health.ny.gov/professionals/ems/pdf/08-03.pdf
7 | https://its.ny.gov/system/files/documents/2025/12/nys-p08-005-accessibility-of-information-communication-technology.pdf

## Implementation Approach
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
IMP-01 | The Contractor must achieve a production-ready Converged E&E System that is fully operational and capable of processing new applications, renewals, and enrollment transactions for Medicaid, Child Health Plus (CHPlus), Basic Health Program (BHP), and Qualified Health Plans (QHPs) no later than July 1, 2030.
IMP-02 | The Contractor must make all QHPs, BHP, CHPlus, and Medicaid populations available in the Converged E&E System prior to the start of Open Enrollment for Coverage Year 2031.
IMP-03 | The Contractor must maintain uninterrupted coverage access for all actively enrolled consumers throughout implementation of the Converged E&E System. No consumer may experience a coverage gap as a result of system migration activities.
IMP-04 | The Contractor must collaborate with the Department to determine the optimal implementation strategy for all programs supported by the NYSOH System.
IMP-05 | The Contractor must leverage the existing modular, cloud-native architecture of the MECM System to build the Converged E&E System.
IMP-06 | The Contractor must design and develop any new components of the Converged E&E System using a modular, cloud-native architectural approach to establish a modern technology environment by decomposing the system into independent, scalable microservices. This approach must include the DDI of service components to achieve cloud-native optimization while maintaining data integrity, compliance, and seamless operations. These microservices must enhance flexibility, scalability, resilience, compliance, and operational efficiency.
IMP-07 | The Contractor must structure the Converged E&E System into independent services organized around the Department’s business domains, such as user authentication, data processing, and reporting.
IMP-08 | The Contractor must specify bounded contexts to avoid creating a distributed monolith and must outline any applicable incremental migration patterns, such the Strangler Fig, if used.
IMP-09 | The Contractor must apply a decentralized approach that allows services to use appropriate programming languages and persistence technologies while emphasizing shared interoperability practices, such as API contracts and tolerant readers for versioning.
IMP-10 | The Contractor must implement mechanisms for inter-service communication (e.g., synchronous HTTP or asynchronous event-driven messaging), including strategies for handling eventual consistency, sagas for distributed transactions, and circuit breakers for fault tolerance.
IMP-11 | The Contractor must employ infrastructure automation, CI/CD pipelines, containerization (e.g., Docker), orchestration (e.g., Kubernetes), and monitoring tools to enable independent Deployments and real-time failure detection.
IMP-12 | The Converged E&E System must support horizontal scaling of individual services, efficient resource optimization, and performance testing within a distributed environment.
IMP-13 | The Contractor must organize their team to assume and operate end to end services including ongoing maintenance and direct collaboration with Department stakeholders.
IMP-14 | The Converged E&E System must leverage the ESSs provided by the Department and other interfaces from third-party vendors, as well as the Health Member ID (HMID), lakehouse, analytics, and reporting capabilities provided by the EDW vendor once those capabilities become available.
IMP-15 | The Contractor must fully integrate the Converged E&E System with all required external systems prior to production Deployment. No production Deployment may occur with unresolved critical interface deficiencies.
IMP-16 | The Contractor must develop and maintain an integration catalog within the ITDD and an ICD for each interface.
IMP-17 | The Contractor must complete successful bidirectional transaction testing for each interface in the system Integration Testing (SIT) environment, including carrier testing, with documented results demonstrating correct data exchange, error detection, and recovery prior to Deployment.
IMP-18 | The Contractor must obtain confirmation from the IT trading partner that each interface has been accepted in the partner environment and documented through an interface certification acknowledgement prior to Deployment.
IMP-19 | The Contractor must conduct performance testing for each interface to demonstrate that throughput and response-time thresholds are met under peak load conditions prior to Deployment.

## Business Requirements
Requirement Number | Capability | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column D is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
BUS-01 | N/A | The Converged E&E System and AMS must adhere to all requirements governing the MECM System and the AMS as defined at the conclusion of the Transition-In period. Development of the MECM System is ongoing. Requirements as of June 30, 2026 are set forth in Exhibit G.12 – Current MECM System and AMS Requirements Traceability Matrix. The Department will provide the Contractor with an updated version of the MECM System and AMS Requirements Traceability Matrix during the Transition-In period.
BUS-02 | N/A | The Converged E&E System and the AMS must comply with all applicable State and federal policies.
CUS-01 | Customer Service | The Converged E&E System must allow qualified business partners to apply for premium tax credits and Cost-Sharing Reductions (CSRs) on behalf of the consumer in the Assistor Portal and Partner Portal.
CUS-02 | Customer Service | The Converged E&E System must allow qualified business partners to submit documents for verification requests on behalf of the consumer in the Assistor Portal and Partner Portal.
CUS-03 | Customer Service | The Converged E&E System must allow qualified business partners to shop for, compare, and select a QHP or Stand-Alone Dental Plan (SADP) for enrollment on behalf of the consumer in the Assistor Portal and Partner Portal.
CUS-04 | Customer Service | The Converged E&E System must allow qualified business partners access to apply for and review Special Enrollment Periods (SEPs) on behalf of the consumer in the Assistor Portal and Partner Portal.
CUS-05 | Customer Service | The Converged E&E System must allow qualified business partners to apply for BHP, CHPlus, and Medicaid on behalf of the consumer in the Assistor Portal and Partner Portal.
CUS-06 | Customer Service | The Converged E&E System must allow qualified business partners to shop for, compare, and select a health plan for BHP, CHPlus, and Medicaid on behalf of the consumer in the Assistor Portal and Partner Portal.
CUS-07 | Customer Service | The Converged E&E system must enable licensed agents and brokers, as well as certified Navigators and Assistors, to submit applications for qualified individuals for premium tax credits, CSRs, BHP, CHPlus, Medicaid, and any additional program as identified by the Department.
CUS-08 | Customer Service | The Converged E&E System must support customer inquiries that include, at a minimum, the following: • Capture inquiries • Track inquiries • Manage inquiries • Close inquiries • Additional features as defined by the Department
CUS-09 | Customer Service | The Converged E&E System must leverage existing integrations with the Customer Service System to synchronize consumer inquiries to an associated member or case record.
SHC-01 | Stakeholder Communications | The Converged E&E System must allow authorized users to request an informational email regarding other benefit programs, such as the Supplemental Nutrition Assistance Program (SNAP), when specified criteria are met by any household member on the account.
SHC-02 | Stakeholder Communications | The Converged E&E System must automatically notify content owners and system administrators when content is approaching its scheduled review date or has not been updated within a configurable time frame.
SHC-03 | Stakeholder Communications | The Converged E&E System must include a workflow that allows authorized users to publish urgent information, such as public health alerts or system outage notifications, immediately by bypassing standard approval steps.
SHC-04 | Stakeholder Communications | The Converged E&E System must allow authorized users to send out information related to Executive and Department priorities on an ad hoc basis through communication channels that include, at a minimum, the following: • Mail • Email • Text (Short Message Service [SMS]) • WhatsApp
CHM-01 | Channel Management | The Converged E&E system must have an identity proofing process for Assistors that complies with Department, State, and federal policies.
CHM-02 | Channel Management | The Converged E&E System must allow account creation and profile completion for Assistors.
CHM-03 | Channel Management | The Converged E&E System must support the creation of a Primary Oversight Manager and Secondary Oversight Manager roles by authorized users, which may only be assigned to Assistors or brokers who are currently certified or licensed by the Office of NYSOH.
CHM-04 | Channel Management | The Converged E&E System must allow designated users to assign, change, and remove the Primary Oversight Manager and Secondary Oversight Manager roles through the user interface in the Assistor Portal.
CHM-05 | Channel Management | The Converged E&E System must allow designated users to assign multiple Assistors and brokers to a Secondary Oversight Manager through a bulk transfer process.
CHM-06 | Channel Management | The Converged E&E System must allow designated users to assign or unassign a Secondary Oversight Manager to an Assistor or broker through the user interface in the Assistor Portal.
CHM-07 | Channel Management | The Converged E&E System must maintain Primary and Secondary Oversight Manager roles with the ability to view, in read-only mode, the dashboards of all assigned Assistors or brokers and associated clients within the same Assistor agency in the Assistor Portal.
CHM-08 | Channel Management | The Converged E&E System must allow consumers to link their NY.gov account to an existing application or case when the application or case was initiated or completed by an Assistor, Provider, or Customer Service Representative.
CHM-09 | Channel Management | The Converged E&E System must allow users to search for Assistors or brokers by preferred language.
CHM-10 | Channel Management | The Converged E&E System must provide links to Issuer websites that offer health plans for QHPs and SADPs to consumers during enrollment.
CHM-11 | Channel Management | The Converged E&E System must provide a small business Employer Portal that includes, at a minimum, the following: • Account setup and management • Ability to submit application for eligibility determination • Qualification for tax credits
CHM-12 | Channel Management | The Converged E&E System must allow Issuers to view and download invoices from the Issuer Portal.
CHM-13 | Channel Management | The Converged E&E System must allow Issuers to send reinstatements through the Issuer Portal to reinstate coverage for individuals.
CHM-14 | Channel Management | The Converged E&E System must provide configurable termination management that enables authorized parties, such as Issuers and administrative users, to initiate, track, and process coverage terminations, cancellations, and reinstatements. This capability must support execution through both manual user interfaces, such as the Issuer Portal, and standard electronic transactions, including outbound and inbound Accredited Standards Committee (ASC) X12 834 enrollment and maintenance transactions and designated future interfaces.
CHM-15 | Channel Management | The Converged E&E System must provide an Issuer Portal that supports account creation, setup, and management by Issuers and authorized users.
CHM-16 | Channel Management | The Converged E&E System must be configurable to allow changes to the Issuer Portal without customization and without requiring change requests that carry additional costs.
CHM-17 | Channel Management | The Converged E&E System must allow authorized system administrators to customize global graphical user interface (GUI) elements, including logos, color palettes, and typography, without requiring underlying code changes.
CHM-18 | Channel Management | The Converged E&E System must provide the ability to develop and deploy portal pages with translated content.
CHM-19 | Channel Management | The Converged E&E System must allow the use of a custom, branded domain name for the public-facing website.
CHM-20 | Channel Management | The Converged E&E System must allow the use of a custom, branded domain name for the Member Portal, Worker Portal, Issuer Portal, Partner Portal, Employer Portal, and Assistor Portal.
CHM-21 | Channel Management | The Converged E&E System must allow the creation and management of multiple subdomains to segment content for different audiences.
CHM-22 | Channel Management | The Converged E&E System must include functionality to define a mandatory review date for all online and web content.
CHM-23 | Channel Management | The Converged E&E System must allow bulk updates to content, enabling administrators to update recurring information across multiple pages simultaneously.
CHM-24 | Channel Management | The Converged E&E System must provide a content archiving process that allows administrators to remove outdated content from the live site while retaining it in a secure, nonpublic archive for compliance and historical recordkeeping.
CHM-25 | Channel Management | The Contractor must maintain period review of all online and web content for accuracy and relevance at a frequency determined by the Department.
CHM-26 | Channel Management | The Converged E&E System must allow users to browse general information, check Open Enrollment dates, and explore basic eligibility without logging in.
CHM-27 | Channel Management | The Converged E&E System must maintain fluid layouts that adapt to any screen size and require minimal scrolling.
CHM-28 | Channel Management | The Converged E&E System must maintain public-facing, unauthenticated pages and follow a responsive website design.
CHM-29 | Channel Management | The Converged E&E System must not allow hosting of any websites in a Department environment unless otherwise indicated by the Department.
CHM-30 | Channel Management | The Converged E&E System must allow qualified entities to access the Assistor Portal, Member Portal, Worker Portal, Issuer Portal, Partner Portal, and Employer Portal as determined by the Department.
CHM-31 | Channel Management | The Converged E&E System must provide identity proofing, including multi-factor authentication (MFA) flows in accordance with federal guidance, and offer alternative verification routes and escalation for failures with audit logging.
CHM-32 | Channel Management | The Converged E&E System must include a live chat interface for customer inquiries and assistance that can be configured based on the Department's business and technical needs.
CHM-33 | Channel Management | The Converged E&E System must support the use of virtual agents powered by artificial intelligence (AI) within authenticated and secured areas of the application that operate within configurable permission boundaries and support seamless escalation to live human agents.
CHM-34 | Channel Management | The Converged E&E System must allow an agent to view the user's profile, current application status, and the specific page the user is viewing if an authenticated live chat is initiated.
CHM-35 | Channel Management | The Converged E&E System must allow agents to transfer chats to another department, such as appeals or technical support, or escalate to a supervisor while retaining the entire chat history.
CHM-36 | Channel Management | The Converged E&E System must provide a dashboard for Customer Service Center workers to manage multiple concurrent live chat sessions.
CHM-37 | Channel Management | The Converged E&E System may, at the Department’s discretion and direction, provide users with supplemental or complementary functionality through a mobile application.
CHM-38 | Channel Management | The Converged E&E System must allow the account holder or representative the ability to receive notices in an alternative notice format in accordance with Department, State, and federal policies.
CHM-39 | Channel Management | The Converged E&E System must allow the Account Holder or Representative to receive notices in an alternative format in accordance with Department, State, and federal policies.
CHM-40 | Channel Management | The Converged E&E System must use a single, centralized knowledge base to provide consistent answers to the chatbot and web FAQs across all channels.
CHM-41 | Channel Management | The Converged E&E System must present the Customer Service Representative with the user's last known location in the application process if a user abandons a process on one channel and switches to another, including when transitioning from a web application to the Customer Service Center.
CON-01 | Consumer Management | The Converged E&E System must provide anonymous plan comparisons for employers based on criteria determined by the Department and in accordance with State and federal policies.
CON-02 | Consumer Management | The Converged E&E System must allow consumers and anonymous users to perform a basic search for providers using keywords, such as provider name, clinic name, and specialty.
CON-03 | Consumer Management | The Converged E&E System must allow consumers and anonymous browsers to search for providers by location, including city, state, or ZIP Code, and specify a search radius (e.g., within five [5], ten [10], or twenty-five [25] miles).
CON-04 | Consumer Management | The Converged E&E System must allow consumers and anonymous users to filter provider search results based on a specific health plan or network to confirm the provider is in-network.
CON-05 | Consumer Management | The Converged E&E System must provide advanced filtering options for provider searches that include, at a minimum, the following: • Provider type (e.g., physician, specialist, hospital, urgent care) • Specialty (e.g., cardiology, pediatrics) • Languages spoken • Accepting new patients (yes or no) • Provider gender
CON-06 | Consumer Management | The Converged E&E System must display provider search results in a clear, easy-to-read list format that includes a summary of information for each provider.
CON-07 | Consumer Management | The Converged E&E System must display provider search results through a detailed profile page that includes, at a minimum, the following: • Full name • Credentials • Specialties • Board certifications • Office locations • Hours • Contact information • Hospital affiliations • Languages spoken • Wheelchair accessibility information • Health plans or networks accepted
CON-08 | Consumer Management | The Converged E&E System must include a link to an external mapping service, such as Google Maps, on each provider profile page to enable users to receive directions, such as walking, driving, or public transit, to the provider's location.
CON-09 | Consumer Management | The Converged E&E System must comply with age validation and dependent relationship rules based in accordance with State and federal laws.
CON-10 | Consumer Management | The Converged E&E System must identify individuals who have died at a frequency determined by the Department and in accordance with State and federal policies.
CON-11 | Consumer Management | The Converged E&E System must identify individuals who have received Advance Premium Tax Credits (APTCs) or CSRs and have become eligible for enrollment in Medicare on a basis determined by the Department and in accordance with State and federal policies.
CON-12 | Consumer Management | The Converged E&E System must allow force closures that end the eligibility and coverage of individuals based on criteria set by the Department and in accordance with State and federal policies.
CON-13 | Consumer Management | The Converged E&E System must determine employer eligibility based on, at a minimum, the following: • Status as a small employer with one (1) to one hundred (100) employees • Offering coverage to, at a minimum, all full-time employees • Principal business address in New York or offering coverage to each eligible employee serving a primary worksite in New York • Compliance with federal and State codes Eligibility determinations must be supported using Department's BRE. The Contractor must change eligibility rules at the Department's request without customization and without requiring change requests that carry additional costs.
CON-14 | Consumer Management | The Converged E&E System must provide on-screen notices and confirmations throughout the shopping and plan selection process.
CON-15 | Consumer Management | The Converged E&E System must support execution of all annual enrollment periods without solution customizations that require change orders or carry additional costs.
CON-16 | Consumer Management | The Converged E&E System must maintain and enhance a solution architecture to support up to three (3) SEPs per year without solution customizations that require change orders or carry additional costs.
CON-17 | Consumer Management | The Converged E&E System must be configured to perform plan selection and management for Medicaid, CHPlus, BHP, and QHPs.
CON-18 | Consumer Management | The Converged E&E System must be configured to perform plan selection and management for APTCs and CSRs.
CON-19 | Consumer Management | The Converged E&E System must accept selection of a health plan by individuals determined eligible for enrollment in Medicaid, BHP, CHPlus, or QHPs.
CON-20 | Consumer Management | The Converged E&E System must allow enrollment period and end date adjustments when an individual is redetermined eligible for Medicaid, CHPlus, BHP, or APTC, as determined by the Department and in accordance with State and federal policies.
CON-21 | Consumer Management | The Converged E&E System must allow consumers to shop for and select plans that include, at a minimum, medical and dental benefits, medical-only plans, and dental-only plans during enrollment.
CON-22 | Consumer Management | The Converged E&E System must allow the account holder to complete plan selection for future programs to support enrollment without disruption of coverage.
CON-23 | Consumer Management | The Converged E&E System must perform enrollment and disenrollment 834 transactions for Medicaid, BHP, CHPlus, and QHPs.
CON-24 | Consumer Management | The Converged E&E System must indicate enrollment deadlines and effective dates in accordance with Department, State, and federal policies.
CON-25 | Consumer Management | The Converged E&E System must provide a single application that is configurable to support a dynamic experience that adapts questions in real time based on user inputs to determine eligibility for all programs.
CON-26 | Consumer Management | The Converged E&E System must accept applications and determine eligibility for all programs at any time during the year in accordance with Department, State, and federal policies.
CON-27 | Consumer Management | The Converged E&E System must limit the collection of information from and about individuals seeking coverage to the minimum necessary to process an application.
CON-28 | Consumer Management | The Converged E&E System must allow consumers to select their preferred language for the application.
CON-29 | Consumer Management | The Converged E&E System must continue to perform annual redeterminations of eligibility for qualified individuals for Medicaid, CHPlus, BHP, and QHPs, which must include, at a minimum, the following: • Delivery of a notice of annual redetermination to consumers • Retrieval of current information from federal and State data sources • Requests for additional information from consumers as needed • Validation of updated and additional information provided by consumers • Completion of eligibility redeterminations • Recalculation of the amount of advance payments of the premium tax credit when a redetermination results in a change • Determination of cost-sharing category based on updated household income • Notification of eligibility redetermination results through the consumer's preferred communication channel
CON-30 | Consumer Management | The Converged E&E System must conduct re-enrollment in a health plan for individuals who remain eligible for enrollment in Medicaid, BHP, CHPlus, and QHPs, in accordance with Department, State, and federal policies.
CON-31 | Consumer Management | The Converged E&E System must be configured to allow additional verification of information as defined by the Department and in accordance with State and federal policies.
CON-32 | Consumer Management | The Converged E&E System must provide links to Issuer websites that offer QHPs on the Small Business Health Options Program (SHOP) marketplace to employers during anonymous browsing.
CON-33 | Consumer Management | The Converged E&E System must prevent the collection of information from and about individuals who are anonymously browsing and not seeking or applying for coverage.
CON-34 | Consumer Management | The Converged E&E System must provide anonymous screening of eligibility without requiring consumers to establish an account.
CON-35 | Consumer Management | The Converged E&E System must provide anonymous plan comparison without requiring consumers to establish an account.
CON-36 | Consumer Management | The Converged E&E System must provide consumers and anonymous browsers with shopping and enrollment features for medical and dental plans that include, at a minimum, the following: • Provider directory • Indicators of plan characteristics • Consistent presentation of standard plan features • Emphasis on points of comparison selected by the consumer • Comparison across plan metal tiers, such as Bronze, Silver, Gold, Platinum, and Catastrophic • Comparison of benefits and coverage using a standardized presentation format • Monthly premium estimator including gross premiums with net savings • Out-of-pocket cost estimator • APTC calculator • Cost-sharing information • Plan quality ratings • Medical loss ratio • Results of enrollee satisfaction surveys • Enrollee commentaries about plans and Issuers • Search criteria • Advanced filtering
CON-37 | Consumer Management | The Converged E&E System must provide links to Issuer websites that offer health plans to consumers during anonymous browsing.
CON-38 | Consumer Management | The Converged E&E System must provide anonymous employer shopping and decision features that include, at a minimum, the following: • Provider directory • Indicators of plan characteristics • Consistent presentation of standard plan features • Emphasis on points of comparison selected by the user • Plan comparison • Comparison of benefits and coverage using a standardized presentation format • Contribution estimator • Plan quality ratings • Results of enrollee satisfaction surveys • Enrollee commentaries about plans and Issuers • Search criteria
CON-39 | Consumer Management | The Converged E&E System must allow designated users to create Assistor and agency profile information.
CON-40 | Consumer Management | The Converged E&E System must allow designated users to update Assistor and agency profile information.
CON-41 | Consumer Management | The Converged E&E System must allow a user assigned the Primary Oversight Manager role to view all Assistors or brokers within the agency where the Primary Oversight Manager role is assigned.
CON-42 | Consumer Management | The Converged E&E System must allow Primary and Secondary Assistor Oversight Managers to view defined client events that occurred within the previous two (2) years of uninterrupted association with the Assistor agency.
CON-43 | Consumer Management | The Converged E&E System must allow Primary and Secondary Assistor Oversight Managers to view activity logs of their assigned Assistors for the previous two (2) years of uninterrupted association with the Assistor agency.
CON-44 | Consumer Management | The Converged E&E System must allow qualified business partners to access client electronic communications, notices, and health insurance-related tax forms.
CON-45 | Consumer Management | The Converged E&E System must allow users to select their preferred language for all written communications, such as letters, emails, and notifications.
CON-46 | Consumer Management | The Converged E&E System must allow administrative users to search and view Assistor and Provider activity.
CON-47 | Consumer Management | The Converged E&E System must allow qualified entities to submit appeals on behalf of the consumer through the Assistor and Partner Portals.
CON-48 | Consumer Management | The Converged E&E System must allow designated users to identify potential duplicate accounts when contacted by a potential duplicate account holder.
CON-49 | Consumer Management | The Converged E&E System must allow for an administrative user to search Assistor and Provider accounts and view all associated case and member records.
CON-50 | Consumer Management | The Converged E&E System must allow consumers to extend and remove access to their accounts for designated individuals, such as Providers, Certified Application Counselors (CACs), Navigators, and brokers.
CON-51 | Consumer Management | The Converged E&E System must allow consumers to delegate authority to designated individuals, such as Providers, CACs, Navigators, and brokers, for purposes of applying, plan selection, and enrollment.
CON-52 | Consumer Management | The Converged E&E System must allow designated users to capture, update, and close consumer inquiries within the associated member or case record.
STP-01 | Service Transaction Processing | The Converged E&E System must calculate advance payments of the premium tax credit in accordance with 26 CFR §1.36B-3.
STP-02 | Service Transaction Processing | The Converged E&E System must provide instructions in the Member Portal on how consumers can contact their selected Issuer and pay their premiums as part of plan information.
STP-03 | Service Transaction Processing | The Converged E&E System must enable enrollees to accept less than the full amount of advance payments of the premium tax credit for which they are determined eligible.
STP-04 | Service Transaction Processing | The Converged E&E System must support configurable precision and rounding logic for all monetary and numeric outputs from internal or external calculation services that are applicable across all health insurance programs and comply Department, State, and federal policies, rules, and regulations.
STP-05 | Service Transaction Processing | The Converged E&E System must accurately calculate premiums for display to consumers using a defined methodology in accordance with Department, State, and federal policies.
STP-06 | Service Transaction Processing | The Converged E&E System must display the premium amount, if applicable, in plan information in the Member Portal.
STP-07 | Service Transaction Processing | The Converged E&E System must calculate CSRs in accordance with CMS methodology under 45 CFR § 155.305(g).
STP-08 | Service Transaction Processing | The Converged E&E System must generate accurate monthly premium invoices for each Issuer based on a configurable monthly billing cycle.
STP-09 | Service Transaction Processing | The Converged E&E System must generate accurate monthly premium invoices for each Issuer based on the latest enrollment data.
STP-10 | Service Transaction Processing | The Converged E&E System must use configurable invoice templates that can be customized for different Issuers.
STP-11 | Service Transaction Processing | The Converged E&E System must provide detailed reporting and analytics on all generated invoices.
STP-12 | Service Transaction Processing | The Converged E&E System must automatically identify discrepancies between the invoiced premium amount and the actual payment received and determine the delta between a modified transaction and the original submission.
STP-13 | Service Transaction Processing | The Converged E&E System must log identified discrepancies for premium invoices as exception cases in the system for further investigation and resolution.
STP-14 | Service Transaction Processing | The Converged E&E system must maintain a complete audit trail of all actions taken to resolve each discrepancy.
STP-15 | Service Transaction Processing | The Converged E&E System must generate a notice to Issuers for any discrepancies through the Issuer’s preferred method.
STP-16 | Service Transaction Processing | The Converged E&E System must calculate the assessment fee due from each carrier monthly based on total premiums for plans sold by the carrier during the prior month.
STP-17 | Service Transaction Processing | The Converged E&E System must process a monthly carrier assessment fee invoice approval workflow.
STP-18 | Service Transaction Processing | The Converged E&E System must generate monthly invoices of assessment fees for each carrier in batch.
STP-19 | Service Transaction Processing | The Converged E&E System must provide payment details on carrier assessment fee invoices that include, at a minimum, the following: • Total premium amounts for all carrier plans • Line-item adjustments for carrier plans • Additional details as defined by the Department
STP-20 | Service Transaction Processing | The Converged E&E System must perform reconciliation monthly based on actual enrollee premiums and adjustments paid and reported by each carrier.
STP-21 | Service Transaction Processing | The Converged E&E System must identify cases where a third party is responsible for a member's health care costs and initiate recovery from the responsible party.
STP-22 | Service Transaction Processing | The Converged E&E System must provide detailed reporting and analytics on all benefit recovery activities, including the status of all cases, the amount of overpayments recovered, and the aging of outstanding debts.
STP-23 | Service Transaction Processing | The Converged E&E System must store and manage all rebate agreements, including details on rebate tiers, criteria, and payment terms.
STP-24 | Service Transaction Processing | The Converged E&E System must automatically validate rebate claims against the terms of the rebate agreement, as well as sales and transactional data.
STP-25 | Service Transaction Processing | The Converged E&E System must accurately calculate eligible rebate amounts based on validated claim data and the terms of the rebate agreement.
STP-26 | Service Transaction Processing | The Converged E&E System must reconcile all rebate payments with corresponding claims and generate accurate credit memos.
STP-27 | Service Transaction Processing | The Converged E&E System must maintain a complete audit trail of all rebate management activities.
STP-28 | Service Transaction Processing | The Converged E&E System must provide financial forecasting dashboards in the Worker Portal to support rebate program planning and budgeting.
STP-29 | Service Transaction Processing | The Converged E&E System must provide on-demand dashboards in the Worker Portal with insights into customer behavior and program effectiveness for rebate management.
STP-30 | Service Transaction Processing | The Converged E&E System must identify potential benefit overpayments by comparing claims data with E&E records, including identifying payments made for ineligible members, services, or duplicate claims.
STP-31 | Service Transaction Processing | The Converged E&E System must log all identified overpayments as benefit recovery cases in the system.
STP-32 | Service Transaction Processing | The Converged E&E System must provide a centralized platform for managing all benefit recovery cases, including assigning cases to the appropriate personnel, tracking the status of each case, and maintaining a complete audit trail.
STP-33 | Service Transaction Processing | The Converged E&E System must generate and send automated notifications and correspondence to members, providers, and other stakeholders regarding benefit recovery activities.
BPM-01 | Business Partner Management | The Converged E&E System must allow designated users to update business partner status, such as certified, decertified, or terminated.
BPM-02 | Business Partner Management | The Converged E&E System must allow for the creation of additional business partner roles.
BPM-03 | Business Partner Management | The Converged E&E System must maintain integrations with systems used by the Customer Service Center.
BPM-04 | Business Partner Management | The Converged E&E System must allow interfaces (refer to Section 5.2.5.1.F – System Integration for additional details), electronic data integration, or other mechanisms to securely exchange information between the Converged E&E System and other organizations and data sources that include, at a minimum, those listed in Exhibit G.25 – Converged E&E System and AMS Interfaces.
BPM-05 | Business Partner Management | The Converged E&E System must use open interfaces, previously developed APIs, and established web services to the fullest extent possible to facilitate integration, interfaces, and data exchange.
BPM-06 | Business Partner Management | The Converged E&E System must include interfaces to send consumer and appeals data to the AMS.
BPM-07 | Business Partner Management | The Converged E&E System must leverage the capabilities provided by the EDW to for all reporting as defined within this RFP once those capabilities become available.
BPM-08 | Business Partner Management | The Converged E&E System must provide secure account creation with integration to the NY.gov interface.
BPM-09 | Business Partner Management | The Converged E&E System must integrate with NY.gov for direct login and identity proofing of consumers, business partners, and other users as determined by the Department and State policies.
BPM-10 | Business Partner Management | The Converged E&E System must allow a user to be Identity Proofed through the Department of Motor Vehicles (DMV) Customer Identification Verification (CIDV) service, with multiple attempts allowed as determined by the Department and State policies.
PRM-01 | Program Management and Operations | The Converged E&E System must leverage the capabilities provided by the Department's BRE for related logic defined in this RFP.
PRM-02 | Program Management and Operations | The Converged E&E System must generate notifications when enrollment requirements, such as minimum standards and deadlines, are not met and send such notifications to the noticing engine.
PRM-03 | Program Management and Operations | The Converged E&E System must leverage the capabilities of the Department's document management service to support verification documents and paper applications.
PRM-04 | Program Management and Operations | The Converged E&E System must have all applicable functions described in 45 CFR Part 155 that are necessary to operate and maintain a State-Based Exchange (SBE) technology platform, including, at a minimum, the following: • Subpart D - Exchange Functions in the Individual Market: Eligibility Determinations for Exchange Participation and Insurance Affordability Programs • Subpart E - Exchange Functions in the Individual Market: Enrollment in QHPs • Subpart H - Exchange Functions: SHOP • Subpart K - Exchange Functions: Certification of QHPs • Subpart M - Oversight and Program Integrity Standards for State Exchanges • Subpart O - Quality Reporting Standards for Exchanges
PRM-05 | Program Management and Operations | The Converged E&E System must leverage the Department's BRE to perform rules-driven eligibility determinations, including Non-Modified Adjusted Gross Income (MAGI) Medicaid determinations that already exist in the MECM System, for the following: • Eligibility determinations for the following: o MAGI Medicaid o BHP o APTCs o CSRs o CHPlus o QHPs • Ability to enable changes to eligibility determination logic and rules without customization and without requiring change requests that carry additional costs
PRM-06 | Program Management and Operations | The Converged E&E System must maintain business rules supporting E&E for Medicaid, CHPlus, BHP, and QHPs external to the source code and in a common English format.
PRM-07 | Program Management and Operations | The Converged E&E System must provide an internal calculator that yields maximum APTC values consistent with the Federal Hub maximum APTC service, or a comparable service available at the time, for proposed eligibility determinations for annual or monthly renewals.
PRM-08 | Program Management and Operations | The Converged E&E System must follow tax filer and non-filer rules for Medicaid, CHPlus, BHP, and QHPs, including APTC, as determined by the Department and in accordance with State and federal policies.
PRM-09 | Program Management and Operations | The Converged E&E System must follow household composition rules for MAGI Medicaid, CHPlus, BHP, and QHPs, including APTC, as determined by the Department and in accordance with federal policies.
PRM-10 | Program Management and Operations | The Converged E&E System must leverage the Department's BRE to process determinations for the following special populations for Medicaid, BHP, CHPlus, and QHPs: • American Indian or Alaska Native status • Pregnancy • Incarceration • Student status • Non-citizen categories, including Aliessa populations • Special visa statuses • Households with multiple eligible program coverage • Health and Recovery Plan (HARP) individuals • Additional special populations as determined by Department, State, and federal laws
PRM-11 | Program Management and Operations | The Converged E&E System must leverage the Department's BRE to determine presumptive eligibility.
PRM-12 | Program Management and Operations | The Converged E&E System must process Change in Circumstance (CiC) events, such as income, household size, and address, in accordance with 45 CFR §155.330, including effective date logic and retroactivity rules, where applicable.
PRM-13 | Program Management and Operations | The Converged E&E System must support the completion of enrollment transactions for future eligibility.
PRM-14 | Program Management and Operations | The Converged E&E System must follow rules for setting coverage dates based on Department, State, and federal policies.
PRM-15 | Program Management and Operations | The Converged E&E System must follow rules for SEPs in accordance with Department, State, and federal policies.
PRM-16 | Program Management and Operations | The Converged E&E System must follow rules for Medicaid managed care lock-in in accordance with Department, State, and federal policies.
PRM-17 | Program Management and Operations | The Converged E&E System must enable changes to enrollment and plan selection logic and rules without customization and without requiring change requests that carry additional costs.
PRM-18 | Program Management and Operations | The Converged E&E System must support Open Enrollment and SEPs, including plan selection and management, consistent with 45 CFR §155.420, during which qualified individuals may enroll in or change QHPs.
PRM-19 | Program Management and Operations | The Converged E&E System must automatically determine correct coverage effective dates.
PRM-20 | Program Management and Operations | The Converged E&E System must transmit to Issuers the information necessary to enroll eligible applicants in the health plan of their choice for Medicaid, BHP, CHPlus, and QHPs.
PRM-21 | Program Management and Operations | The Converged E&E System must receive from Issuers acknowledgements of receipt of E&E information transmitted by the Converged System for Medicaid, BHP, CHPlus, and QHPs.
PRM-22 | Program Management and Operations | The Converged E&E System must enable the initiation of termination of enrollment and coverage by the individual or the Issuer.
PRM-23 | Program Management and Operations | The Converged E&E System must determine the effective date of termination in accordance with 45 CFR §155.430.
PRM-24 | Program Management and Operations | The Converged E&E System must allow reinstatement due to outstanding premium and must generate new 834 transactions for all previous enrollees for reinstatement.
PRM-25 | Program Management and Operations | The Converged E&E System must support the generation, validation, and transmission of 834 Electronic Data Interchange (EDI) transactions for all eligible individuals, households, and groups across all coverage types and plan categories in accordance with Department, State, and federal policies, rules, and regulations.
PRM-26 | Program Management and Operations | The Converged E&E System must support the generation, validation, and transmission of 834 EDI transactions to all Issuers in compliance with Department, State, and federal policies, rules, and regulations for enrollment events, including, at a minimum, the following: • Enrollment • Re-enrollment • Reinstatement • Termination • Demographic change • Plan change • Retroactive adjustment
PRM-27 | Program Management and Operations | The Converged E&E System must process disenrollments and terminations for QHPs and CHPlus from Issuers due to nonpayment.
PRM-28 | Program Management and Operations | The Converged E&E System must direct consumers to make premium payments to the Issuer of the plan in which they are enrolled.
PRM-29 | Program Management and Operations | The Converged E&E System must provide an Issuer management engine that enables administrative users to search, review, certify, or disallow Issuers in the Issuer Portal.
PRM-30 | Program Management and Operations | The Converged E&E System must process System for Electronic Rate and Form Filing (SERFF) templates from Issuers.
PRM-31 | Program Management and Operations | The Converged E&E System must allow Issuers, administrative users, and other designated users to search and view SERFF data in the Issuer Portal.
PRM-32 | Program Management and Operations | The Converged E&E System must provide Issuer certification reporting functionality that includes, at a minimum, the following: • Monthly and annual reports • Ad hoc reports • Additional reporting as defined by the Department
PRM-33 | Program Management and Operations | The Converged &E System must provide the ability for an Issuer to submit a certification application in the Issuer Portal.
PRM-34 | Program Management and Operations | The Converged E&E System must allow Issuers and administrative users to search, view, and manage health plan rates in the Issuer Portal that include, at a minimum, the following: • Rate effective dates • benefit category • Monthly premium
PRM-35 | Program Management and Operations | The Converged E&E System must allow Issuers and administrative users to search, view, and manage health plan information in the Issuer Portal that includes, at a minimum, the following: • Issuer logo • Plan name • Issuer name • Level of coverage • Plan effective dates • Plan status • Plan counties
PRM-36 | Program Management and Operations | The Converged E&E System must include a disallowance process for administrative users and other designated users.
PRM-37 | Program Management and Operations | The Converged E&E System must allow plan and rate preview for insurance Issuers and administrative users during recurring data correction windows in the Issuer Portal.
PRM-38 | Program Management and Operations | The Converged E&E System must allow reconciliation and correction of plan and rate specification information with Issuers.
PRM-39 | Program Management and Operations | The Converged E&E System must allow dental plans to be offered in conjunction with a QHP or as an SADP.
PRM-40 | Program Management and Operations | The Converged E&E System must process certification of QHPs and SADPs.
PRM-41 | Program Management and Operations | The Converged E&E System must process decertification of QHPs and SADPs.
PRM-42 | Program Management and Operations | The Converged E&E System must allow QHP and SADP Issuers to make annual changes to their rates for the Individual Marketplace in the Issuer Portal.
PRM-43 | Program Management and Operations | The Converged E&E System must process applications for certification from Issuers.
PRM-44 | Program Management and Operations | The Converged E&E System must allow authorized users to disenroll Issuers.
PRM-45 | Program Management and Operations | The Converged E&E System must capture Issuer data defined by the Department for all individual health and dental plans purchased by consumers.
PRM-46 | Program Management and Operations | The Converged E&E System must capture enrollment and premium data received from Issuers.
PRM-47 | Program Management and Operations | The Converged E&E System must provide Issuer assessment reporting functionality that includes, at a minimum, the following: • Monthly and annual reports • Ad hoc reports • Additional reporting as defined by the Department
PRM-48 | Program Management and Operations | The Converged E&E System must provide Issuer rate reporting functionality that includes, at a minimum, the following: • Monthly and annual reports • Ad hoc reports • Additional reporting as defined by the Department
PRM-49 | Program Management and Operations | The Converged E&E System must capture and process user data for voter registration purposes in alignment with Department regulations and State and federal law.
PRM-50 | Program Management and Operations | The Converged E&E System must create a report of voter registration responses as specified by the Department.
PRM-51 | Program Management and Operations | The Converged E&E System must provide that data captured by the Converged E&E System can be transmitted to the EDW for reporting analytics.
PRM-52 | Program Management and Operations | The Converged E&E System must work with the Department to define the specific data to be captured in the Converged E&E System and the EDW.
PRM-53 | Program Management and Operations | The Converged E&E System must capture and report organ donor responses.
PRM-54 | Program Management and Operations | The Converged E&E System must create a report of organ donor responses as specified by the Department.
PRM-55 | Program Management and Operations | The Converged E&E System must allow users with the specified role to retrieve case records based on search criteria.
PRM-56 | Program Management and Operations | The Converged E&E System must provide reporting functionality that includes, at a minimum, the following: • Case data • Member data • Employer data • Business partner data • State and federal data • Additional data as determined by the Department
PRM-57 | Program Management and Operations | The Converged E&E System must allow users with the specified role to retrieve notices based on search criteria.
PRM-58 | Program Management and Operations | The Converged E&E System must create reports within time frames required by Department, State, and federal guidelines.
PRM-59 | Program Management and Operations | The Converged E&E System must create a system job to generate reports based on Department-defined criteria.
PRM-60 | Program Management and Operations | The Converged E&E System must comply with all usability, accessibility, and compliance standards set forth in the OHIP Solution Delivery Domain Document, Usability and Accessibility Standard.
PRM-61 | Program Management and Operations | The Converged E&E System must enforce the use of Secure Sockets Layer (SSL) and Transport Layer Security (TLS) encryption (Hypertext Transfer Protocol Secure [HTTPS]) across all pages and subdomains to support secure data transmission. Refer to the OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard for additional details.
PRM-62 | Program Management and Operations | The Converged E&E system must generate a notice of termination to the individual.
PRM-63 | Program Management and Operations | The Converged E&E System must generate a notice of termination to the Issuer.
PRM-64 | Program Management and Operations | The Converged E&E System must generate and maintain electronic copies of IRS Form 1095-A for applicable consumers in accordance with federal rules, including generation of new, voided, or corrected forms for each of the past seven (7) years.
PRM-65 | Program Management and Operations | The Converged E&E System must store electronic copies of IRS Form 1095-A in consumer accounts.
PRM-66 | Program Management and Operations | The Converged E&E System must provide a communication generation and management module that performs, at a minimum, the following: • Compliance with Department, State, and federal policies, rules, and regulations • Generation of the following: o Individual communications from Department-approved templates o SHOP marketplace communications from Department-approved templates o Communications designed for mailing • Delivery of the following: o Communications in accordance with the timing required by applicable law o Communications using the recipient's preferred communication channel o Communications using the recipient's preferred language • Ability for the Department to manage, control, and configure communication triggers and rules • Construction of communications from Department-approved templates • Ability to tailor communication content • Storage of electronic copies of all communications in a consumer's account
PRM-67 | Program Management and Operations | The Converged E&E System must use communication suppression rules as determined by the Department.
PRM-68 | Program Management and Operations | The Converged E&E System must allow the generation of notices to individuals and employers based on events that include, at a minimum, the following: • Eligibility • Enrollment • Redeterminations • Disenrollment • Renewal • Termination • System-generated events • Additional events as determined by the Department
PRM-69 | Program Management and Operations | The Converged E&E System must post assessment fee invoices to appropriate Issuer accounts.
PRM-70 | Program Management and Operations | The Converged E&E System must generate invoice notices to deliver to Issuers that include, at a minimum, the following: • New invoice postings • Invoice payment reminders • Invoice past-due and enforcement alerts
PRM-71 | Program Management and Operations | The Converged E&E System must manage communications and correspondence in multiple languages as required by applicable State and federal laws.
PRM-72 | Program Management and Operations | The Converged E&E System must deliver employer group applications and associated documentation to the Issuer for processing.

## SDLC
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
SDLC-01 | The Contractor must comply with the Hybrid Iterative Development SDLC methodology outlined in the OHIP Solution Delivery Domain Document, SDLC Standard, to design, develop, and implement the Converged E&E System, unless otherwise approved by the Department.
SDLC-02 | The Contractor must adhere to the following approaches throughout the SDLC to support health equity: • Understand New York State’s statutory definition of health equity, as formalized in New York Public Health Law and the expanded definition in the NYS Health Equity Plan1 • Support the Department’s health equity goals as they relate to the Converged E&E System, the AMS, and other health system modernization efforts • Incorporate health equity principles, consumer centricity, and human-centered design (HCD) into the design, development, and implementation of the Converged E&E System and the AMS • Consider factors that may impact an end user’s interaction and experience with the Converged E&E System and the AMS, including social determinants of health, language, literacy, disability, and location • Support equitable user experiences and efforts to reduce inequities, disproportionate effects, and barriers to access
SDLC-03 | The Contractor must adopt the Department’s preferred collaboration model for all SDLC activities and deliverables. To support collaboration, the Contractor must publish a cycle-level Collaboration Plan with defined office hours and review windows that include, at a minimum, the following artifacts: • End-of-iteration demos, including recorded walkthroughs for stakeholders unable to attend • Concise pre-reads or decision packages distributed at least two (2) business days before sessions
SDLC-04 | The Contractor must establish standards, consistent with those defined by the Department, for use cases, acceptance criteria, and nonfunctional requirements, and must maintain E2E traceability from business objectives through requirements, design elements, development tasks, test cases, test results, and Releases.
SDLC-05 | The Contractor must initiate Converged E&E System implementation and engage with the Department on Phase 1: Scope Prioritization for the first Release within one (1) month of the Contract start.
SDLC-06 | The Contractor must adopt, update, and maintain the System Architecture Design Document (SADD). The Contractor must update the SADD during each Release as changes are made to any infrastructure architecture, application, application framework, shared application services, or software specifications.
SDLC-07 | The Contractor must develop and implement a Business Analysis QA (BAQA) Plan as a part of the Requirements Management Plan. The BAQA Plan must describe the standards, templates, tools, review cadences, metrics, and escalation paths that govern BAQA activities. The Contractor must apply the BAQA Plan during Scope Prioritization and maintained throughout all phases of the SDLC.
SDLC-08 | The Contractor must maintain and update the Release Management Plan to describe the approach and procedures for managing and tracking Converged E&E System Releases, deploying Releases to system environments, and obtaining Department approval for production Deployments and Releases. The Release Management Plan must include, at a minimum, descriptions of the following: • Release Governance • Key Roles and Responsibilities • Scope Prioritization • Release Planning • Building Releases • Testing Releases • Preparing Releases for Deployment • Deploying Releases, including Rollback Process • Validating Releases • Closing Releases
SDLC-09 | The Contractor must propose a Release Schedule as a part of the Release Plan developed within the parameters set forth in this RFP and as elaborated in the OHIP Solution Delivery Domain Document, SDLC Standard. The Release Schedule must contain, at a minimum, the following components: • Holistic view of the Release Schedule, including timelines, Deployment dates, key milestones, dependencies, and pre-Deployment activities • Schedule review and approval process • Approved Deployment dates • CR management • Escalation procedures The Release Schedule must align with the Department’s prioritization of functionality to support the programs and the milestones detailed in Section 5.2.5.1 – Implementation Approach.
SDLC-10 | The Contractor must provide the following Release-specific deliverables for Department review and approval: • Product Roadmap • Release Plan • Planned versus Actual Progress DDI Report • Weekly DDI Status Report • Business Rules Documentation, as detailed in the OHIP Solution Delivery Domain Document, Policy and Business Rules Standard
SDLC-11 | The Contractor must provide an Iteration Status Report as a part of the DDI Weekly Status Report that includes the Iteration Backlog status and RAID log. Refer to Section 5.2.2 – Project Management for additional details.
SDLC-12 | The Contractor must provide reports and matrices used to measure team productivity, such as throughput, cycle time, work in progress (WIP), and team satisfaction.
SDLC-13 | The Contractor must develop a Release Backlog for each Release and obtain Department approval of the goals for the subsequent Release prior to its commencement.
SDLC-14 | The Contractor must identify all new integration points and interfaces required to support the implementation of functionality defined in the RFP and in accordance with the Release Schedule.
SDLC-15 | The Contractor must consider diverse and underserved public health populations and jurisdictions throughout the design and development process to promote inclusivity and address the needs of all users.
SDLC-16 | The Contractor must maintain and update the Requirements Management Plan. The plan must include, at a minimum, the following: • Purpose and objectives for managing Contract, system functional, system nonfunctional, and contractual requirements • Requirements management approach, including documenting requirements, baselining, soliciting stakeholder feedback, tracing requirements throughout the SDLC, and performing updates and maintenance • Department-approved tools used to support requirements management • Types of requirements artifacts to be produced, such as functional specifications and use cases • Requirements writing style guide and quality • Approach to requirements traceability, including versioning and management reporting
SDLC-17 | The Contractor must document all requirements in a timely, clear, and accurate manner to support the M&O and DDI teams. This applies to new, modified, updated, and deleted requirements. The Contractor must make requirements accessible to appropriate stakeholders and maintain a clear history of changes for each requirement.
SDLC-18 | The Contractor must document, maintain, and update requirements using the Department’s preferred requirements management tool, as identified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard. All functional and nonfunctional requirements must be traceable to related designs, artifacts, development tasks, test cases, and test results.
SDLC-19 | The Contractor must maintain and update requirements, as needed, to comply with applicable State and federal laws and regulations, as well as Department policies.
SDLC-20 | The Contractor must implement and maintain control policies and procedures that limit the ability to view, edit, or approve requirements documentation to authorized staff only.
SDLC-21 | The Contractor must implement peer reviews of requirements and scenarios prior to RTM commitment.
SDLC-22 | The Contractor must track and report RTM readiness rate, requirements defects that escape to delivery, rework resulting from requirement gaps, peer review findings, and corrective actions. The Contractor must provide regular BAQA status updates, including audit results and continuous improvement activities, to project leadership and make them available to the Department upon request.
SDLC-23 | The Contractor must conduct periodic audits of requirements quality and traceability. The Contractor must capture lessons learned from these audits and update standards, checklists, and templates accordingly. The findings of this audit must be reviewed with the Department.
SDLC-24 | The Contractor must attend refinement sessions with prepared Ready for Refinement use case shells prepared in the Department’s preferred requirements management tool. Refer to the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard for additional information.
SDLC-25 | The Contractor must obtain agreement among the Product Owner designated by the Department, the Functional Manager, and the Contractor’s development team to lock use cases.
SDLC-26 | The Contractor must mark use cases as “Ready for Development” so they may be selected for implementation as part of current or future iterations.
SDLC-27 | The Contractor must apply appropriate reality-to-requirement guardrails including, at a minimum, the following: • RTM Readiness – Apply entry criteria so use cases enter iterations with testable Behavior-Driven Development (BDD) acceptance criteria, relevant policy and process references, identified dependencies, and at least two (2) iterations of entry-ready maintained in the work queue by Scope Prioritization exit • Early Validation Cadence – Demonstrate progress iteratively within each phase using working software or prototypes paired with usability testing involving real users and avoid long, sequential design and build phases within iterations • Environment and Test Data Readiness – Provide and maintain plans for SIT and UAT environment availability and representative test data, with functionality not considered complete without validation in appropriate environments • Nonfunctional Requirements (NFR) Shift-Left – Integrate NFRs into the RTM as explicit use cases with acceptance criteria and execute incremental security, performance, and accessibility testing throughout iterations (refer to Section 5.2.7 – System Testing for additional details) • Dependency Management – Maintain a cross-Release and interface dependency register, define no-start rules for blocked items, report dependency resolution time frames, and make blocked work visible • Transparent Metrics – Report, at a minimum, decision turnaround times, stakeholder participation (live and asynchronous), entry and exit criteria compliance, blocked work rates, dependency resolution times, requirements defect escape rates, and NFR adherence and incorporate variance analysis, corrective actions, and these metrics into the KPI and Objectives and Key Results (OKR) frameworks (refer to Section 5.5.1 – Key Performance Indicators and Objectives and Key Results for additional details)
SDLC-28 | The Contractor must apply shift-left security during design, as described in the OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard, including threat modeling activities. During development, the Contractor must apply practices such as Static Application Security Testing (SAST) and Static Code Analysis (SCA). Other applicable approaches include the following: • Using Infrastructure as Code (IaC) with version-controlled code to provision infrastructure • Making environments repeatable, auditable, and CI/CD-automated • Performing automated container scanning of images and, where applicable, running containers to identify security and configuration issues before and after Releases • Implementing secret detection
SDLC-29 | The Contractor must validate performance, reliability, and capacity early and continuously using budgets, SLAs, and automated checks, as described in the OHIP Solution Delivery Domain Document, SDLC Standard.
SDLC-30 | The Contractor must build in usability and accessibility from project initiation using WCAG 2.2 checks, assistive technology tests, and design reviews, as described in the OHIP Solution Delivery Domain Document, Usability and Accessibility Standard.
SDLC-31 | The Contractor must develop new business rules and maintain existing business rules, in accordance with the OHIP Solution Delivery Domain Document, Policy and Business Rules Standards, using the Department’s BRE.
SDLC-32 | The Contractor must document business rules in the Business Rules Documentation, maintain traceability to originating use cases and test cases, and manage versioning and change control. The Contractor must develop, govern, and maintain business rules in accordance with the OHIP Solution Delivery Domain Document, Policy and Business Rules Standards and Department guidance.
SDLC-33 | The Contractor must adhere to the following business rules governance goals: • One Hundred Percent (100%) Policy Coverage – Automate one hundred percent (100%) of policies using the Department’s preferred tool • One Hundred Percent (100%) Policy Accuracy – Manage policy implementation to reasonably support one hundred percent (100%) accuracy • Changes Implemented Prior to Policy Start Date – Implement policy change control prior to the policy start or effective date • Satisfaction of Federal Policy Implementation Audits – Comply with federal requirements for policy and rule readability, accessibility, encapsulation, and isolation • What-If Analysis on Client Population – Enable analysis of the impact of policy changes on the existing system populations, including individuals and households
SDLC-34 | The Contractor must follow the Department’s formal approval process for all environment promotions and Deployments (DEV to SIT to UAT to Production). A minimum of two (2) business days’ notice is required prior to promotion. Requests submitted with less than two (2) business days’ notice must follow the conditional approval path and include documented risk and rollback plans.
SDLC-35 | The Contractor must automate CI/CD to execute fast checks on every commit and broader test suites nightly, including integration and performance smoke testing.
SDLC-36 | The Contractor must enforce promotion gates using the gate criteria described in Section 5.2.5.3 – Solution Development Life Cycle in addition to any other mutually agreed-upon thresholds.
SDLC-37 | The Contractor must communicate with end users during DDI of new functionality to support the following: • Understand E2E user experiences interacting with the Converged E&E System and the AMS • Create user roles, customer journeys, service blueprints, problem-space definitions, affinity maps, and flow diagrams to align digital services with offline experiences • Leverage known information to create a seamless, configured user experience and promote equitable access to the Converged E&E System and the AMS • Collaborate with the Department and other identified stakeholders to define and refine each Release’s product vision and support the development and maintenance of product roadmaps and backlogs • Establish feedback loops and metrics for product assessment
SDLC-38 | The Contractor must define testable acceptance criteria using Test-Driven Development (TDD), BDD, and Specification by Example, as described in the OHIP Solution Delivery Domain Document, SDLC Standard.
SDLC-39 | The Contractor must enforce pull-request quality gates, as described in the OHIP Solution Delivery Domain Document, Test Management Standard that include the following: • Structured peer reviews • Unit tests validating individual codebase components • SCA • SAST • Secret scanning for automated detection of sensitive credentials in testing assets • API contract testing to validate interface security, as described in the OHIP Secure API Development Baseline
SDLC-40 | The Contractor must measure and enforce gates based on meaningful quality signals, as described in the OHIP Solution Delivery Domain Document, Test Management Standard. These signals include the following: • Mutation score (percentage of code mutations killed by tests) • Static analysis thresholds • Vulnerability SLAs • Defect-escape rates
Footnotes:
1 | https://www.health.ny.gov/community/health_equity/docs/health_equity_plan.pdf

## DC&M
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
DCM-01 | The Contractor must work with the Department to determine whether existing data conversion and migration (DC&M) approaches can be applied to the DC&M effort for the Converged E&E System.
DCM-02 | The Contractor must convert and migrate ten (10) years of NYSOH System data, measured by eligibility determinations and supporting data, into the Converged E&E System.
DCM-03 | The Contractor must conduct a DC&M Gap Analysis to establish the scope, scale, structure, and complexity of DC&M activities (refer to Section 5.8 – Deliverables for additional details). The Department must approve the DC&M Gap Analysis before any DC&M activities begin.
DCM-04 | The Contractor must develop a DC&M Plan that outlines the strategy, steps, and considerations for transferring data from one system to another.
DCM-05 | The Contractor must work with the Department to establish a DC&M Task Force as defined in Section 5.2.5.4.C – Data Conversion and Migration Governance. The DC&M Plan must define the parameters for this group and include, at a minimum, group composition, meeting cadence, decision rights, escalation paths, a schedule for partner checkpoints, and a plan for alignment with functional/application teams.
DCM-06 | The Contractor must develop and deliver a Data Migration Inventory Report that provides a complete, auditable catalog of all data items in scope and out of scope for migration.
DCM-07 | The Contractor must develop a Data Mapping and Transformation Specification Document that provides a timely and accurate representation of data transformation. This document must include the methodology to reconcile differences between how the NYSOH System and the MECM System handle historical changes to records and define uniqueness (refer to the Examples of Differences in Data Architectures subsection in Section 5.2.5.4.A – Background).
DCM-08 | The Contractor must develop a Data Quality Assessment Report that evaluates, documents, and communicates data health against defined quality standards so risks are identified and addressed before data is used for operations, analytics, reporting, or transformation initiatives. The Data Quality Assessment Report must include, at a minimum, the following: • Data quality scorecards for each data domain that illustrate pre-cleansing baseline, post-cleansing improvements, and trends across conversion iterations • Heatmaps illustrating data quality by domain • Severity-ranked list of all identified data quality issues with proposed remediation assignments
DCM-09 | If the Data Quality Assessment Report identifies any data domain below Department-defined quality thresholds, the Contractor must develop and deliver a CAP for Department approval.
DCM-10 | The Contractor must profile one hundred percent (100%) of in-scope source data at the attribute level before conversion design begins.
DCM-11 | Based on profiling results, the Contractor must develop and execute a Data Cleansing Strategy that addresses how data quality issues identified in the Data Quality Assessment Report will be remediated before conversion begins.
DCM-12 | The Contractor must identify and reconcile all reference data domains between source and target systems before conversion begins.
DCM-13 | The Contractor must define the approach for creating golden records, including survivorship rules and source precedence logic, for all applicable domains, including provider master data, member master data, and organizational hierarchies.
DCM-14 | The Contractor must produce comprehensive source-to-target mapping documentation before conversion begins. This documentation must provide one hundred percent (100%) coverage for all target data attributes and include, at the column level, the following: • Complete data lineage, including source, transformation version, and target • Business rules, transformation logic, and survivorship rules • Definitions for handling nulls, defaults, truncation, time zone conversions, precision, and character encoding
DCM-15 | The Contractor must expand the data model to accommodate any net-new data elements in the NYSOH System that do not have a corresponding structure in the MECM System data model.
DCM-16 | The Contractor must develop and document data models for the Converged E&E System, including a CDM, LDM, and PDM.
DCM-17 | The Contractor must define clear, measurable, and testable acceptance criteria that are approved by Department before conversion begins.
DCM-18 | The Contractor must develop scripts, code, and configure tools required for Extract, Transform, Load (ETL).
DCM-19 | The Contractor must implement, at minimum, the reconciliation controls defined in the OHIP Data and Information Management Domain Document, Data Conversion Standard at every stage of the conversion process.
DCM-20 | The Contractor must develop reconciliation reports that provide source-to-target reconciliation evidence for each conversion lot, including record counts, control totals, variance analysis, root causes, and Data Owner signoffs.
DCM-21 | The Contractor must resolve all conversion exceptions using processes that include, at a minimum, the following: • Capture of exceptions in real time during conversion execution, including root cause codes, record keys, timestamps, and reproducible steps • Routing of exceptions to a centralized repository accessible to Contractor and Department teams • Classification of exceptions by severity and assignment to appropriate resolvers • Reprocessing of resolved exceptions through the conversion pipeline with validation against acceptance criteria • Escalation of unresolved exceptions within defined SLA windows in accordance with the Department’s incident management process
DCM-22 | The Contractor must coordinate with the EDW vendor to carry out any necessary bootstrapping processes that include, at a minimum, the following: • Data contracts and schema/versioning management • ID and code crosswalks • Feed delivery and Cutover schedules • Joint data quality and reconciliation activities
DCM-23 | The Contractor must perform a minimum of three (3) successful E2E dry runs in a Production-like environment before Cutover.
DCM-24 | The Contractor must meet or exceed all dry run exit criteria as defined in the OHIP Data and Information Management Domain Document, Data Conversion Standard.
DCM-25 | The Contractor must maintain a data validation checklist covering all acceptance criteria. Records that fail validation must be routed to an error queue or exception report for remediation. Only data that passes all validation checks may be committed to the Production database or forwarded to the Converged E&E System.
DCM-26 | The Contractor must validate converted data across all downstream endpoints and use cases, including, at a minimum, the following: • Reports and data deliveries that consume converted data • Application screens and fields that display converted data • Interfaces and data exchanges that transmit converted data to downstream systems • Federal reporting submissions
DCM-27 | The Contractor must design and implement a tagging or flagging mechanism that distinguishes converted records from records created natively within the Converged E&E System. The proposed approach must be documented in the Data Mapping and Transformation Specification Document and approved by the Department prior to the first dry run. The tag or flag must be a persistent attribute in the Converged E&E System.
DCM-28 | The Contractor must confirm the following conditions are met before Production Cutover: • Data quality, reconciliation, performance, and security thresholds met or exceeded • Successful completion of all test cases or Department-approved remediation plan • No severity level one (1) defects open and all exceptions within agreed tolerances documented • Explicit Department go/no-go authorization
DCM-29 | The Contractor must develop and test a rollback plan before executing Cutover activities. The rollback plan must include rollback triggers, pre-conversion backup, post-conversion backup, tested restore procedures, bridge reactivation, and backfill and catch-up processes.
DCM-30 | The Contractor must develop data quality monitoring rules that include dashboards, alerts, and automated checks to monitor data health and process stability in production. Automated monitoring for critical domains must run, at minimum, daily. Alerts must be configured for quality threshold breaches, job failures, and performance degradation.
DCM-31 | The Contractor must correct all data errors introduced during conversion. Backfills must be performed with no or minimal downtime, as agreed, at no additional cost during the warranty period.
DCM-32 | The Contractor must purge all intermediate files and temporary staging areas containing sensitive data within twenty-four (24) hours of successful data migration unless subject to a legal hold. The Contractor must provide formal evidence of the purge, such as a certificate of destruction or audit logs, to the Department within forty-eight (48) hours of the purge event.
DCM-33 | The Contractor must retain ten (10) years of data in the Converged E&E System, measured by eligibility determinations and supporting data. After the ten (10)-year retention period, the data must be archived.
DCM-34 | The Contractor must archive all NYSOH System data that was not converted and migrated into the Converged E&E System.
DCM-35 | The Contractor must archive data in the AWS Glacier archive, which will store all archived data, including FTI. The Contractor is responsible for maintaining this archive.
DCM-36 | The Contractor must define all retention, archiving, and disposition requirements in the DC&M Plan and the DMP.
DCM-37 | The Contractor must implement detailed audit logging for the conversion process. At minimum, audit logs must include, at a minimum, the following: • Operator identity • Start and end timestamps • Affected records, including counts, keys, and scope • Applied transformation rules and versions • Errors, exceptions, and manual adjustments
DCM-38 | The Contractor must provide the following reports to Department: • Data Quality Reports – Conversion of Data Quality Assessment Reports prior to user testing and ongoing after Go-Live • Issues Log – Log of all records failing data validation, including root causes and resolution status • Reconciliation Reports – Source-to-target reconciliation evidence for each conversion cohort, including record counts, control totals, variance analysis, and approvals • Final Conversion Report – Summary of the entire conversion project, including outcomes, lessons learned, data quality achieved, and final approvals • Post-Production Compliance Dashboard – Dashboard showing data exchange service levels, timeliness, and error rates, including visual indicators when interfaces are down or data quality falls below thresholds
DCM-39 | The Contractor must provide and demonstrate all conversion activities, data, environments, artifacts, and related materials at the Department’s request.
DCM-40 | The Contractor must provide knowledge transfer and documentation on conversion tools to the Department.
DCM-41 | The Contractor must maintain documentation of conversion processes, mapping specifications, validation results, and security measures. Documentation and audit records must demonstrate compliance with standards and policies and support Certification Reviews (CRs).

## Training
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
TRN-01 | The Contractor’s training staff must participate in design and requirements definition activities to support development of accurate and effective training materials and to eliminate gaps in the training curriculum.
TRN-02 | The Contractor must coordinate with other parties responsible for training, including, at a minimum, the Customer Service Center vendor and external training vendors, to ensure their training staff also participate in design and requirements definition activities.
TRN-03 | The Contractor must develop the training approach and materials for specific target audiences, including, at a minimum, Contractor staff, Department staff, Customer Service Center staff, Frontline Workers, and Assistors. The training approach, topics, and materials must be appropriate to the needs of each audience.
TRN-04 | The Contractor must support other parties responsible for training, including, at a minimum, the Customer Service Center vendor and external training vendors, through the following: • Serve as the point of contact (POC) for training-related questions regarding the Converged E&E System and the AMS • Provide access to the system training environments to support development of training materials and training delivery • Host regularly scheduled meetings to support improvement and customization of training materials • Facilitate collaborative solutioning sessions to identify common scenarios and develop appropriate resolution-focused training • Conducting train-the-trainer (T3) sessions
TRN-05 | The Contractor must develop and maintain the training curriculum for Department staff. Department staff training must cover, at a minimum, the following: • End-User Training o Converged E&E System and AMS functionality, including search methods, accessing user help, and error handling o New or modified functionality introduced during the Contract term • Stakeholders/Project Team Training o BC/DR, including staged exercises o Tools used within or in support of the Converged E&E System and AMS project, such as tools for Release planning, defect and issue management, and data analysis (e.g., Jira, Erwin Data Modeler, Microsoft Project, Tableau)
TRN-06 | The Contractor must create training materials for each audience identified in Section 5.2.5.5.A – Training Audiences, including, at a minimum, the following: • Facilitator Guides – Detailed scripts for instructors delivering in-person or virtual training, including talking points, activity instructions, timing cues, and responses to common questions • Participant Guides and Workbooks – Manual for learners to follow during training sessions, including key concepts, space for notes, and hands-on exercises • Presentation Slides – Visual materials used during instructor-led training (ILT) to present information, display screenshots, and guide training sessions • Job Aids – Concise reference materials providing step-by-step instructions for completing common tasks • Web-Based Training (WBT) Modules – Self-paced e-learning courses supporting independent learning, including knowledge checks as appropriate • Instructional Videos – Short, pre-recorded videos (e.g., 2-5 minutes) demonstrating task execution or explaining key concepts • Course Outlines and Storyboards – Planning artifacts defining learning objectives, content flow, and interactive elements prior to course development • Evaluation Forms – Surveys and assessments used to measure training effectiveness and user comprehension
TRN-07 | The Contractor must review and update training materials in collaboration with Department staff using an ongoing, iterative process. All training materials must be updated, at a minimum, prior to each Release.
TRN-08 | The Contractor must utilize the Department’s central document repository to store all training materials.
TRN-09 | The Contractor must track and maintain the history of changes and approvals for all training materials.
TRN-10 | The Contractor must provide annual training to Contractor staff and Department-identified stakeholders on execution of the BC/DR Plan.
TRN-11 | The Contractor must document any instances in BC/DR exercises where trained personnel were unable to complete required recovery procedures, adjust training materials and plans to address identified deficiencies, and submit updated materials to the Department for approval.
TRN-12 | The Contractor must maintain the existing training environments used to support the MECM System and the AMS. Training environments must operate independently to prevent maintenance activities from affecting other environments.
TRN-13 | The Contractor must maintain training environments at a version equal to or no more than one (1) Release behind the Production system, unless otherwise approved by the Department.
TRN-14 | The Contractor must configure the training environment to mirror Production security roles and provide role-based access controls (RBAC) to allow users to practice skills introduced in training courses.
TRN-15 | The Contractor must make training environments accessible via the internet in accordance with approved roles and responsibilities.
TRN-16 | The Contractor must host and provide technical support for the training environments.
TRN-17 | The Contractor must manage and support batch schedules within the training environments and must execute Department-requested training batch scheduler run cycles within two (2) hours.
TRN-18 | The Contractor must develop and maintain user manuals providing detailed instructions for use of the Converged E&E System and the AMS, including functionality introduced in new Releases.
TRN-19 | The Contractor must maintain user manuals in accordance with ISO/IEC/IEEE 26512:2018, System and software engineering – Requirements for acquirers and suppliers of information for users, Section 8, which specifies requirements for software user documentation.
TRN-20 | The Contractor must facilitate user manual walkthrough session, including system demonstrations as needed, to allow the Department and third-party training vendors to ask questions and provide feedback.
TRN-21 | The Contractor must collaborate with the Department to develop and maintain a Training Plan that documents activities required to train all Department-identified personnel on use and operation of the Converged E&E System and the AMS. Refer to Section 5.8 – Deliverables for additional details.
TRN-22 | The Contractor must conduct an annual training needs assessment for all stakeholder groups and recommend training improvements aligned to Department-defined user roles.
TRN-23 | The Contractor must develop and maintain training metrics and recommend updates to training based on collected feedback and performance data. Training metrics must be agreed upon by the Department and the Contractor and incorporated into the KPI and OKR frameworks. Refer to Section 5.5.1 – Key Performance Indicators and Objectives and Key Results for additional details.

## Deployment
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
DEP-01 | The Contractor must develop and implement a comprehensive Deployment Plan and strategy for all Releases related to the migration of the MAGI Medicaid, CHPlus, BHP, and QHP Populations from the NYSOH System to the Converged E&E System. This plan must include, at a minimum, the following: • Resource Availability Plan • Go-Live communications • Deployment task list • Deployment schedule with start and end times for each Deployment task • Issue Management Plan • Blackout and system unavailability period determination • Rollback Plan
DEP-02 | The Contractor must create a Deployment strategy that serves as the guiding principle for meeting specific objectives during the migration process.
DEP-03 | The Contractor must verify full integration of all Department requirements into the Converged E&E System.
DEP-04 | The Contractor must complete all required documentation for the Converged E&E System, including technical documentation, functional documentation, and user manuals.
DEP-05 | The Contractor must resolve all critical and high severity defects prior to implementation and must document defect resolution activities.
DEP-06 | The Contractor must conduct a minimum of three (3) Deployment Procedure Reviews for each Deployment Release of the Converged E&E System, unless otherwise directed by the Department.
DEP-07 | The Contractor must provide guidance to the project team, as required, during any blackout or system unavailability period.
DEP-08 | The Contractor must provide a Go/No-Go Document for Department approval confirming that all applicable readiness criteria have been met prior to each Deployment. The document must include, at a minimum, the following: • Roles and responsibilities of Contractor and Department staff during the Deployment and transition period • Confirmation that DC testing and migration testing are complete and verification that procedures are in place to correctly load legacy data • Hypercare procedures for incident and defect management • Acceptance criteria for successful Deployment completion • Confirmation of resolution of all critical and high-severity defects identified in prior phases and a Department-approved mitigation plan for medium-severity defects • Acceptance criteria for successful cutover from legacy systems, including the NYSOH System, to the Converged E&E System • Final strategy and schedule for implementing the MAGI Medicaid, CHPlus, BHP, and QHP Populations from the NYSOH System to the Converged E&E System
DEP-09 | The Contractor must conduct a User Engagement Survey after each Release to assess the satisfaction and engagement level of users of the Converged E&E System. The survey must address, at a minimum, ease of use, responsiveness, analytics support, and reliability.

## Hypercare
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
HYP-01 | The Contractor must provide Hypercare and post-Deployment support services for each Release. The Contractor and the Department must mutually agree on the duration of each Hypercare phase.
HYP-02 | The Contractor must plan for and provide onsite Hypercare services at designated Department locations for each Deployment. With Department approval, a portion of staff performing Hypercare services may perform such activities remotely.
HYP-03 | The Contractor must develop and submit to the Department, for review and approval, a comprehensive Hypercare Plan that describes post-Cutover activities performed during the Hypercare phase. At a minimum, the Hypercare Plan must include the following: • Processes for addressing, documenting, tracking, reporting, and resolving defects identified during testing or uncovered during normal operations and managed as incidents, including categorization based on business criticality and resolution time frames aligned to criticality levels • Description of Hypercare processes, management of Hypercare functions, and Contractor responsibilities • Process for reporting and resolving all severity level one (1) and level two (2) incidents prior to the end of the Hypercare phase • Process to address remaining severity level three (3) and level four (4) incidents that may remain outstanding at the end of the Hypercare phase • Strategy and identification of staff who will assist the Department with modifications during the Hypercare phase • Strategy and identification of staff responsible for proactively gathering user feedback from users during the Hypercare phase
HYP-04 | The Contractor must provide the Department with a Production Defect Remediation Plan that describes the approach for addressing and correcting identified defects following Go-Live.
HYP-05 | The Contractor must track and manage defects that arise immediately following Go-Live. The Contractor must log defects for resolution using the Department’s ITSM tool, as specified in the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard.
HYP-06 | The Contractor must make available Department-approved staff who provided configuration and customization services during implementation throughout the Hypercare phase to resolve incidents and defects and provide knowledge transfer to Department resources.
HYP-07 | The Contractor must assist the Department in resolving all critical and high-severity defects identified during Deployment and Hypercare prior to exiting the Hypercare phase and prior to any subsequent Deployments.
HYP-08 | The Contractor must assist the Department in developing a schedule to resolve all remaining medium- and low-severity defects that remain outstanding at the end of the Hypercare phase.
HYP-09 | The Contractor must perform rollback activities when delivered system functionality does not operate in accordance with established requirements and SLAs.

## System Testing
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
TEST-01 | The Contractor must provide a Test Management Plan (TMP) that includes, at a minimum, the following: • Test Objectives and Scope – Defines the objectives and scope of the testing phase, including which parts of the Converged E&E System must be tested • Roles and Responsibilities – Defines, for each Release, roles and responsibilities of Contractor and Department staff, detailing who is responsible for various aspects of the testing process • Test Case and Test Script Development – Describes, at a minimum, the following: o Process for developing test scenarios, test cases, and test scripts o Preparatory steps for each test type o Timelines for developing test cases and test scripts and preparing test data o Process for Department review and approval of test cases to confirm compliance with predefined standards prior to execution • Entry and Exit Criteria – Defines entry and exit criteria to confirm that tests are executed only when all predefined criteria have been met and are considered complete only when all required outcomes are achieved and verified, including coordination with the Department for each test type • Testing Tools and Automation – Lists testing tools, such as Jira or other tools approved by the Department, and automation frameworks to be used, if applicable, including schedules for tool setup, configuration, and validation to confirm readiness prior to testing and updates to the Department-approved tracking tool • Test Data Requirements – Defines test data requirements and Contractor responsibilities, unless otherwise agreed by the Department, and includes, at a minimum, the following: o Test data creation and data masking efforts needed to protect sensitive information o Contractor process for creating and refreshing test data o Use of clean and consistent test data that supports testing procedures • Metrics and Reporting – Defines how testing progress and outcomes must be measured, including the format, content, and frequency of test status reports and metrics such as pass and fail rates, defect density, and coverage levels • Communication Plan – Outlines how the Contractor must report progress to the Department, schedule regular status meetings, and establish mechanisms for issue escalation to support clear and ongoing communication • Content for All Test Types – Outlines the overall management of each test type and describes how each test type is designed to fully test various functions and features of the Converged E&E System, including traceability of each requirement to one or more test cases The Contractor must update the TMP and its components as the project evolves. The Department will review and approve all changes to the approved TMP.
TEST-02 | The Contractor must develop and submit a comprehensive Test Schedule to the Department for review and approval. The Contractor must develop this schedule in coordination with the availability of necessary Department resources. The Test Schedule must encompass detailed elements to facilitate planning and execution of testing activities, including, at a minimum, the following: • Scope –Identifies which parts of the system, functionalities, and features will undergo testing for each scheduled test type and provides an organized timeline outlining each phase of the testing process, including key milestones and deliverables • Resources, Roles, and Responsibilities – Documents resource assignments for all personnel involved in testing, including Contractor, Department, and other MES vendor teams, as applicable, to support resource availability and prevent scheduling conflicts • Test Environments – Specifies test environment setup activities and timelines to confirm environments are ready prior to testing • Testing Tools and Automation Frameworks – Lists testing tools and automation frameworks and documents schedules for tool setup, configuration, and validation • Test Data Requirements – Provides timelines for developing test cases and test scripts and preparing test data, including timelines supporting Department review and approval of test cases prior to execution • Dependencies and Constraints – Identifies schedule dependencies and constraints, including reliance on other projects, departments, or external entities, and acknowledges risks that could impact the Test Schedule • Review and Approval Cycles – Establishes timelines for interim and final Department review cycles, including time buffers to accommodate feedback and necessary revisions • Communication Strategy – Outlines the frequency for reporting testing progress to the Department through regularly scheduled status meetings and identifies mechanisms for issue escalation and the standard cadence for Contractor-submitted test status reports
TEST-03 | The Contractor must use time travel testing to simulate past, future, or fixed dates and times across all relevant test types.
TEST-04 | The Contractor must provide documentation that defines the content of all customized test cases, test scenarios, and test scripts that the Contractor must execute for testing (e.g., unit testing, SIT, DC and migration).
TEST-05 | The Contractor must provide unit testing results demonstrating that the Converged E&E System and the AMS are operating in compliance with requirements and design specifications. The Contractor must provide documentation that includes a summary of results and identified defects, including remediation plans for open items.
TEST-06 | The Contractor must provide SIT results demonstrating that the Converged E&E System and the AMS are operating in compliance with requirements and design specifications. The Contractor must provide documentation that includes test results, identified defects and their priority and severity, and defects that remain open following SIT, including remediation plans for open items.
TEST-07 | The Contractor must perform Trading Partner Testing (TPT) to validate connectivity and confirm that electronic data is accurately, securely, and seamlessly exchanged between the Converged E&E System, the AMS, and trading partners.
TEST-08 | The Contractor must coordinate TPT planning, including early notification to trading partners at least four (4) weeks prior to the start of TPT. Planning must also establish testing volumes, request frequency, and the volume of test data created by trading partners.
TEST-09 | The Contractor must provide the Department’s testing team with high-level testing scripts to support development of early system feature prototypes.
TEST-10 | The Contractor must support the Department’s solution exploration testing team in creating interface responses in a user-friendly and timely manner.
TEST-11 | The Contractor must provide solution exploration testing results demonstrating that the Converged E&E System and the AMS are operating in compliance with requirements and design specifications. The Contractor must provide documentation that includes test results, identified defects and their priority and severity, and defects that remain open following solution exploration testing, including remediation plans for open items.
TEST-12 | The Contractor must provide DC and migration test results demonstrating that all records have been converted as agreed upon and documented in the approved Data Mapping Specification document. Refer to Section 5.8 – Deliverables for additional details.
TEST-13 | The Contractor must provide E2E testing results demonstrating that the Converged E&E System and the AMS function as complete, integrated solutions from a user’s initiating action through the final outcome.
TEST-14 | The Contractor must provide performance, stress, and load testing results within the Test Results Report demonstrating that the Converged E&E System and the AMS are operating in compliance with requirements, design specifications, and SLAs. The Contractor must provide documentation that includes results from performance, stress, and load testing. Refer to Section 5.8 – Deliverables for additional information on the Test Results Report.
TEST-15 | The Contractor must complete E2E testing prior to UAT, unless an alternative timeline is approved by the Department.
TEST-16 | The Contractor must collaborate with the Department to define UAT processes and procedures, including final acceptance criteria. These processes and procedures must incorporate accessibility best practices (e.g., 18F guidelines) and include internationalization and plain-language principles.
TEST-17 | The Contractor must provide documentation defining the content of all standard Converged E&E System and AMS test cases, test scenarios, and test scripts to be used by the Department for development of UAT cases, scenarios, and scripts.
TEST-18 | The Contractor must determine the length and schedule of the UAT phase during scope prioritization based on project scope and SDLC duration. The Department will hold the Contractor accountable for any defects promoted to UAT and the Production Environment without explicit Department authorization, in accordance with SLAs. The Contractor must resolve such defects at no additional cost to the Department. The code base promoted to UAT must be treated as a Production candidate with minimal functional defects so the Department can focus on validating business capabilities during UAT.
TEST-19 | The Contractor must coordinate with the Department to identify business user groups to participate in UAT, schedule UAT sessions, and obtain Department approval of UAT results prior to Deployment.
TEST-20 | The Contractor must perform regression testing of the entire system, in accordance with the TMP, to validate that no new defects are introduced into existing system functionality following each Release.
TEST-21 | At the conclusion of UAT, the Contractor must execute a Department-approved regression test suite, provide satisfactory regression testing results, and provide comprehensive regression testing documentation to demonstrate alignment with Deployment readiness requirements. The Contractor must submit regression test cases, test scenarios, test scripts, test results, and the defect log to the Department. All Critical and High defects identified during regression testing must be resolved prior to Deployment.
TEST-22 | The UAT process must align with the following: • CMS Acceptable Risk Controls for ACA, Medicaid, and Partner Entities (ARC-AMPE) • HIPAA • IRS Publication 1075 compliance requirements The UAT process must confirm that no production data containing Protected Health Information (PHI), Personally Identifiable Information (PII), or FTI is used until the Authority to Connect (ATC) from CMS and authorization from the IRS have been obtained. Refer to Section 5.7 – Security and Privacy for additional details.
TEST-23 | The Contractor must provide, including training, technical assistance, and issue resolution, for testers during UAT execution.
TEST-24 | Upon successful completion of UAT, the Contractor must submit a high-level overview of significant events and activities, the scope of the testing, details of issues identified during UAT, and a summary of defects, including priority and severity, to the Department for review and approval. This submission must be included in the Go/No-Go Document deliverable and constitutes the formal UAT approval reviewed by the Department during the Go/No-Go meeting.
TEST-25 | The Contractor must provide security and privacy testing results demonstrating that the Converged E&E System and the AMS are operating in compliance with requirements and design specifications. The Contractor must provide documentation that includes the testing scope, results, identified defects and their priority and severity, and defects that remain open following security and privacy testing. As necessary, Department staff will comply with nondisclosure requirements regarding detailed findings that may impact other Contractor clients. Refer to Section 5.2.4 – Maintenance and Operations and Section 5.7 – Security and Privacy for additional details.
TEST-26 | The Contractor must conduct DR testing on an annual basis. This testing must include both manual and automated procedures to validate comprehensive recovery of the Converged E&E System and the AMS and must account for the unique characteristics of a consumer-facing system that is available at all times, twenty-four (24) hours per day and three-hundred sixty-five (365) days per year. Additionally, DR testing must include tabletop exercises, partial or component testing, and full solution testing as defined in Section 5.2.7.3 – Test Types.
TEST-27 | The Contractor must provide DR testing results demonstrating that the Converged E&E System and the AMS are operating in compliance with requirements and design specifications. The Contractor must provide documentation that includes issues encountered during DR testing and the remediation actions completed as a result. Refer to Section 5.2.4 – Maintenance and Operations and Attachment F –SLAs for additional details specific to DR-related requirements.
TEST-28 | The Contractor must conduct usability and accessibility testing at key development milestones, including during testing phases 2, 3, and 4 as described in Section 5.2.7 – System Testing, ensuring that participants reflect the diversity of the user population.
TEST-29 | The Contractor must recruit representative users who mirror the actual or anticipated user base to participate in usability and accessibility testing, including users with varying technical abilities and language backgrounds, with Department approval of the final selection of end users.
TEST-30 | The Contractor must provision one (1) or more staging environments for representative users to conduct usability and accessibility testing.
TEST-31 | The Contractor must facilitate usability and accessibility testing sessions to gather both qualitative and quantitative feedback.
TEST-32 | The Contractor must collaborate with the Department to prioritize and implement usability and accessibility improvements based on usability and accessibility testing results.
TEST-33 | The Contractor must maintain a defect log throughout all testing phases, including severity, resolution status, retest results, and defects that remain open after each round of UAT prior to Deployment.
TEST-34 | The Contractor must provide documented evidence of defect resolution and successful retesting. No known Critical or High-severity defects may remain unresolved at the time of production Deployment.
TEST-35 | The Contractor must not bill the Department for remediation of defects that were present prior to Deployment and should have been identified and resolved during pre-Deployment testing phases. Defect remediation following Deployment will be considered part of the Contractor’s obligation to deliver a fully tested and functional system.
TEST-36 | The Contractor’s testing environments must model production operations when interacting with mock interface points within the system.
TEST-37 | The Contractor must design, implement, and continuously maintain a comprehensive automated test suite that exercises all relevant layers of the system, such as unit testing, SIT, E2E testing, performance testing, security testing, and regression testing. Only Department-approved tools and frameworks may be used to execute the test suite and generate human- and machine-readable test and coverage reports, which must be archived with each build for audit purposes.
TEST-38 | The Contractor must manage communication and coordination with other vendors and teams participating in testing activities to support proper planning and seamless execution of testing activities. This includes proactively engaging relevant parties to confirm availability and developing an integrated Testing Schedule. The Contractor must establish a communication framework, facilitate regular meetings, and provide status updates to support alignment and readiness for testing and Deployment. These activities must include the Department’s Test Manager.
TEST-39 | The Contractor must conduct modular certification testing for individual services to support incremental CMS and IRS approvals, ensuring that each service meets independent compliance requirements.
TEST-40 | The Contractor must ensure that testing team members are trained to recognize and report defects accurately.

## OCM
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
OCM-01 | The Contractor must utilize a recognized, industry-standard organizational change management (OCM) methodology, such as the Prosci Awareness, Desire, Knowledge, Ability, and Reinforcement (ADKAR®) model; Kotter’s Eight (8)-Step Process; or another proven framework to guide all change management activities. The selected methodology must be approved by the Department.
OCM-02 | The Contractor must align all OCM milestones, deliverables, and resource dependencies with the Converged E&E System and AMS Project Roadmap.
OCM-03 | The Contractor must conduct and document a comprehensive change readiness and impact assessment describing how new system functionality and processes will affect existing workflows, roles, and business units.
OCM-04 | The Contractor must conduct and document change readiness and impact assessments at the following intervals to measure user preparedness and identify areas requiring intervention, on a cadence determined by the Department: • Six (6) months prior to Go-Live • Three (3) months prior to Go-Live • Four (4) weeks prior to Go-Live
OCM-05 | The Contractor must develop and implement a multi-channel Communication Plan that includes stakeholder mapping, message sequencing, and delivery mechanisms such as email, intranet postings, town hall sessions.
OCM-06 | The Contractor must draft, format, and provide all communication artifacts and templates required to execute OCM activities defined in the Communication Plan.
OCM-07 | The Contractor must coordinate with other OCM activities in which the Department is engaged, including other initiatives and projects related to the Converged E&E System and the AMS.
OCM-08 | The Contractor must define target KPIs and provide a real-time or near-real-time digital OCM performance dashboard accessible to Department leadership. The Contractor must present these metrics during monthly readiness reviews beginning no later than ninety (90) days prior to the targeted Go-Live date and continuing for a minimum of ninety (90) days following Go-Live.
OCM-09 | The Contractor must provide a digital change readiness dashboard accessible to Department leadership. The Contractor must present this dashboard during weekly readiness reviews beginning no later than sixty (60) days prior to the targeted Go-Live date and continuing for a minimum of thirty (30) days following Go-Live.
OCM-10 | The Contractor must design and execute a comprehensive upskilling and competency development program to support the Department’s transition to a modern product management operating model. The Contractor must deliver targeted training and coaching to support demonstrable Product Owners proficiency across the product management life cycle.

## Maj. Sys. Updates, CBT, & Enh.
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
UPD-01 | The Contractor must collaborate with the Department to identify, define, and prioritize major system updates and enhancements throughout the Contract term.
UPD-02 | The Contractor must staff one (1) stable, cross-functional Capacity-Based Team (CBT). The CBT must include eight (8) dedicated full-time individuals (i.e., not full-time equivalents [FTEs]). Members on the CBT will be considered Key Staff, as defined in Section 5.3 – Staffing.
UPD-03 | The Contractor must comply with the Task Order process described in Section 5.2.8.4 – Task Order Process to define the scope, schedule, budget, and resources for each approved major system update or enhancement.
UPD-04 | The Contractor must respond to enhancement requests by submitting the required Task Order within one (1) week of receipt of the request from the Department, unless otherwise specified by the Department.
UPD-05 | The Contractor must prepare and submit all deliverables identified in an approved Task Order and must develop a DED for each deliverable.
UPD-06 | The Contractor must propose initiatives to improve efficiency, security, and functionality as part of the System Enhancement and Upgrade Report (refer to Section 5.8 – Deliverables for additional details).

## AI Usage
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
AIML-01 | The Contractor must submit an AI Usage Plan for all proposed uses of AI to the Department for review and approval.

## CMS Cert. and Compliance.
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
CERT-01 | The Contractor must support Streamlined Modular Certification (SMC) as mandated in the following: • State Medicaid Director Letter (SMDL) No. 22-001, Updated Medicaid IT Systems Guidance – Streamlined Modular Certification for Medicaid Enterprise Systems (April 14, 2022)1 • CMS Streamlined Modular Certification Guidance2 • Medicaid Streamlined Modular Certification3 • CMS MES Certification Repository4
CERT-02 | The Contractor must support the Department in achieving MES certification for the Converged E&E System. The Contractor must collaborate with the Department and its third-party vendors to develop and execute a Certification Plan that defines the responsibilities and activities required to obtain MES certification.
CERT-03 | The Contractor must deliver a Readiness Assessment that measures systems status and readiness, workload capacity, and interface integration and must successfully complete an Operational Readiness Review (ORR).
CERT-04 | The Contractor must support CR for the Converged E&E System and the AMS as required by CMS, including, at a minimum, making all relevant materials available to demonstrate compliance with the State’s required outcomes and metrics and assisting in system demonstrations.
CERT-05 | The Contractor must implement MITA goals and objectives. Applicable conditions and standards are documented in the CMS MES Certification Repository5.
CERT-06 | The Contractor must implement a solution that reflects all MITA technical and data management standards. The Contractor must coordinate with the Department to verify that the Converged E&E System adheres to MITA technical compliance guidelines and must participate in any MITA State Self-Assessment activities.
CERT-07 | The Contractor must work with the Department, the Technical Advisory Services (TAS) Contractor, and other vendors to perform certification-related activities, including the following: • Establishing and refining outcomes, metrics, and evaluation criteria • Executing processes required to produce evaluation deliverables • Maintaining and presenting evaluation deliverables to CMS • Participating in meetings and evaluation sessions associated with MES certification • Addressing deficiencies identified during certification evaluations • Coordinating certification activities across the Department
CERT-08 | The Contractor must provide the Department with monthly operational reporting required by CMS in a mutually agreed-upon template.
CERT-09 | The Contractor must maintain a list of outcomes based on CMS-required and State-defined outcomes. The Contractor must include review progress against those outcomes during project review meetings at intervals defined by the Department or upon request by the Department or CMS.
CERT-10 | The Contractor must monitor current MES certification guidance and support the Department in achieving certification in accordance with current or grandfathered CMS requirements.
CERT-11 | The Contractor must support all Department requests and directives related to achieving MES certification. The Contractor must incorporate changes resulting from Department decisions into Contractor processes and technologies to support certification.
CERT-12 | The Contractor must fulfill all obligations related to MES certification in accordance with the requirements of this RFP and any additional CMS-mandated certification requirements.
CERT-13 | The Contractor must maintain certification artifacts within a centralized repository owned and approved by the Department. Certification artifacts include, at a minimum, software, data, process documentation, and testing documentation.
CERT-14 | The Contractor must provide certification-related training to Department staff and other vendors participating in in the certification process for the Converged E&E System. The Contractor must update training materials, training plans, and the Certification Plan as required and must obtain Department approval for all updates.
CERT-15 | The Contractor must provide all technical, functional, and operational information required for the Department to obtain Authorization to Operate (ATO), in accordance with CMS guidance stated on the CMS CyberGeek website6.
CERT-16 | The Contractor must support all activities related to the three (3) year renewal of the ATO, including participation in reassessments and submission of updated documentation demonstrating ongoing compliance.
CERT-17 | The Contractor must support all activities related to ATO reauthorization when the Converged E&E System or the AMS undergoes a CMS-defined significant change.
CERT-18 | The Contractor must ensure that Contractor personnel are available to participate in all meetings, reviews, and consultations related to the ATO process, as requested by the Department.
CERT-19 | The Contractor must provide technical designs, operational plans, testing results, security documentation, and subject matter expertise necessary for the Department to complete and submit all application sections of the Blueprint for Approval of State-Based Health Insurance Exchanges7.
CERT-20 | The Contractor must participate in CMS-conducted ORRs and CRs as requested by the Department. This includes preparing for and attending regular progress monitoring calls, providing testing results, demonstrating system functionality, and formally addressing any findings or required CAPs identified by CMS during oversight activities.
CERT-21 | The Contractor must ensure that the Converged E&E System and all related processes are configurable to operate within the Department’s governance structure, as documented in the State’s Declaration of Intent Letter and the approved Exchange Blueprint Application.
Footnotes:
1 | https://www.medicaid.gov/federal-policy-guidance/downloads/smd22001.pdf
2 | https://www.medicaid.gov/medicaid/data-and-systems/downloads/smc-certification-guidance.pdf
3 | https://www.medicaid.gov/medicaid/data-systems/streamlined-modular-certification
4 | https://cmsgov.github.io/CMCS-DSG-DSS-Certification/
5 | https://cmsgov.github.io/CMCS-DSG-DSS-Certification-Staging/Conditions for Enhanced Funding/
6 | https://security.cms.gov/learn/authorization-operate-ato#types-of-authorizations
7 | https://www.cms.gov/cciio/resources/fact-sheets-and-faqs/downloads/cms-blueprint-application.pdf

## Transition-Out
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
TO-01 | Upon expiration of the Contract, upon the Contractor’s receipt of a notice of termination, or at the request of the Department, whichever is sooner, the Contractor must provide all Transition-Out and Cutover assistance necessary to enable the Department or its designee to effectively close out the Contract and transition services, functions, and responsibilities to the Department or a Successor Contractor.
TO-02 | The Contractor must develop, deliver, maintain, and execute a Transition-Out period and associated documentation that includes, at a minimum, identifying and implementing all activities, tasks, and deliverables required to transition all services, functions, and responsibilities for operating and maintaining the Converged E&E System, the AMS, and related subsystems and databases to the Department or a Successor Contractor.
TO-03 | The Contractor must develop, deliver, maintain, and execute Transition-Out activities and associated deliverables that include, at a minimum, the following: • Transition-Out Plan • Transition-Out Schedule • Transition-Out Training and Knowledge Transfer Sessions • Knowledge Transfer Artifacts • Transition-Out Weekly and Monthly Status Reports • Post-Cutover Assistance
TO-04 | During the Transition-Out period, the Contractor must facilitate a structured and orderly knowledge transfer for management and operations of the Converged E&E System and the AMS. Knowledge transfer must include, at a minimum, source code, all forms of system documentation and artifacts, and all intellectual property and ownership assets governed by this RFP (refer to Section 6.9 – Ownership). Knowledge transfer activities must be completed before the end of the Contract or upon termination of the Contract.
TO-05 | The Contractor must transfer all items needed to enable the Department or a Successor Contractor to establish a systems development environment, including, at a minimum, the following: • Application code • Software configuration • Data • Technical information
TO-06 | The Contractor must maintain sufficient project staff throughout the Transition-Out period to comply with all performance standards, SLAs, and requirements identified in this RFP and the Contract.
TO-07 | The Contractor must conclude the Transition-Out period upon successful completion of the Final Transition-Out Review and receipt of the Department’s approval. Successful completion of the Final Transition-Out Review requires the Contractor to demonstrate completion of all activities, tasks, and deliverables identified in the Transition-Out Schedule.
TO-08 | The Contractor must cooperate with and assist the Department or a Successor Contractor at end of the Contract by supporting transition planning, preparation, testing, and transfer of services, functions, and data.
TO-09 | The Contractor must develop, deliver, maintain, and execute a Transition-Out Plan prior to the end of the Contract that includes, at a minimum, the following: • Approach for supporting Transition-Out and Transition Cutover of all in-scope services, functions, and operations (SA, M&O, DDI, and PM) from the Contractor to the Department or a Successor Contractor • Narrative descriptions of each activity, task, and deliverable • Roles and responsibilities for the Contractor, the Department, and any Successor Contractor, including required roles or positions • Description of the creation and maintenance of a RAID log documenting risks, issues, decisions, and action items, including responsible parties, due dates, and actions taken • Plan and schedule for Transition-Out of all documentation and source code • Transition-Out Training Plan detailing the approaches and methodologies the Contractor must use to transfer knowledge to Department or Successor Contractor resources, including, at a minimum, the following: o Schedule of planned training sessions and demonstrations o Number of staff to be trained by topic area o Training topics with objectives and summaries for each topic o Length, location, and delivery method for each training session
TO-10 | The Contractor must execute and oversee all activities specified in the approved Transition-Out Plan throughout the Transition-Out period.
TO-11 | The Contractor must develop, deliver, maintain, and execute a Transition-Out Schedule that identifies and manages all Transition-Out activities and tasks, with associated dates or time frames, required for successful Transition Cutover to the Department or a Successor Contractor. The Transition-Out Schedule must incorporate the full Transition-Out period.
TO-12 | The Transition-Out Schedule must include, at a minimum, the following: • Baselining of the schedule and tracking of actuals • Activities and tasks with clear and meaningful names • Tasks for Contractor development of each Transition-Out deliverable • Tasks for the Department review of each Transition-Out deliverable • Tasks for the Contractor revision of each Transition-Out deliverable following Department review • Subsequent Department review of each Transition-Out deliverable following Contractor revision • Additional rounds of Department review and Contractor revision, as required • Department approval of each Transition-Out deliverable • Predecessor and successor dependencies for tasks • Resource assignments for tasks • Estimated hours and durations for tasks • Custom task fields and custom resource fields, as requested by the Department • Appropriate Contractor and Successor Contractor resource assignments and estimated hours The Contractor must assign actual resource names to near-term tasks, defined as tasks scheduled within one hundred twenty (120) days. The Contractor may assign generic resource titles, such as roles or teams, to tasks that are not classified as near-term.
TO-13 | The Contractor must manage updates and changes to the Transition-Out Schedule throughout the Transition-Out period, including re-estimation of activities, tasks, subtasks, and associated hours and durations. The Contractor must communicate and review all updates and changes during Weekly Transition-Out Status Report meetings.
TO-14 | The Contractor must conduct training and knowledge transfer sessions and demonstrations as identified in the Transition-Out Plan and Transition-Out Schedule.
TO-15 | Prior to initiating Transition-Out Training and Knowledge Transfer activities, the Contractor must provide the Department with the following: • Overview of scope items (SA, M&O, DDI, and PM), training materials covering all scope items, and review methods for training and knowledge transfer sessions, including items that require mutual agreement between the Contractor and a Successor Contractor • Schedule of planned training and knowledge transfer sessions and demonstrations • Description of the professional background, experience, subject matter expertise, and prior training experience for each staff resource facilitating the sessions and demonstrations • Number of staff to be trained per area • Training and knowledge transfer topics • Training and knowledge transfer methodology, including descriptions of training materials and other Knowledge Transfer Artifacts • Length and location for each training and knowledge transfer session or demonstration • Sample training and knowledge transfer materials and delivery method for each session or demonstration
TO-16 | Prior to the end of the Contract, the Contractor must develop, maintain, and provide knowledge transfer and training materials, including artifacts and documentation, for use in planned training sessions and demonstrations. The Department must review and approve these materials.
TO-17 | The Contractor must share final and editable versions of all key deliverables related to the SA, PM, DDI, and M&O scope areas and functions. At a minimum, these must include the deliverables and artifacts identified in this RFP, as well as any additional deliverables and artifacts agreed upon by the Department and the Contractor. The Contractor must submit these key deliverables to the Department for review at least one (1) month before the start of the Transition-Out period.
TO-18 | The Contractor must update and finalize all artifacts in coordination with the Department before sharing those artifacts with a Successor Contractor.
TO-19 | The Contractor must organize and facilitate weekly meetings to report on the progress of Transition-Out activities. Based on information presented by the Contractor during these meetings, the Department will assess whether the Contractor is on track to complete scheduled Transition-Out and Transition Cutover activities for the Department or a Successor Contractor.
TO-20 | The Weekly Project Status Report must include, at a minimum, the following: • Description of progress made for each task, deliverable, and milestone • Identification of any variance from the approved baseline • Description of risks and issues • Relevant KPIs
TO-21 | The Contractor must prepare a Monthly Status Report for an executive-level audience at the Department. At a minimum, the Monthly Status Report must include summary information from the Weekly Project Status Reports and any additional information requested by the Department.
TO-22 | The Contractor must conduct and facilitate a Transition-Out Final Review meeting for an executive-level audience to demonstration completion of Transition-Out activities. The Contractor must provide information demonstrating that all transition components, tasks, and activities are complete and that the Department or a Successor Contractor is now responsible for all services, functions, and operations.
TO-23 | The Contractor must support all weekly and monthly status report meetings with meeting agendas and accurate meeting minutes.
TO-24 | The Contractor must conduct a series of Transition-Out Readiness Reviews with the Department for each transition area and provide evidence of readiness to transfer full operational control and responsibility to the Department or a Successor Contractor. Transition-Out Readiness Reviews apply, at a minimum, to each of the transition areas (SA, PM, M&O, and DDI).
TO-25 | The Contractor must conduct Transition-Out Readiness Reviews with the Department to demonstrate termination of Contractor access to all Converged E&E System and AMS environments, systems, and source code.
TO-26 | Following Transition Cutover, the Contractor must make staff available to provide ad hoc support and post-Transition assistance to the Department or a Successor Contractor, as needed to address inquiries or issues.
TO-27 | The Contractor must acknowledge each post-Transition inquiry within one (1) business day and provide clear next steps and recommended paths to resolution.
TO-28 | The Contractor must be available for post-Transition touchpoints at a cadence mutually agreed upon with the Department or a Successor Contractor.

## Staffing
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
STAFF-01 | The Contractor must provide each of the Key Staff positions as defined in Section 5.3.2 – Key Staff.
STAFF-02 | The Contractor must provide that all proposed Key Staff and Support Staff meet, at a minimum, the required qualifications and provide evidence of required and preferred qualifications in their proposal. Evidence must include the following: • Resume for each proposed Key Staff individual that demonstrates relevant experience • Proof of required certifications, such as Project Management Professional (PMP)®, ITIL, Certified Business Analysis Professional (CBAP®), and The Open Group Architecture Framework (TOGAF®), if applicable • Narrative summary describing how the individual meets or exceeds the role-specific qualifications and responsibilities • Prior project examples demonstrating similar work Minimum qualifications must include, at a minimum, the following: • Advanced oral and written communication skills • Ability to perform assigned roles with minimal management oversight • Compliance with the role qualifications provided in this RFP • Strong analytical, organizational, and problem-solving abilities • Willingness and ability to perform the following: o Actively participate in designated project meetings o Represent the best interests of the Department o Identify and escalate issues as appropriate o Contribute to required weekly, monthly, or quarterly status reports
STAFF-03 | The Contractor must provide that all Contractor staff, including subcontractors, understand the Contractor’s roles and responsibilities, understand relevant Department policies, and complete mandatory Department training on time. The Contractor must maintain a tracker for the completion status of all mandatory staff trainings within the Department’s document repository.
STAFF-04 | The Contractor must coordinate with Department staff to capture staff onboarding and offboarding requirements and incorporate those into the Contractor’s onboarding and offboarding processes.
STAFF-05 | The Contractor must assemble its Key Staff at the primary project site no later than two (2) weeks following Contract approval and execution and must be onsite fifty percent (50%) or more during the Contract term. Being onsite means co-locating with Department staff at the office facility described in Section 5.4 – Office Facility.
STAFF-06 | The Contractor must provide knowledge transfer to incoming staff and create, maintain, and make available to the Department documentation that supports the knowledge transfer.
STAFF-07 | The Contractor must provide that all Key Staff positions are filled by employees of the Contractor.
STAFF-08 | The Contractor must manage the lists of Key Staff and Support Staff contained within this RFP and facilitate Department approval for changes to Key Staff and Support Staff in accordance with RFP requirements.
STAFF-09 | Prior to onboarding, the Contractor must submit Key Staff and Support Staff resumes and proof of certifications for Department review and approval. The Contractor must receive Department approval of each resource prior to onboarding.
STAFF-10 | The Contractor must designate backup personnel to provide coverage when staff are unavailable for more than three (3) business days, such as during vacation or brief illness. This includes, at a minimum, providing advance notice to the Department and identifying the designated backup personnel.
STAFF-11 | The Contractor must reduce staff turnover and maintain continuity of responsibilities for any Key Staff and Support Staff positions that are replaced. A qualified replacement must be available within thirty (30) calendar days of the vacancy, subject to Department review and approval. In the event the Department does not approve the replacement Key Staff or Support Staff member, the Contractor must resubmit a replacement for Department approval within forty-five (45) business days. Absence of Department approval does not reset the clock on the Key Staff Turnover SLA (refer to Attachment F – SLAs).
STAFF-12 | The Contractor must ensure all Key and Support Staff supporting the Converged E&E System and AMS are located within the Contiguous United States (CONUS).
STAFF-13 | The Contractor must provide that all staff, including subcontracted staff, comply with the requirements of this RFP.

## Office Facility
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
OF-01 | The Contractor must locate a facility within a ten (10)-mile radius of the current Department offices located at 11 Corporate Woods Boulevard, Albany, NY 12211. The facility must not be adjacent to railroad tracks or bodies of water. The Department must approve the location prior to occupancy.
OF-02 | At the Department’s discretion, the Contractor must allow at least sixty (60) calendar days for the Department to review lease agreements and conduct an optional site inspection prior to final lease execution.
OF-03 | The Contractor must identify a site with at least forty thousand (40,000) square feet of office space for the duration of the Contract term.
OF-04 | The Contractor must ensure the office facility is fully operational and accessible twenty-four (24) hours per day, seven (7) days per week, three hundred sixty-five (365) days per year. This accessibility must be provided to all authorized Department staff and Department-authorized consultant staff and must allow unescorted access at any time without prior notice.
OF-05 | The Contractor must provide the office facility for occupancy by Contractor staff, Department staff, and third-party consultant staff authorized by the Department. Department staff are anticipated to be co-located with the Contractor team in this facility for the Contract term.
OF-06 | The Contractor’s office facility must include, at a minimum, the following: • Suite for the Department, consultant staff, and visitors, consisting of shared space for both Department staff and the Contractor team to support collaboration and meetings • Entry area with reception desk, physical security controls, seating for visitors, coat closet, and related amenities • Wellness room compliant with all applicable NYS labor regulations, including, at a minimum, NYS Labor Law 206-c regarding rights of nursing mothers and NYS Human Rights Law (Executive Law 296) regarding reasonable accommodations for religious observance • General-purpose room for printing and mail processing • Storage space for office supplies, IT supplies, and janitorial supplies, including items such as masks, hand sanitizer, tissues, soap, toilet paper, first aid kits and supplies, Automated External Defibrillators (AEDs), and other health and safety equipment • Lockable room with a minimum size of two hundred fifty (250) square feet dedicated for storage of computers, laptops, and technology assets All spaces listed in this requirement must be shared with and accessible to Department staff. The facility must allow for the following activities: • Contract administration and work location for Department and Contractor staff • Project coordination • Requirements definition and review sessions, collaboration sessions, and meetings • System demonstrations, testing, and solution exploration activities • Discussions, presentations, and deliverable walkthroughs • Technical and user support functions to maintain office equipment • Transition management support • Training sessions • Twenty-four (24) hours per day, seven (7) days per week access to the Department IT/network room by designated Department staff
OF-07 | The Contractor is responsible for procuring and maintaining all equipment, installations, and office needs for the site for both Department and Contractor teams. Requirements for the Department must include, at a minimum, the following: • Twenty-five (25) offices, each approximately one hundred fifty (150) to two hundred fifty (250) square feet, each equipped with the following: o One (1) digital speaker phone o One (1) appropriately sized table o One (1) desk o Two (2) rolling ergonomic chairs o One (1) 4’x 6’ glass board or wall-adhesive glass board appropriate to the layout o One (1) digital presentation screen appropriate to the layout • Minimum of one hundred eighty (180) flexible, integrated, 6’x8’ cubicles designed to accommodate one hundred seventy (170) permanent or long-term Department staff and ten (10) visitors or future employees, including the following: o Tackable acoustical panels with glass tops and data and power integration o One (1) 36” x 18” glass board o One (1) locking three (3)-drawer file cabinet o One (1) three (3)-drawer cabinet located under the desk area (all keyed alike) o Workstation equipment, including one (1) laptop, two (2) external monitors, docking station, wireless keyboard, and mouse o Multiple electrical outlets • Two (2) IT rooms, approximately three hundred (300) square feet each, that include the following: o Secure access control o Power outlets o Network connectivity o Workbenches o Task lighting o Storage for tools, spare parts, and equipment • One (1) Main Distribution Frame (MDF) room, approximately sixty (60) square feet, with secure access control, environmental controls, power outlets, network connectivity, and rack space for servers and network equipment • Phones, furniture, layout design, and workspace components that support flexibility to accommodate additional staff • Rolling ergonomic chairs for all workstations and conference rooms, additional ergonomic chairs, whiteboard and glass board supplies, coat hangers, portable projectors or other audiovisual (AV) equipment, surge-protected extension cords, and trash and recycling bins • General-use file cabinets and shelving • Wall clocks in break/lunchrooms, conference rooms, and designated common areas • Conference rooms that include, at a minimum, the following: o One (1) conference room with table seating for forty (40) people with overflow seating for twenty-five (25) additional people o One (1) conference room with table seating for twenty-five (25) people with overflow seating for twenty-five (25) additional people o Six (6) conference rooms with table seating for twelve (12) people with overflow seating for ten (10) additional people o Four (4) conference rooms with table seating for ten (10) people o Two (2) conference rooms with table seating for eight (8) people o Conference room equipment and features that include, at a minimum, the following: ◼ AV projection equipment or screen display with secure Internet connectivity and appropriately sized display ◼ Department Local Area Network (LAN) connectivity ◼ Digital speaker phone with conference call capability, including a hardwired Department conference phone ◼ Video conferencing equipment ◼ Bluetooth and Wi-Fi connectivity ◼ Glass board or wall-adhesive glass board with a minimum size of 4’x 6’ as appropriate to the layout
OF-08 | The Contractor is responsible for all costs related to securing and maintaining the site, including, at a minimum, the following: • Leasehold requirements, including improvements • Utilities, including electricity, water, gas, sewer, and waste • Telephone and data services, with lines terminating at the point of demarcation on the Department network • Maintenance of telecommunications circuits between Department offices and Contractor facilities • Network switches and wireless access points to support Department staff and twenty-five percent (25%) growth • Office equipment and supplies, including glass boards and supplies, wall clocks, coat hangers, surge-protected extension cords, masks, hand sanitizer, tissues, soap, toilet paper, first aid kits and supplies, AEDs, and other health and safety equipment • Janitorial services and related supplies • Security, including physical security and access controls • Storage, transportation, shredding, and HIPAA-compliant disposal of confidential documents and media • Insurance • Electrical outlets, power, and distribution systems sufficient to support operations • Hardware acquisition and maintenance • Installation and maintenance of data lines for the Department network
OF-09 | For activities approved by the Department to be performed at a location other than the Contractor site, the Contractor must provide toll-free communications, including, at a minimum, Wi-Fi, Virtual Private Network (VPN), and Voice over Internet Protocol (VoIP), for Department staff to conduct work. These communications require coordination with the Department and NYS Office of Information Technology Services (ITS).
OF-10 | The Contractor must prepare a Facility Management Plan and submit it to the Department for review and approval within thirty (30) days of signing the lease. The Contractor must update the Facility Management Plan annually or at the request of the Department and must include all items described in this RFP/Contract, as well as records of improvements and services impacting the facility. The Facility Management Plan must comply with Public Employee Safety and Health (PESH) regulations and applicable town or municipality standards. Each element of the plan must be approved by the Department. The Facility Management Plan must include, at a minimum, the following: • Responsibilities of the Contractor, subcontractors, and leasing entity • Physical security details, including physical access control, storage of IT hardware and documentation, and protection of other physical assets • Monthly physical security audits • Summaries of requirements and audit results to support HIPAA compliance • Facility description and build-out plan • Floor plan layout, including square footage • Seating chart • Electrical specifications • Telecommunications specifications • Internet specifications • Fire and smoke detection specifications • Fire exit routes • Office, conference room, meeting room, break/lunchroom layouts • Furnishings for cubicles, offices, conference rooms, meeting rooms, break/lunchrooms • Wellness room or private location compliant with NYS labor regulations • Asset inventory of all Department assets purchased through the Contract, including IT equipment and office supplies • Facility security system and operation • Locations of AEDs • Number and names of staff trained in cardiopulmonary resuscitation (CPR) and use of AEDs • Parking plans, numbering, and assignments • Meeting rooms with descriptions that include, at a minimum, the following: o Number and types of meeting rooms o Seating capacity of each meeting room o Equipment included in each meeting room
OF-11 | The Contractor must provide the Department with reports detailing office facility utilization, including parking usage, occupancy of office space, and utility consumption, at a cadence defined by the Department and reflected in the Facility Management Plan. The Department reserves the right to adjust payments based on demonstrable cost savings resulting from reduced utilization.
OF-12 | The Contractor must equip a training room for classroom training to accommodate instructor-led sessions for thirty (30) staff. The training room must include, at a minimum, the following: • Hardware, software, and telecommunications necessary to support development, maintenance, and delivery of training programs and a seamless training experience • Capability to deploy approved training media, including teleconferencing, web-based training, and computer-based training • Portable tables or desks, ergonomic chairs, computers, tables, whiteboards or glass boards, and flip charts • Ceiling projector or digital display devices with secure Internet and Department network connectivity • Network printer or access to a nearby printer • Coat hangers or coat closet, trash and recycling bins, and a wall clock
OF-13 | The Contractor must provide a secure and adequately sized break/lunchroom that includes, at a minimum, the following: • Two (2) microwaves, toasters, and toaster ovens • Commercial-grade coffee machines with coffee and tea supplies • Utensils, cups, and kitchen supply storage • Refrigerators with freezers • Water dispensers with hot and cold water • Counter space, sinks, dish drying racks, dish detergent, paper towels • Trash and recycling containers • Vending machines or alternative food service providers within the facility • Hot water available within thirty (30) to sixty (60) seconds of activation
OF-14 | The Contractor must supply file cabinet storage for printing supplies, digital telephone service, and three (3) color multifunction printers with capabilities including printing, copying, scanning, emailing, and faxing. Printers must support Wi-Fi and network connectivity, automatic and manual paper feed, duplex scanning, and stapling. Printers must support paper sizes of 8.5” x 11”, 8.5” x 14”, and 11” x 17”. The Contractor must provide ink, toner, and paper, as well as maintenance for all printers.
OF-15 | The Contractor must ensure that the selected facility provides a minimum of two hundred (200) reserved parking spaces for Department use, including the following: • One hundred eighty (180) spaces reserved for staff • Twenty (20) spaces reserved for visitors or growth • At least ten (10) accessible spaces in compliance with local, State, and federal requirements Parking for Contractor and Department staff must be designated, reserved, and contiguous with the leased office space. Accessible parking must comply with all applicable requirements for quantity and design. If parking is shared with other tenants, Department spaces must be reserved and numbered. Parking must be available for the entire Contract term at no additional cost to the State. The Contractor must provide covered garage parking with security if feasible.
OF-16 | The Contractor must obtain and maintain all permits, approvals, licenses, certifications, and authorizations required by local, State, and federal entities for the site throughout the Contract term.
OF-17 | The Contractor must comply with all Occupational Safety and Health Administration (OSHA), PESH, and Department of Labor (DOL) environmental impact and fire code requirements, building codes, and accessibility regulations.
OF-18 | The Contractor must provide and maintain all necessary network and telecommunications circuits, including Wi-Fi, VPN, and VoIP. These circuits must be coordinated with the Department and NYS ITS.
OF-19 | The Contractor must install all required network wiring with Category 6e or higher copper cables and Optical Multimode 4 (OM4) twelve (12)-strand armored fiber cables with lucent connectors (LCs).
OF-20 | The Contractor must protect equipment from physical risks, including power failures and electrical anomalies. The Contractor must provide an electrical supply that includes, at a minimum, the following: • Dependable power supply with an uninterruptible power supply (UPS) and surge protection devices • Equipment tested and maintained in accordance with manufacturer recommendations • Multiple power feeds to prevent a single point of failure • Cooling systems to maintain appropriate operating temperatures
OF-21 | The Contractor must conduct ongoing facilities management and day-to-day facility maintenance throughout the term of the Contract, including, at a minimum, the following: • Daily cleaning, including on-call support • Daily trash removal • Recycle material pickup • Snow removal to support staff safety • Carpets and mats at all entry and exit points • Maintenance activities that include, at a minimum, the following: o Lighting o Vacuuming o Dusting o Pest control o Cleaning of common areas, including bathrooms, kitchen, hallways, and conference and meeting rooms • Building maintenance in accordance with the terms of the lease, including, at a minimum, the following: o Plumbing o Electrical systems o Generators o Air quality o Heating, ventilation, and air conditioning (HVAC) o Roof o Temperature controls
OF-22 | The Contractor must designate one (1) or more individuals to be responsible for reception and to perform activities that support daily facility operations. Reception personnel must be present at the reception area and available during business days from 8:30 a.m. to 4:30 p.m. Eastern Time, at a minimum. The Department reserves the right to modify these hours.
OF-23 | The Contractor must select a facility in a secure area protected by a defined security perimeter with appropriate security signage and entry controls that include, at a minimum, the following: • Physical access controls • Secure access card readers • Access rights that are regularly reviewed and updated • External surveillance cameras with a minimum of fourteen (14)-day footage archive
OF-24 | The Contractor must ensure that communication switches and network components receive the level of physical protection necessary to prevent unauthorized access.
OF-25 | The Contractor must ensure that power and telecommunications cabling carrying information or supporting information services are protected from interception or damage. The Contractor must document existing power and cabling covered by this requirement and provide that documentation to the Department for appropriate protective action.
OF-26 | The Contractor must ensure that wiring closets, communications rooms, and service rooms are secured to protect information resources and prevent unauthorized access to sensitive information.
OF-27 | The Contractor must obtain prior Department approval for the use of any equipment by the Contractor, its subcontractors, or others for work performed outside the Contractor’s premises, regardless of ownership. Security for such equipment must be equivalent to onsite equipment used for the same purpose, considering risks associated with offsite work. Equipment may include, at a minimum, personal computers, mobile phones, and similar devices used for offsite work or transport.
OF-28 | For any devices that must connect to the Department network, the Contractor must ensure that the devices are screened and approved by the Department prior to connection.
OF-29 | The Contractor must provide security safeguards to protect the Department and its contractors from harm and to protect all equipment from unauthorized access or damage, including, at a minimum, the following: • Sufficient lighting • Security access card system with magnetic locks, monitoring by security personnel, request-to-exit devices, and sounders • Recorded and supervised visitor access documented in a daily visitor log that includes date, time, name, and purpose of visit, with Department to the log upon request • Regular review and updates of access rights • Security patrols during business hours • External surveillance cameras with a minimum fourteen (14)-day footage archive
OF-30 | The Contractor must ensure that all lighting in the facility is dimmable to allow Department staff to adjust brightness levels as needed. The Contractor must also provide programmable lighting controls to support management of lighting configurations.
OF-31 | The Contractor must coordinate with the appropriate local law enforcement agency, such as sheriff’s office, city police, or town police, to conduct a facility walkthrough and complete an active shooter assessment. The Contractor, in coordination with the Department and any landlord or leaseholder, must implement all required security measures and recommendations resulting from the assessment.
OF-32 | The Contractor must provide document destruction and shredding services for the office facility to support secure disposal of sensitive information.
OF-33 | For multi-floor buildings equipped with elevators, the Contractor must ensure that elevator services remain operational twenty-four (24) hours per day, seven (7) days per week to support facility operations.

## Reporting
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
REP-01 | The Contractor must provide reports in Department-approved formats.
REP-02 | The Contractor must maintain audit-ready report packages, including source data references, calculation methods, and change history, and must furnish supporting documentation upon request.
REP-03 | The Contractor must deliver reports through Department-approved channels, such as secure portals or document repositories, and apply appropriate security classification, redaction, and access controls in accordance with the OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard.
REP-04 | The Contractor must use version control with dates and identifiers.
REP-05 | The Contractor must maintain a Master Report Catalog that includes, at a minimum, the following: • Title • Owning section • Audience • Cadence • Due date • Owner • Delivery location The Contractor must maintain alignment between the Master Report Catalog and updates to the underlying sections.
REP-06 | The Contractor must store reports and supporting artifacts in the Department-approved repository and comply with all applicable State and federal records retention requirements.
REP-07 | The Contractor must provide that both the Converged E&E System and the AMS replicate operational and analytical data in near-real time, including all schemas, tables, and columns except FTI, to the Department's lakehouse platform to support operational reporting and near-real-time analytics.
REP-08 | The Contractor must develop and implement a comprehensive KPI Framework that aligns with the Department’s SLAs and programmatic goals to track Converged E&E System and AMS performance, as well as user and consumer satisfaction. The Contractor must update the KPI Framework annually or as requested by the Department. The Contractor must provide the KPI Framework for Department review and approval, including actual performance data and reporting against the defined indicators and baseline values, by the start of the second year of the Contract.
REP-09 | The Contractor must conduct a joint KPI Workshop with the Department within ninety (90) days following the effective date of the Contract to define and mutually agree on an initial set of KPIs, associated measurement methodologies, and reporting frequencies. The output of the KPI Workshop must be a formally documented list of initial KPIs.
REP-10 | The Contractor must document the initial KPIs in an approved deliverable and execute them on a mutually agreed-upon schedule defined in the KPI Framework deliverable, which must be completed within one hundred twenty (120) days following the effective date of the Contract.
REP-11 | The Contractor must research and develop best methods for monitoring and tracking performance evaluation, including procurement of any necessary hardware or software.
REP-12 | The Contractor must report to the Department, at a minimum, quarterly on each established KPI once that KPI has been approved by the Department.
REP-13 | The Contractor must meet with the Department annually, or as otherwise mutually agreed, to review the continued relevance and effectiveness of the existing KPIs and propose additions or modifications based on operational data and evolving business needs. Any changes to the KPIs must be mutually agreed upon and reflected in the KPI Framework deliverable.
REP-14 | The Contractor must draft a Shared Responsibility Protocol for any KPI for which measurement is not technically feasible through automated reporting by the Converged E&E System and the AMS alone or requires input from the Department. The Contractor must obtain Department approval of the protocol and update the KPI Framework deliverable to define responsibilities for data collection, aggregation, and validation to support accurate performance measurement.
REP-15 | The Contractor must develop and implement an OKR Framework to drive accountability and progress toward strategic and cross-functional goals that extend beyond operational performance tracking. The Contractor must update the OKR Framework quarterly and align goals with system-wide impact, transformation, and continuous improvement. Operational metrics tracked through the KPI Framework must not be duplicated in OKRs.
REP-16 | The Contractor must deliver a Product Roadmap that reflects delivery activities aligned with current OKRs. The Product Roadmap is intended to provide directional insight into future workstreams over, at most, six (6) to twelve (12) months at a time. The Contractor must revise the Product Roadmap iteratively based on programmatic priorities, operational feedback, and discovery, in collaboration with the Department.
REP-17 | The Contractor must review the Product Roadmap with the Department as part of the quarterly OKR Summit process. The Product Roadmap must reflect the sequencing, interdependencies, and intended outcomes of technical, operational, and design activities aligned with the Department’s strategic priorities and the OKR Framework.
REP-18 | The Contractor must establish, in coordination with the Department, a Joint Steering Committee to govern and continuously improve KPIs and OKRs and to provide strategic guidance and oversight of the partnership. The Joint Steering Committee must be comprised of designated executives and key program stakeholders from the Department and the Contractor. Each party must designate its initial members in writing in a mutually agreed-upon deliverable. The Joint Steering Committee must meet no less than quarterly to perform its duties, including, at a minimum, reviewing service performance and overseeing the Continuous Improvement Program defined in this RFP.
REP-19 | The Contractor must establish, in coordination with the Department, a formal, collaborative Continuous Improvement Program with the goal of proactively identifying and executing initiatives to enhance the services supported by the Converged E&E System and the AMS, system performance, and value delivered to consumers. As a standing agenda item in the quarterly Joint Steering Committee meetings, the committee must review the following: • Historical performance data, service metrics, and user feedback • Potential improvements for the upcoming quarter, including improvement priorities in high-impact focus areas, such as enhancing specific features, improving workflows, or optimizing technical processes
REP-20 | The Contractor must establish, in coordination with the Department, a Resource and Investment Framework to determine appropriate resourcing and funding for initiatives identified through the Continuous Improvement Program. Each initiative within an Improvement Action Plan must be categorized by the Joint Action Committee as either an “Operational Enhancement” or a “Strategic Investment” as defined in Section 5.5.1 – Key Performance Indicators and Objectives and Key Results.

## IT
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
IT-01 | The Contractor must be responsible for providing their team, including Key Staff and Support Staff, with IT equipment, laptops, and other components necessary to perform responsibilities and comply with the requirements of this RFP. Laptops must have enough processor speed, memory, and hard drive space to operate and support the current release of Microsoft’s operating system and Microsoft Office Suite software, as well as any additional equipment and software necessary to comply with the requirements of this RFP. The Department must image all laptops to facilitate access to Departmental assets. The Department will provide the make and model of workstations suitable for imaging by the Department.
IT-02 | If requested by the Department, the Contractor may be required to procure equipment through a third-party vendor(s) for two hundred fifty (250) workstations for Department staff. Equipment for each workstation must include, at a minimum, a laptop, two external monitors, docking station, wireless keyboard, and wireless mouse. Laptops must adhere to Transaction Processing Performance Council (TPC) benchmarks and have sufficient processor speed, memory, and hard drive space to operate and support the current release of Microsoft’s operating system and Office Suite software, as well as any additional equipment and software necessary to access and utilize the Department’s network. Laptops requiring replacement or upgrades will be delivered to the Contractor’s primary site for work to be performed at that site. The Department will provide specifications for all workstations that the Contractor must procure.
IT-03 | The Contractor must provide print and mail services to support the business functions and services associated with the Converged E&E System and the AMS. This includes generating, processing, and sending files in appropriate formats, including, at a minimum, large print, audio compact disc (CD), data CD, and braille, for mail processing and printing services.
IT-04 | The Contractor must provide the equipment, software, training, and facilities to support print and mail services.
IT-05 | The Contractor’s print and mail center must be capable of high-volume printing and mailing, at levels necessary to support programs associated with the Converged E&E System, of various communication types that include, at a minimum, letters, forms, notices, postcards, flyers, brochures, ID cards, enrollment packages, and welcome kits. This includes the ability to handle different paper sizes, envelopes, and folding requirements. Printed documents must include basic black printing on white paper, as well as full-color, glossy, multifold brochures and presentation materials.
IT-06 | The Contractor’s print and mail center must provide a variety of mailing services to meet different business needs that include, at a minimum, print production, mass mailings, mail tracking, and postage expenditure monitoring (separate from print and mail expenditures).
IT-07 | The Contractor must track all mailings.
IT-08 | The Contractor’s print and mail center mail center must have a robust QA process to verify the accuracy and completeness of all mailings.
IT-09 | The Contractor must handle all mailings in a secure and confidential manner in compliance with all applicable State and federal regulations, including HIPAA.
IT-10 | The Contractor must provide detailed reporting on print and mail volumes, timeliness, and error rates, as well as the status of each mailing, including delivery and return information.
IT-11 | The Contractor must account for the USPS holiday schedule for printing and mailing.
IT-12 | The Contractor’s print center must handle returned mail and update recipient addresses.
IT-13 | In accordance with applicable State and federal policies, the Contractor must provide notices or correspondence to individuals in their preferred written language, including, at a minimum, the following twelve (12) common languages spoken by individuals with limited English proficiency in New York State: • Spanish • Chinese (Traditional) • Chinese (Simplified) • Russian • Yiddish • Bangla (Bengali) • Haitian Creole • Korean • Arabic • French (France) • Polish • Urdu In addition to these twelve (12) languages, the NYS Language Access Law requires agencies to include four additional languages specific to each agency. Based on data obtained from the Language Access Plan and the most recent five (5)-year NYC Administration for Children’s Services (ACS) data, the Contractor must provide notices or correspondence in four (4) additional languages: Japanese, Hindi, Nepali, and Burmese.
IT-14 | The Contractor must provide notices or correspondence to individuals that reflect their preferences in the Converged E&E System.
IT-15 | The Contractor must integrate the Converged E&E System with the Department’s selected print and mail vendor if the Department procures a print and mail vendor independently.
IT-16 | If requested by the Department, the Contractor may be required to provide software procurement services. Software procurement services are defined as the procurement of a third-party software product by the Contractor on behalf of the Department. For these services, the Contractor may act as a payee agent managing the procurement process. The Department, as the end user, must hold any applicable license in its name directly with the third-party vendor and comply with the vendor’s terms. Management of software license usage and other license requirements is the responsibility of the Department, with assistance from the Contractor as mutually agreed.
IT-17 | The Contractor and the Department must meet quarterly, or as needed, to review software procurements.
IT-18 | The Contractor must maintain an end-of-life document to track and monitor software license expiration and renewal dates.
IT-19 | The Contractor must notify the Department of the need for software procurement services one hundred eighty (180) days in advance of the proposed installation. The purchase of the software must occur with sufficient time to support installation.
IT-20 | The Contractor must notify the Department one hundred eighty (180) days in advance of the expiration of a software license requiring renewal, termination, re-procurement, or installation.
IT-21 | In software versioning, the current release version is known as N and the prior major version is N-1. Older versions are labeled as N-2, N-3, and so on. For the purposes of the software currency policy, N means the version of software designated and approved by the Department as the current standard for Deployment. N-1 is one (1) release prior to the designated version, and N-2 is two (2) or more releases prior. Conversely, N+1 is any version level released by a manufacturer, in production or beta, after the N version. The Contractor must maintain the following versioning requirements for all software supporting the Converged E&E System: • N-1 must have at least twelve (12) months remaining before being designated end of support or unsupported. • N-2 or older versions must be updated, replaced, or discontinued within twelve (12) months. • If a refresh is not possible for technical or business reasons, an exception must be requested and approved by the Department, including impacts on cost and security. • Early adoption of N+1 release requires an exception approved by the Department, and a current version list must be maintained and updated in the SADD.
IT-22 | The Contractor must review decisions for software procurement services with the ARB.
IT-23 | The Contractor must follow the NYS OGS Terms and Conditions of manufacturer and distributer contracts for software procurement services.
IT-24 | The Contractor must retain and maintain all software license certificates and copies of all purchase orders in the Department’s preferred document repository.
IT-25 | Software procurement services must be performed by the Contractor and must not be subcontracted or delegated to any other organization, subdivision, association, individual, corporation, partnership, group of individuals, or other such entity without prior written consent of the Department.
IT-26 | The Contractor must obtain Department review and approval prior to incorporating any intellectual property into the Converged E&E System or the AMS.
IT-27 | If the Contractor receives Department approval to incorporate its intellectual property into the Converged E&E System or the AMS, the Department’s rights to that intellectual property upon Contract termination or solution transition must be protected.
IT-28 | The Contractor must grant the Department, or a Department-selected entity, perpetual, irrevocable, nonexclusive, and royalty-free licenses to use, modify, and support all Contractor intellectual property necessary to operate the Converged E&E System and the AMS. These licenses must allow continued operation and enhancement by the Department or its selected entity.
IT-29 | If the Contractor receives Department approval to incorporate intellectual property into the Converged E&E System or the AMS, the Contractor must provide all documentation and materials necessary for the Department to continue using the intellectual property.

## Security & Privacy
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
SP-01 | The Contractor must comply with OHIP Security and Privacy Standards, which include, at a minimum, the following: • OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard • OHIP API Secure Development Baseline Standard • OHIP AI Security and Privacy Baseline Standard
SP-02 | The Contractor must provide the Department with an Information Security Risk Assessment (ISRA) at the frequency defined in Section 5.8 – Deliverables. The ISRA must include findings from the Security Information and Event Management (SIEM) solution, industry alerts, and analysis of potential impact of security breaches to sensitive data, critical system components, and preventative strategies to address identified or reported vulnerabilities and threats.
SP-03 | The Contractor must perform a Well-Architected Review of the Converged E&E System's cloud security architecture on a schedule agreed upon with the Department. The review shall apply the security pillar of the applicable cloud provider's well-architected framework, the AWS Well-Architected Framework for AWS-hosted components and the Google Cloud Well-Architected Framework for Google Cloud-hosted components.
SP-04 | The Contractor’s solution must include a security and privacy control framework based on the OHIP Security, Privacy, and Compliance Domain Standards with fine-grained RBACs that restrict read, write, and update capabilities at a data domain level so users access only the information necessary for their specific responsibilities.
SP-05 | The Contractor must maintain an SSPP in accordance with the OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard. The Contractor must maintain comprehensive security documentation, including policies, standards, architecture documents, the SSPP, control descriptions, incident response, and DR procedures. The Contractor must maintain documentation as current and must inform the OHIP Security Team when changes are made.
SP-06 | The Contractor must engage a third-party vendor to perform security auditing, for System and Organization Controls 2 (SOC 2) audits, penetration testing, and risk assessments. The Contractor must provide certificates and reports to the Department.
SP-07 | The Contractor must use a multi-layered preventative and reactive approach to comply with all business and technical requirements and SLAs. This approach must include, at a minimum, logical boundary security, redirection of connections, separation of duties, user authentication and authorization, and end-user behavior analysis.
SP-08 | The Contractor must provide reference within the M&O Manual to the SSPP to identify and mitigate threats to the system, including, at a minimum, applications, networks, and facilities.
SP-09 | The Contractor must maintain the Department-provided Data Protection Plan (DPP) and include it in the SSPP.
SP-10 | The Contractor must develop, update, and maintain the DMP.
SP-11 | The Contractor must develop Safeguard Procedures Reports that outline measures and protocols to protect sensitive data. The reports must provide a detailed account of the physical, technical, and administrative safeguards implemented to prevent unauthorized access, disclosure, alteration, or destruction of PHI, PII, FTI, and other protected data.
SP-12 | The Contractor must be responsible for the following: • Authentication Processes – Maintenance and documentation of methods to verify user identity before accessing systems or resources for users based on role categories and access mechanisms • Security and Privacy Framework – Implementation and maintenance of a framework that includes the following: o Use of Public Key Infrastructure (PKI) following standard practices, including accepted Certificate Authorities (CAs) o Documentation of certificate policies and certificate practice statements, including a key escrow strategy o Use of fundamental technical standards, including X.509 certificate format and public cryptographic standards o Implementation of PKIs across entities to address interoperability requirements • Enterprise Authorization Service – Provision of a system IAM service that interoperates with the enterprise IAM service provided by the Department and includes the following: o RBACs and content-based access controls (CBACs) for information exchanged using the enterprise IAM service, including controls at page, action, and field levels within applications or modules o RBACs limited to specific modules or extended across multiple modules o Interfaces that allow authorized users to create, edit, and implement role-based and group-based security at the data element, field, or resource level for users, processes, and applications based on individual characteristics or functional security groups o Support for PKI for trusted processes, applications, user registration, and authorization aligned with Unified Data Access Profiles (UDAP™) o Support for signature of user agreements regarding federal and State laws about data access and use o Secure token server mechanisms supporting authorization and access permissions using Security Assertion Markup Language (SAML), Web Services Security (WS-Security), and native Open Authorization (OAuth), including frameworks such as Substitutable Medical Applications, Reusable Technologies (SMART) and Unfair, Deceptive, or Abusive Acts or Practices (UDAAP) o Physical and electronic environments using PKI to verify transactions and user identity and deny access to unauthorized users
SP-13 | The Contractor must ensure that network management and control system tools are available to a minimum of three (3) additional users, as determined by the Department, on a floating basis to provide unrestricted access to the performance monitoring and failure alert data.
SP-14 | The Contractor must grant read-only access for independent analysis and verification as directed by the Department.
SP-15 | The Contractor must, at a minimum, be responsible for the following: • Security management of logging data and equipment used for security logging services • Routine monitoring of security logs to identify threats and trends • Monitoring of login transactions from the Worker Portal, Assistor Portal, and Member Portal for response times, user authentication, and other related metrics as determined by the Department • Recommendations and immediate remedial actions based on threat severity
SP-16 | The Contractor must design, document, and implement a Risk-Based Security and Privacy Framework. The framework must include, at a minimum, the following key elements: • Risk-Based Security and Privacy Framework Key Elements o Risk Assessment – Regular conduct of risk assessments to identify vulnerabilities and threats to information systems and data o Impact Assessment – Evaluation of the potential impact and likelihood of identified vulnerabilities and threats o Risk Mitigation – Implementation of appropriate security measures to reduce identified risks to an acceptable level o Continuous Monitoring – Continuous monitoring of systems and implemented security controls to detect and respond to threats timely o Incident Response and Recovery – Development of plans and procedures to respond to security incidents and breaches, mitigate their impact, and restore normal operations o Training and Awareness – Education of Contractor staff, subcontractors, and other staff on their roles in maintaining security and privacy, including handling sensitive information and recognizing potential threats o Compliance – Compliance with relevant federal laws, regulations, and guidance, and accountability for adherence to these requirements • Fail-Safe and Redundancy Measures o Fail-Safe Systems – Implementation of systems that do not expose sensitive information or leave access controls vulnerable in a failed state o Redundancy – Implementation of fully redundant network and equipment components, including use of geographically remote AWS and GCP cloud regions to separate primary (Production) and secondary (DR) sites o Transaction Contingencies – Development of contingencies for storing transactions dependent on business partner data availability (e.g., IRS, U.S. Department of Homeland Security [DHS], SSA) o Periodic Testing – Performance of periodic testing of failover and failback capabilities • Baseline Oversight Activities o Compliance Integration – Implementation of processes, tools, and technologies to integrate compliance oversight activities, including ongoing monitoring and periodic reporting with evidence of compliance with security, privacy, data exchange, and usage requirements o Risk Management – Alignment of risk management activities with NIST SP 800-37 guidance o Secured Coding Practices – Implementation of secure coding practices within SDLC best practices to prevent common software vulnerabilities o Documentation – Documentation of required privacy artifacts o Approval Authority – Approval authority for accreditation of systems and interconnections o Privacy Principles – Application of privacy principles guided by the U.S. Department of Health and Human Services (HHS), including the following: ◼ Individual Access ◼ Correction ◼ Openness and Transparency ◼ Individual Choice ◼ Collection ◼ Use and Disclosure Limitation ◼ Data Integrity ◼ Accountability • Staffing Requirements – Development and maintenance of fully trained staff capable of responding to stakeholder inquiries while protecting confidentiality and maintaining the security and integrity of all systems
SP-17 | The Contractor must be responsible for managing all security incidents through its standard life cycle that includes, at a minimum, the following: • Identification • Collection and preservation of evidence • Containment • Eradication • Recovery • Follow-up The Contractor must also perform the following: • Inform the Department, as soon as possible but no later than one (1) hour from detection, of all incidents or exposures of information that may have compromised the secure delivery of data • Directly report all security incidents affecting or potentially affecting the Converged E&E System and the AMS to Department personnel, or Department-approved designee(s), using NIST SP 800-86 Guide to Integrating Forensic Techniques into Incident Response1 o Incidents as specified in NIST SP 800-61 (as amended) in the Cybersecurity and Infrastructure Security Agency (CISA) Federal Incident Notification Guidelines2 o Any incident involving compromised PHI, PII, or FTI reported to CISA and the Department personnel defined in requirement SP-29 within one (1) hour of detection, regardless of reporting time frame • Provide a formal report to the Department within twenty-four (24) hours of initial notification that includes, at a minimum, the following: o Data elements involved and extent of the data impacted o Description of unauthorized persons known or reasonably believed to have improperly used or disclosed PHI, PII, or FTI o Description of where PHI, PII, or FTI was improperly transmitted, sent, or used o Description of probable causes of improper use or disclosure, including an RCA o Determination of whether civil code or any other State or federal laws requiring breach notification are triggered
SP-18 | The Contractor must provide the ability to time out users in the Member Portal, Assistor Portal, Worker Portal, Partner Portal, Issuer Portal, and Employer Portal after a period of inactivity. The Department will define the required inactivity period.
SP-19 | The Contractor must provide administrative access to the Converged E&E System to designated and approved stakeholders.
SP-20 | The Contractor must maintain a security solution that automatically restricts user or system access when anomalies in behavior are detected during attempts to access data.
SP-21 | The Contractor must notify the Department of any open-source software used as a system component. Refer to the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard for additional details.
SP-22 | The Contractor must request Department approval for any open-source software implementation at least thirty (30) calendar days prior to planned implementation. Refer to the OHIP Infrastructure & Operations Domain Document, Preferred Operational Tools Standard for additional details.
SP-23 | Through structured QA and testing processes, the Contractor must certify software upgrades and patches and security patches for all third-party software supporting the system.
SP-24 | The Contractor must monitor federal exchange initiatives and demonstrate best efforts to anticipate and implement changes to hosted environments to comply with new federal and State encryption and information security standards for origin authentication, data integrity, and signer nonrepudiation for digital signatures.
SP-25 | The Contractor’s personnel who provide support for the AWS- and GCP-hosted environments storing unmasked data must be U.S. citizens and maintain National Agency Check with Inquiries (NACI) Tier-1 clearance or greater. The Contractor must include evidence of compliance in assessor artifacts and deliverables.
SP-26 | The Contractor must maintain logs for all transactions that include, at a minimum, all essential data, which must be retained in accordance with the OHIP Infrastructure & Operations Domain Document, Log Management Standard.
SP-27 | The Contractor must maintain adequate security staffing to provide twenty-four (24) hours per day, seven (7) days per week, three hundred sixty-five (365) days per year uninterrupted security monitoring and prompt issue response in accordance with the OHIP Security, Privacy, and Compliance Domain Document, Security and Privacy Compliance Standard. The Contractor must provide a similar level of support, including staff security knowledge, experience, and accessibility, during normal business hours for DevSecOps support, auditing, testing, scanning, and reporting for the Contractor and other vendors designated by the Department.
SP-28 | In consultation with the Department, the Contractor must take over and maintain the security solution supporting the AWS GovCloud and GCP platforms. The security solution must include management and staff skill levels that support, at a minimum, the following security controls: • Secure SDLC that uses federated authentication and authorization • Monitoring, detection, alerting, and prevention of security vulnerabilities • Roles, responsibilities, and operating procedures
SP-29 | The Contractor must maintain the application at Federal Information Security Management Act (FISMA) Moderate level of certification throughout the Contract term with the Department and provide evidence of continuous monitoring of control compliance and retention of certification status. The Department reserves the right to review, approve, and request additional detail in the Contractor’s proposed artifacts used as proof of certification, ongoing compliance, and retention of certification status.
SP-30 | The Contractor must provide the Department with a list of staff, identified by name and role, who have system administration, monitoring, or security responsibilities and who will receive security alert advisories and directives from the Department. The list must also include designated Department personnel.
SP-31 | The Contractor must ensure that integration activities do not counteract or nullify, by design or inadvertently, any federal, State, or local security, privacy, and confidentially standards as described in the NYS Enterprise Security Plan standards and SSP workbooks. To support this requirement, the Contractor must provide a Cross-System Security and Privacy Standards Analysis and Review report that is approved in writing by the Department’s CIO, Chief Information Security Officer (CISO), Security Director, or their designee prior to the integration activity being authorized to operate.
SP-32 | The Contactor must work with the Department to implement and maintain a consent management capability with either its IAM solution or the enterprise IAM to collect and manage user consents in compliance with State and federal regulations as required.
SP-33 | The Contractor must use commercial Governance, Risk, and Compliance (GRC) tools or Contractor-provided GRC tools, subject to Department approval, to identify system vulnerabilities or risks and manage policies, control user access, and streamline compliance processes. The Contractor must share reports generated by the GRC tool at a regular frequency or on an ad hoc basis as directed by the Department.
SP-34 | The Contractor must comply with all State and federal laws governing the monitoring, interception, recording, use, or disclosure of wire, oral, or electronic communications. In the case of any exception, the Contractor must obtain Department approval.
SP-35 | The Contractor must use commercial data anonymization tools to de-identify data to protect the privacy of individuals. De-identified data sets may be used for system testing and generation of business intelligence applicable to a population.
SP-36 | The Contractor must provide secure and confidential backup, storage, and transmission for hard copy and electronically stored information.
SP-37 | The Contractor must comply with the Department’s OHIP Offshoring Data Policy (refer to Exhibit G.11 – OHIP Offshoring Data Policy), which prohibits the storage, processing, or access of protected data by any employees, agents, representatives, contractors, or subcontractors located outside of the United States and its territories.
Footnotes:
1 | https://csrc.nist.gov/pubs/sp/800/86/final
2 | https://www.cisa.gov/federal-incident-notification-guidelines

## SLAs
Requirement Number | Requirement Description | Does the Bidder comply with this requirement (Yes or No)? | If the Bidder's response to the question in column C is "No," provide a detailed explanation for alternative solutions, workarounds, or compensatory measures to achieve the same outcome and comply with the requirement's intent.
SLA-01 | The Contractor must continuously track, monitor, and report on all SLAs defined in Attachment F – SLAs throughout the Contract term. SLA reporting must be provided in a format acceptable to the Department and in compliance with the required artifacts defined in Attachment F – SLAs. Tracking and monitoring must enable the Department to easily identify when performance thresholds are not met.
SLA-02 | The Contractor must develop and maintain a formal process for ongoing review of SLAs between the Department and the Contractor. The Contractor must submit this process to the Department for approval within ninety (90) calendar days of the Contract start date.
SLA-03 | The Contractor must monitor performance against all SLAs required by the Department. SLA monitoring and reporting must be accurate and provide the Department with a comprehensive view of performance for each service.
SLA-04 | The Contractor must perform periodic reviews of SLA compliance and performance on a schedule defined by the Department and must provide formal reports of findings to the Department.
SLA-05 | The Contractor must maintain SLA compliance for system capacity and performance under increased business volumes, including impacts driven by seasonal fluctuations.
SLA-06 | The Contractor must understand and document the data sources and measurement method for all SLAs and must support the Department during SLA audits and validation procedures.
SLA-07 | The Contractor must apply SLA management principles consistent with the most current version of ITIL to support SLA governance and operations.
SLA-08 | The Contractor must implement the necessary technologies, processes, and personnel to manage and monitor SLAs. All technologies and processes used to measure SLA performance must be fully documented and made available to the Department at all times to support transparency and accountability.
SLA-09 | The Contractor must maintain a comprehensive SLA dashboard accessible to the Department that summarizes current and historical SLA metrics. The Contractor’s SLA dashboard must implement an automated reporting mechanism that the Department can use on demand. The dashboard must be able to aggregate SLA metrics and provide drill-down capabilities for all SLAs, where feasible, in accordance with the requirements defined in Attachment F – SLAs, on a continuous basis throughout the duration of the Contract. Any SLA data missing from the dashboard, unless otherwise approved by the Department, is considered a failed SLA.
SLA-10 | The Contractor must collaborate with the Department to define and obtain Department approval for the data sources and measurement processes used for SLA monitoring and reporting.