## Phase 1 W (completed)
MRT Project # | Date | Schedule | Budget | Risk | Project/Task Description | State Savings 2011-2012 ($millions) | Status/Team Lead Information
Key |  |  |  |  | Completed, On Track, Caution, Alert
P = Completed 8 = On Track ▲ = Caution T = Alert _ = Unknown
As of: | 8/24/16
209 |  |  |  |  | Project Name: Expand Hospice Division Lead: OLTC Team Lead: Rebecca Fuller Gray Add'l Staff: Diane Jones, Mike Heeran Description: This proposal will expand hospice: Expand concurrent hopsice and curative care to Medicaid adults; Expand definition of terminal illness to 12 months; Integrate hospice into medical home and ACO projects | 0 | Competed August 2016
| 2011-03-25 | P | P | P | Request data to determine the number of dual eligibles, i.e. Medicare and Medicaid over age 18 that access hospice benefits; to determine the current length of stay for hospice; determine the number of Medicaid only individuals that access hospice
| 2011-05-05 | P | P | P | Request DLA to review the proposal in terms of Social Security Act issues
| 2011-05-15 | P | P | P | Contact the CMS Central Office to clarify rules regarding election of hospice benefit and the continuation of curative treatment in adults
| 2011-05-24 | P | P | P | Discuss components of the proposal with the Hospice and Palliative Care Association of NYS
| 2011-07-01 | P | P | P | Evaluate research to determine how to implement the expansion of the definition of terminal illness to 12 months if possible
| 2011-08-01 | P | P | P | Conclude discussions with CMS and hospice association and make determination on implementing expansion of definition of terminal illness to 12 months
| 4/1/11 9/1/11 9/15/11 9/30/11 10/7/11 | P | P | P | Perform fiscal analysis to determine the impact from extending definition of terminal illness to 12 months
| 9/15/11 10/15/11 | P | P | P | Draft Federal Notice for SPA change
| 9/28/11 9/30/11 10/30/11 11/22/11 | P | P | P | Submit Federal Notice to be published on 12/7/2011
| 6/1/11 8/1/11 9/1/11 10/1/11 | P | P | P | Initiate research on the medical home model of care delivery in NYS and specifically as it relates to the Affordable Care Act and end of life care. Health care reform legislation authorizes the Department of Health and Human Services (HHS) to test medical homes among other new care-delivery models. Supporters hope patient-centered medical homes will help refocus the U.S. health care system on the benefits of primary care.
| 6/1/11 8/1/11 9/1/11 10/1/11 | P | P | P | Initiate research on the ACO and its success in NYS and applicability to hospice in particular. The accountable care organization has been a model for health care reform, yet its success has been limited to a handful of health care systems across the country. The accountable care organization model has recently taken on far greater significance since being introduced as one of Medicare’s pilot programs in the Senate’s health reform bill.
| 2011-10-06 | P | P | P | Draft revised hospice regulations
| 10/12/11 1/15/12 | P | P | P | Prepare notice to state register for publication of regulations
| 12/1/11 3/1/12 | P | P | P | Revise billing methodology and payment rules for implementation
| 12/15/11 9/15/11 9/30/11 10/30/11 12/15/11 4/1/12 5/22/12 | P | P | P | Submit state plan amendment to CMS
| 10/30/12 11/30/12 12/31/12 1/29/13 2/19/13 4/10/13 4/24/13 5/29/13 6/19/13 7/3/13 8/7/13 8/28/13 9/11/13 10/16/13 10/23/13 | P | P | P | Submit Notice of Proposed Rulemaking to State Register to post regulations for Public Comment
| 7/26/12 9/20/12 11/15/12 1/24/13 3/21/13 5/23/13 7/18/13 9/12/13 11/21/13 | P | P | P | Present regulations to PHHPC Codes Committee for informational purposes
| 1/15/12 04/10/12 5/1/12 10/1/12 12/1/12 | 8 | 8 | 8 | Draft DAL
| 11/28/11 3/15/12 5/1/12 9/30/12 10/15/12 11/15/12 1/18/13 2/18/13 3/30/13 5/31/13 7/29/13 10/10/13 11/1/13 1/6/14 2/7/14 3/3/14 | P | P | P | Prepare response to public comments
| 2014-03-31 | P | P | P | Draft revised hospice regulations based on public comments
| 5/6/14 7/1/14 7/29/14 10/14/14 12/14/14 1/23/15 3/3/15 3/20/15 5/1/15 6/1/15 6/15/15 7/15/15 8/14/15 9/15/15 10/15/15 1/28/16 2/23/16 1/25/16 | P | P | P | Prepare notice to state register for publication of revised regulations
| 5/13/14 7/8/14 8/5/14 10/28/14 12/16/14 2/3/15 3/17/15 3/31/15 5/19/15 7/1/15 7/15/15 8/14/15 9/14/15 10/13/15 11/13/15 2/16/16 3/8/16 1/26/16 | P | P | P | Submit Notice of Revised Proposed Rulemaking to State Register to post regulations for Public Comment
| 2016-02-10 | P | P | P | Revised Proposed Rule published in the State Register
| 7/21/14 9/3/14 9/16/14 12/9/14 2/2/15 3/6/15 4/20/15 5/15/15 7/7/15 9/1/15 9/15/15 10/15/15 11/5/15 12/7/15 3/8/16 4/12/16 | P | P | P | Prepare response to public comments
| 12/8/11 4/05/12 5/24/12 7/26/12 9/20/12 11/15/12 3/21/13 & 4/11/13 5/23/13 & 6/6/13 7/18/31 & 8/1/13 9/12/13 & 10/3/13 11/21/13 & 12/12/13 1/2014* & 2/2014* *tentative dates; 2014 PHHPC schedule not yet available 1/30/14 & 2/13/14 3/27/14 & 4/10/14 5/22/14 & 6/12/14 7/24/14 & 8/7/14 11/13/14 & 12/4/14 1/29/15 &2/12/15 3/26/15 & 4/16/15 5/21/15 & 6/11/15 7/23/15 & 8/6/15 9/24/15 & 10/8/15 11/19/15 & 12/10/15 1/28/16 & 2/11/16 5/19/16 & 6/9/16 | 8 | 8 | 8 | Present regulations to PHHPC Codes Committee for recommendation and to full Council for adoption (task split and continued on lines below) |  | *tentative dates; 2014 PHHPC schedule not yet available
| 5/19/16 7/21/16 | P | P | P | Present regulations to PHHPC Codes Committee for recommendation
| 6/9/16 8/4/16 | P | P | P | Present regulations to full Council for adoption
| 12/28/2011 04/28/2012 8/1/12 10/31/12 12/31/12 4/10/13 6/11/13 8/14/13 10/23/13 12/31/13 3/12/14 5/14/14 6/18/14 8/22/14 12/24/14 2/25/15 4/28/15 6/16/15 8/15/15 10/21/15 12/23/15 2/25/16 6/22/16 8/31/16 9/30/16 | P | P | P | Publish notice of adoption to State Register
| 2/15/2012 04/15/2012 6/1/12 11/1/2012 1/1/13 4/1/13 7/1/13 9/2/13 11/6/13 1/10/14 3/24/14 5/28/14 6/27/14 8/27/14 1/5/15 3/11/15 5/4/15 5/11/15 6/30/15 9/15/15 11/20/15 1/22/16 3/25/16 7/27/16 9/22/16 10/21/16 | P | P | P | Prepare and Post DAL
| 1/1/12 4/1/12 5/1/12 11/1/12 1/1/13 4/1/13 7/1/13 9/2/13 11/15/13 1/15/14 4/1/14 6/1/14 7/1/14 9/1/14 2/1/15 4/10/15 6/1/15 7/13/15 10/1/15 12/11/15 2/19/16 4/22/16 8/29/16 10/13/16 11/18/16 | P | P | P | Implement expanded hospice benefit in NYS
| TBD | 8 | 8 | 8 | Note: This item is being removed because these demonstration projects were not announced by CMS and are not expected to happen. Encourage NYS hospices to apply to participate in CMS's 15 three-year demonstration projects to evaluate impact of concurrent hospice and curative care for adults when available. Demonstration in design phase and presently not funded. Anticipated project date not known.

## Boo Yah
BOO-YAH!